## BACKGROUND
1. Background
1.1. Legislative Requirement
Section 40 of the Municipal Systems Act 32 of 2000 as amended outlines that a Municipality must establish mechanisms to monitor and review its Performance Management System so as to measure, monitor, review, evaluate and improve performance of its organizational and departmental levels.
The Municipal Planning and Performance Management Regulations, 2001 stipulates that that a municipality’s performance management system entails a framework that describes and represents how the municipality’s cycle and processes of performance planning, monitoring, measurement, review, reporting and improvement will be conducted. Alfred Nzo District Municipality in compliance with the Performance Regulations developed and adopted its Performance Management System Policy Framework which gives an indication of the approach by the municipality towards performance management.
During the financial year under review, the municipality developed and adopted its Service Delivery and Budget Implementation Plan hence quarterly performance reports on implementation of municipality projects and programmes as per approved IDP, Budget and SDBIP were produced at the end of each quarter.
Section 46 (1) of the Municipal Systems Act 32 of 2000 as amended stipulates that a municipality must prepare for each financial year a performance report reflecting:
The performance of the municipality and each external provider during that financial year;
A comparison of the performance with target set for and performances in the previous financial year; and
Measures taken to improve performance.
It is against the above-mentioned background that Alfred Nzo District Municipality has drafted its Annual Performance Report for 2016/17 reflecting level of performance by the municipality and further reflects some comparison with the performance in the previous financial year (2015/16). The annual performance report reflects on the municipal performance per National Key Performance Area.
Signed By:
Executive Mayor
Cllr. S. Mehlomakhulu
Signed By:
Municipal Manager
Mr. Z.H. Sikhundla

## MUNICIPAL PERFORMANCE OVERVIEW
1.1. Municipal Performance Overview
The approach towards giving an overview in terms of the level of performance by the municipality during the 2016/17 financial year has been based on a number of projects or programmes the municipality set as targets to achieve in line with approved Integrated Development Plan and Service Delivery and Budget Implementation Plan. Projects and Programmes were categorized in relation to National Key Performance Areas and the level of performance by the municipality per KPA is highlighted. Two scenario measures have been used to assess the state of performance by the municipality and scenario are as follow:
Target Achieved
Target not achieved
Targets that are being categorized as achieved are those targets where the municipality completed or achieved 100% of the set target. Target not achieved are those targets that the municipality did not perform even a minimum level or where nothing at all was done.

## ALIGNMENT CRITERIA
1.3. IDP Alignment Criteria
1.3.1. Vision
A self-sustainable municipality that guarantees effective and efficient rural development
1.3.2. Mission
Creating a conducive environment, by improving human capabilities, enhancing relevant skills, and maximizing the utilization of natural resources in order to improve quality of life for its communities.
1.3.3. Core Values
Ø Integrity;
Ø Transparency;
Ø Professionalism
Ø Co-operation;
Ø Innovation;
Ø Accountability;
Ø Honesty;
Ø Fairness;
Ø Efficiency and effectiveness

## OBJECTIVES
1.3.4. Objectives
Index | National Key Performance Areas | Desired Outcome | Ref | Strategic Objective | Outcome 9 Output | Back To Basics | Pillar No.
A | Municipal Transformation And Organisational Development | Self-sustainable, compliant, efficient and capable Municipality | A1 | Improve organisation, capacity, knowledge and Transformation | Implement a differential approach to Municipal Financing, planning and support | Building Capable Local Government Institutions | 5
|  |  | A2 | Optimise systems, administration and operating procedures
|  |  | A3 | Increase performance and efficiency levels
B | Basic Service Delivery | Improved quality of life | B1 | Increase access to municipal services | Improved access to basic services | Delivering Basic Services | 2
|  |  | B2 | Improve the quality of Municipal Infrastructure services
|  |  | B3 | Improve the quality and flow of water and sanitation
C | Local Economic Development | Development in Rural areas and maximum utilisation of natural resources | C1 | Strengthen internal & external LED capacity | Implementation of Community works Programme and supported Cooperatives | N/a | N/a
|  |  | C2 | Improve economic viability
|  |  | C3 | Promote the earnings potential of ANDM Communities
D | Financial Viability And Financial Management | Self-sustainable, compliant, efficient and capable Municipality | D1 | Increase revenue collection | Improve Municipal Financial and Administrative Capability | Sound financial management and accounting | 4
|  |  | D2 | Improve expenditure management and controls
|  |  | D3 | Maximise economies of scale and value for money by complying with SCM policies.
|  |  | D4 | Improve budgeting, reporting and compliance.
|  |  | D5 | Optimise use of municipal assets
|  |  | D6 | Strengthen financial management system
E | Good Governance And Public Participation | Self-sustainable, compliant, efficient and capable Municipality | E1 | Promote Public participation and Good Meaningful Governance | Deepen Democracy through a refines Ward Committee System | Putting People First | 1 & 3
|  |  | E2 | Strengthen Governance and reduce risk |  | Good Governance
F | Cross Cutting Issues | Integrated Development and strong partnerships. | F1 | Improve Municipal planning and spatial development | One window of co-ordination | N/a | N/a
|  |  | F2 | Improve Disaster Management and Prevention
|  |  | F3 | Improve community and health and safety
|  |  | F4 | Improve Environmental Health & Safety
|  |  | F5 | Strengthen Intergovernmental Relations

## STATEMENT OF FINANCIAL PERFORMA
Statement of Financial Performance
Revenue
Revenue from exchange transactions
Service charges | 28,509,000 | (9,027,360) | 19,481,640 | 23,861,498 | 4,379,858
Rental of facilities and equipment
329,920 | (198,825) | 131,095 | 433,587 | 302,492
Agency services | - | - | - | 26,323 | 26,323
Other Income | 1,001,770,000 (937,777,264) | 63,992,736 | 2,131,635 | (61,861,101)
Interest received - investment | 8,000,000 | - | 8,000,000 | 8,107,691 | 107,691
Total revenue (excluding capital transfers and contributions)
1,038,608,920 (947,003,449) | 91,605,471 | 34,560,734 | (57,044,737)
Revenue from non-exchange transactions
Transfer revenue
Government grants & subsidies 1,104,428,000 | 35,405,000 1,139,833,000 | 957,429,188 (182,403,812)
Public contributions and donations
Total revenue from non- exchange transactions
Total revenue from exchange transactions'
Total revenue from non- exchange transactions'
- | - | - | 405,000 | 405,000
1,104,428,000 | 35,405,000 1,139,833,000 | 957,834,188 (181,998,812)
1,038,608,920 (947,003,449) | 91,605,471 | 34,560,734 | (57,044,737)
1,104,428,000 | 35,405,000 1,139,833,000 | 957,834,188 (181,998,812)
Total revenue | 2,143,036,920 (911,598,449) 1,231,438,471 | 992,394,922 (239,043,549)
Expenditure
Employee Cost | (213,766,586) | (9,477,428) | (223,244,014) | (235,595,403) | (12,351,389)
Remuneration of councillors | (9,293,963) | (46,314) | (9,340,277) | (8,917,832) | 422,445
Litigation expenditure | - | - | - | (2,817,114) | (2,817,114)
Depreciation and amortisation | (55,000,000) | - | (55,000,000) | (52,910,937) | 2,089,063
Finance costs | (36,369,175) | 35,408,929 | (960,246) | (2,518,719) | (1,558,473)
Lease rentals on operating lease | - | - | - | (2,584,135) | (2,584,135)
Debt Impairment | (20,000,000) | - | (20,000,000) | - | 20,000,000
Repairs and maintenance | (41,331,901) | (5,500,000) | (46,831,901) | (130,163,998) | (83,332,097)
Bulk purchases | (4,500,000) | (2,000,000) | (6,500,000) | (6,191,742) | 308,258
Contracted Services | - | - | - | (54,330,905) | (54,330,905)
Transfers and Subsidies | (20,000,000) | - | (20,000,000) | (23,679,419) | (3,679,419)
General Expenses | (281,381,399) | 3,734,951 | (277,646,448) | (115,787,694) | 161,858,754
Total expenditure | (681,643,024) | 22,120,138 | (659,522,886) | (635,497,898) | 24,024,988
| 2,143,036,920 | (911,598,449) | 1,231,438,471 | 992,394,922 | (239,043,549)
| (681,643,024) | 22,120,138 | (659,522,886) | (635,497,898) | 24,024,988
Operating surplus / (deficit) | 1,461,393,896 | (889,478,311) | 571,915,585 | 356,897,024 | (215,018,561)
Actuarial gains/losses | - | - | - | 184,738 | 184,738
Gain on non-current assets held for sale or disposal groups
- | - | - | 1,399,541 | 1,399,541
- | - | - | 1,584,279 | 1,584,279
1,461,393,896 (889,478,311) 571,915,585 | 356,897,024 (215,018,561)
- | - | - | 1,584,279 | 1,584,279
Surplus before Capex 1,461,393,896 (889,478,311) 571,915,585 358,481,303 (213,434,282) Deficit before taxation 1,461,393,896 (889,478,311) 571,915,585 358,481,303 (213,434,282) Surplus - - - - -
Surplus for the year from contiuning operations
1,461,393,896 (889,478,311) 571,915,585 | 358,481,303 (213,434,282)
Capex | (1,461,393,752) 889,478,167 (571,915,585) | - | 571,915,585
Surplus for the year from contiuning operations

## OVERALL PERFORMANCE
OVERALL PERFORMANCE
Unit | Total No. of targets | Targets Achieved | Targets not Achieved | % Achieved | % Not Achieved
Office of the Municipal Manager | 86 | 60 | 26 | 70% | 30%
Corporate Services | 47 | 41 | 6 | 87% | 13%
IDMS | 104 | 61 | 43 | 59% | 41%
Community Development Services | 60 | 39 | 21 | 65% | 35%
Planning & Economic Development | 28 | 22 | 6 | 79% | 21%
BTO | 59 | 44 | 15 | 75% | 25%
Total | 383 | 266 | 117 | 69% | 31%

## 11.1.1. OMM-Communications
11.1. OFFICE OF THE MUNICIPAL MANAGER
11.1.1. COMMUNICATIONS
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/2016 | Actual 2015/2016 | Annual Target 2016/2017 | Actual 2016/2017 | Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.1.1.1 | 01 Communication equipment procured | Procurement of audio visuals and Equipment | A2 | Optimise systems, administration and operating procedures | Number of communication equipment procured | 600000 | VOTE:CAPEX: 50110 | 1 | 1 | 1 Communication equipment procured by 30 June 2017 | Achieved | Y | 0 | 27600 | None | None | Order & Invoices | Y | Not Applicable
11.1.1.2 | 04 Hiring of professional sound system major Council events | Audio and Visuals | A2 | Optimise systems, administration and operating procedures | Number of Hiring of professional sound system major Council events |  | Opex: 11100 44007 | 4 | 4 | 4 Hiring of professional sound system major Council events by 30 June 2017 | Not Achieved | N |  |  | Major Council event was cancelled due to institutional financial challenges | Rescheduling of the Major Council event | Invoices of goods and services procured | Y | Not Applicable
11.1.1.3 | 15 activities branded and marketed | Branding and Marketing | A2 | Optimise systems, administration and operating procedures | Number of products procured to brand and market municipal programmes | R 1 500 000.00 | VOTE: OPEX: 111044013 | 1 | 1 | 15 activities branded and marketed by 30 June 2017 | Achieved | Y | R 1 500 000.00 | 1550999.76 | None | None | Branding and marketing products, | Y | Not Applicable
11.1.1.4 | 15 activities branded and marketed | Branding and Marketing | A2 | Optimise systems, administration and operating procedures | Number of website & intranet upgrade | 0 | N/a | 1 | 1 | 15 activities branded and marketed by 30 June 2017 | Achieved | Y | 0 | R0.00 | None | None | Invoices of website & intranet update | Y | Not Applicable
11.1.1.5 | 15 activities branded and marketed | Branding and Marketing | A2 | Optimise systems, administration and operating procedures | Number of Communication strategy review and induction sessions conducted | 0 | N/a | 1 | 1 | 15 activities branded and marketed by 30 June 2017 | Achieved | Y | 0 | R0.00 | None | None | Reviewed communications strategy and attendance register | Y | Not Applicable
11.1.1.6 | 15 activities branded and marketed | Branding and Marketing | A2 | Optimise systems, administration and operating procedures | Number of diaries, journals and calendars procured | 0 | N/a | 1 | 1 | 15 activities branded and marketed by 30 June 2017 | Achieved | Y | 0 | R0.00 | None | None | Diaries, journals & calendars | Y | Not Applicable
11.1.1.7 | 15 activities branded and marketed | Branding and Marketing | A2 | Optimise systems, administration and operating procedures | Number of annual communicators Awards event | 0 | N/a | 1 | 0 | 15 activities branded and marketed by 30 June 2017 | Achieved | Y | 0 | R0.00 | None | None | Attendance register | Y | Project was done in 2016/2017 financial year.
11.1.1.8 | 15 activities branded and marketed | Branding and Marketing | A2 | Optimise systems, administration and operating procedures | Number new items posted on the website, intranet and social media networks annually. | 0 | N/a | 400 | 817 | 15 activities branded and marketed | Achieved | Y | 0 | 0 | None | None | Copies of items posted on website, intranet and social media networks | Y | Not Applicable
11.1.1.9 | 4 Newsletters Produced annually | Newsletter and leaflets Production | E1 | Promote Public participation and Good Meaningful Governance | Number of newsletters produced and distributed. | 200000 | VOTE:111044070 | 4 | 6 | 4 Newsletters Produced annually by 30 June 2017 | Achieved | Y | 200000 | 165764.74 | None | None | Copies of publications produced | Y | Not Applicable
11.1.1.10 | 06 leaflets produced Annually | Newsletter and leaflets Production | E1 | Promote Public participation and Good Meaningful Governance | Number of leaflets produced |  |  | 12 | 12 | 06 leaflets produced Annually by 30 June 2017 | Achieved | Y |  |  | None | None | Copies of Publications | Y | Not Applicable
11.1.1.11 | 02 Newsletters produced | Newsletter and leaflets Production | E1 | Promote Public participation and Good Meaningful Governance | Number of eaflets to be translated |  |  | 4 | 4 | 02 Newsletters produced by 30 June 2017 | Achieved | Y |  |  | None | None | Copies of the new publications | Y | Not Applicable
11.1.1.12 | 02 signage activities done annually | Signage | E1 | Promote Public participation and Good Meaningful Governance | Number of procurement signage for municipal facilities done annually | 0 | 111044092 | 2 | 2 | 02 signage activities done annually by 30 June 2017 | Achieved | Y | 0 | R0.00 | None | None | Samples of signage products and invoices | Y | Not Applicable
11.1.1.13 | 30 municipal programmes publicized | Publicity and Awareness Costs | E1 | Promote Public participation and Good Meaningful Governance | Number of municipal programmes published | 2100000 | 111044084 | 30 | 41 | 30 municipal programmes publicized by 30 June 2017 | Achieved | Y | 2100000 | 1320724.3 | None | None | Audio clips, cuttings and photos | Y | Not Applicable
11.1.1.14 | 30 municipal programmes publicized | Publicity and Awareness Costs | E1 | Promote Public participation and Good Meaningful Governance | Number of Panel Discussion conducted annually |  |  | 3 | 3 | 30 municipal programmes publicized by 30 June 2017 | Achieved | Y |  |  | None | None | Attendance register and photos | Y | Not Applicable
11.1.1.15 | 30 municipal programmes publicized | Publicity and Awareness Costs | E1 | Promote Public participation and Good Meaningful Governance | Number of Phuhla Alfred Nzo Radio programmes conducted annually |  |  | 30 | 30 | 30 municipal programmes publicized by 30 June 2017 | Achieved | Y |  |  | None | None | Audio Clips and Photos | Y | Not Applicable
11.1.1.16 | 30 municipal programmes publicized | Publicity and Awareness Costs | E1 | Promote Public participation and Good Meaningful Governance | Number of Media Engagements session conducted annually |  |  | 4 | 4 | 04 Media engagement by June 2017 | Achieved | Y |  |  | None | None | Attendance registers | Y | Not Applicable
11.1.1.17 | 2 Legacy & Heritage (LH) programmes conducted | Heritage and Legacy Programmes | E1 | Promote Public participation and Good Meaningful Governance | Number of Legacy programmes – cultural festival and heritage month conducted as part of Heritage Month activities | R500 000.00 |  | 2 | 2 | 2 Legacy & Heritage (LH) programmes conducted by 30 June 2017 | Achieved | Y | R500 000.00 | 0 | None | None | Attendance registers and photos | Y | Not Applicable
11.1.1.18 | 12 community outreaches conducted quarterly | Community Outreaches | E2 | Strengthen Governance and reduce risk | Number of community outreaches conducted annually | R 300 000.00 | 111044021 | 12 | 12 | 12 community outreaches conducted quarterly | Achieved | Y | R 300 000.00 | 213711 | None | None | Attendance registers and photos | Y | Not Applicable

## 11.1.2 IGR
OFFICE OF THE MUNICIPAL MANAGER
11.1.2. INTERGOVERNMENTAL RELATIONS
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/2016 | Actual 2015/2016 | Annual Target 2016/2017 | Actual 2016/2017 | Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.1.2.1 | 4 IDP rep forum supported | IGR and Stakeholders management | A2 | Strengthen Intergovernmental Relations | Number of IDP Rep Forums Supported | R 500 000.00 |  | None | None | 4 IDP rep forum supported by 30 June 2017 | 4 IDP rep forums coordinated | Y | R 500 000.00 | 539356.68 | None | None | Attendance register and report | Y | Not Applicable
11.1.2.2 | 4 stakeholders meeting convened | IGR and Stakeholders management | F5 | Strengthen Intergovernmental Relations | Number of Technical Forums held with stakeholders |  |  | None | None | 4 stakeholders meeting convened by 30 June 2017 | 4 IGR Sub Forums held with stakeholders | Y |  |  | None | None | Attendance register and report | Y | Not Applicable
11.1.2.3 | 4 stakeholders meeting convened | IGR and Stakeholders management | F5 | Strengthen Intergovernmental Relations | Number of District Mayor’s Forum held with stakeholders |  |  | 4 | 4 | 4 stakeholders meeting convened by 30 June 2017 | 4 District Mayors Forums held with stakeholders | Y |  |  | None | None | Attendance register and report | Y | Not Applicable
11.1.2.4 | 4 Bilateral or multilateral meetings held | Municipal cooperative agreements | F5 | Strengthen Intergovernmental Relations | Number of bilateral or multilateral meeting held locally or international. | R 800 000.00 |  | 4 | 4 | 4 Bilateral or multilateral meetings held by 30 June 2017 | 4 Bilateral or Multilateral meetings held | Y | R 800 000.00 | 703357.46 | None | None | Bilateral or Multinational report | Y | Not Applicable
(MIR & Protocol)

## 11.1.3 IA
OFFICE OF THE MUNICIPAL MANAGER
11.1.3. INTERNAL AUDIT
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/2016 | Actual 2015/2016 | Annual Target 2016/2017 | Actual 2016/2017 | Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.1.3.1 | 1 Adopted internal audit plan | Develop strategic internal audit plan. | A2 | Optimise systems, administration and operating procedures | Number of Internal Audit Plan developed and adopted by Audit Committee | R200 000.00 |  | 100% | 100% | 1 Adopted internal audit plan by 30 June 2017 | 1 Adopted internal audit plan by 30 June 2017 | Y | R200 000.00 | 0 | None | None | Approved Internal Audit Plan | Y | Not applicable as the set targets were met in the previous financial year
[17 empty] | Audit Committee minutes | Y
11.1.3.2 | Updated Dashboard Report | Maintain Dashboard report | A2 | Optimise systems, administration and operating procedures | % of updated dashboard reports | 0 |  | None | None | Updated Dashboard Report by 30 June 2017 | 4 updated Dashboard reports by 30 June 2017 | Y | 0 | 0 | None | None | Dashboard report | Y | Not applicable as the set targets were not set in the previous financial year
11.1.3.3 | Monitor and report on implementation of AG plan | Follow-up on implementation of management action plan | A2 | Optimise systems, administration and operating procedures | Number of follow-ups IA and AG conducted | 0 |  | 2 | 2 | Monitor and report on implementation of AG plan by 30 June 2017 | 4 Follow up reviews done on the implementation of management action Plan | Y | 0 | 0 | None | None | Internal Audit Report | Yes | Not applicable as the set targets were met in the previous financial year
[17 empty] | Audit Committee minutes | Yes
11.1.3.4 | Internal Audit Methodology updated | Revise internal audit methodology | A2 | Optimise systems, administration and operating procedures | % of Internal Audit Methodology Revised | R 200 000.00 |  | 100% | 100% | Internal Audit Methodology updated by 30 June 2017 |  | N | R 200 000.00 | 0 | The IA methodology was not revised due to lack of funds | The non achieved target will be addressed during the financial year 2017-18 | Revised Internal Audit Methodology | N | Not applicable as the set targets were met in the previous financial year
11.1.3.5 | Completed mandatory Internal Audit assignments | Co-sourced specialised and mandatory Internal Audit Assignments | A2 | Optimise systems, administration and operating procedures | % of completed mandatory Internal audit assignments | R800 000.00 |  | None | None | 4 Completed mandatory Internal Audit assignments by 30 June 2017 | 4 Completed mandatory Internal Audit assignments by 30 June 2017 | Y | R800 000.00 | 1421628.99 | None | None | Audit Committee minutes | Yes | Not applicable as the set targets were not set in the previous financial year
[17 empty] | Internal Audit Reports | Yes
11.1.3.6 | Completed specialized Internal Audit Assignments |  | A2 | Optimise systems, administration and operating procedures | % of completed co-sourced specialized Internal audit assignments |  |  | None | None | 4 Completed specialized Internal Audit Assignments by 30 June 2017 | 3 Completed specialized Internal Audit Assignments by 30 June 2017 | N |  |  | The ICT audit was not performed due to lack of funds | The non achieved target will be addressed during the financial year 2017-18 | Audit Committee minutes | Yes | Not applicable as the set targets were not set in the previous financial year
11.1.3.7 | 6 audit committee meetings held. | Maintain effective Audit Committee | E2 | Strengthen Governance and reduce risk | Number of audit committee meeting held. | 600000 |  | 6 | 5 | 6 audit committee meetings held by 30 June 2017 | 4 | N | 600000 | 357120 | The variance was due to non-sitting of audit committee meeetings as a result of postponements | Calendar of audit committee meetings will be circulated to all audit committee members, and compliance to it will also be enhanced year 2017-18 | Invitation letters | Yes | Calendar of audit committee meetings will be circulated to all audit committee members, however due to postponements of some of the meetings, the target was still not met

## 11.1.4. OMM-LEGAL SERVICES
OFFICE OF THE MUNICIPAL MANAGER
11.1.4. LEGAL SERVICES
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/2016 | Actual 2015/2016 | Annual Target 2016/2017 | Actual 2016/2017 | Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.1.4.1 | Legislatively compliant Policies | Analysis of Policies submitted for vetting | A2 | Optimise systems, administration and operating procedures | % of ANDM Policies analysed | 0 | OPEX | 100% | 100% | 100% of ANDM Policies analysed by 30 June 2017 | 0% ANDM Policies Aalysed | N | 0 | R 0-00 | Non submitted | Annual review to be effected by departments | Submission Register | N | Not Applicable
11.1.4.2 | Legislatively compliant Policies | Legal Services | A2 | Optimise systems, administration and operating procedures | % of ANDM cases attended to | 2000000 | 1110044053 | None | None | 100% ANDM cases attended to by 30 June 2017 | 100% ANDM cases attended to by 30 June 2017 | Y | 2000000 | R 2 000 000-00 | None | None | Reports from Attorneys | Y | Not Applicable
11.1.4.3 | Legislatively compliant Policies | Legal support and representation | A2 | Optimise systems, administration and operating procedures | % of Contracts drafted, analysed and vetted | 0 | OPEX | 100% | 100% | 100% Contracts drafted, analysed and vetted by 30 June 2017 | 100% Contracts drafted, analysed and vetted by 30 June 2017 | Y | 0 | R 0-00 | None | None | Signed Contracts Register | Y | Not Applicable
11.1.4.4 | Legislatively compliant Policies | Legal support and representation | E2 | Strengthen Governance and reduce risk | Number of compliance Circulars Developed | 0 | OPEX | 12 | 12 | 12 compliance Circulars Developed by 30 June 2017 | 12 compliance Circulars Developed by 30 June 2017 | Y | 0 | R 0-00 | None | None | Issued circulars register | Y | Not Applicable
11.1.4.5 | Adopted By-laws which are legally compliant | Development and Review of bylaws | E2 | Strengthen Governance and reduce risk | Number of reviewed and/or By-laws | 100000 | OPEX | 6 | 0 | 6 reviewed and/or By-laws by 30 June 2017 | None | N | 100000 | R 0-00 | Financial constraints | Availability of funds | Council resolution. | N | Project to be done in 2016-2017 financial year
[17 empty] | Attendance Registers. | N
11.1.4.6 | Legally compliant Municipalities within ANDM | District Legal Services forum | F5 | Strengthen Intergovernmental Relations | Number of Fully Functionally District Legal Services Forum | 0 | OPEX | 1 | 1 | 1 Fully Functionally District Legal Services Forum by 30 June 2017 | None | N | 0 | R0.00 | None | None | Signed Terms of Reference. | Y | Not Applicable
[17 empty] | Attendance registers. | Y

## 11.1.5. OMM-OMM
OFFICE OF THE MUNICIPAL MANAGER
11.1.5. OFFICE OF THE MUNICIPAL MANAGER
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/2016 | Actual 2015/2016 | Annual Target 2016/2017 | Actual 2016/2017 | Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.1.5.1 | 1 Municipal Planning calendar developed | Municipal Planning Calendar | A2 | Optimise systems, administration and operating procedures | Number of Municipal Planning calendar developed | 0 | N/a | 1 | 1 | 1 Municipal Planning calendar developed by 30 June 2017 | 1 municipal calender developed by 30 June 2017 | Y | 0 | 0 | None | None | Council Resolution | Y | Not Applicable
[17 empty] | Calendar | Y
11.1.5.2 | 4 Sessions to Monitor the implementation of the Municipal Calendar | Municipal Planning Calendar | A2 | Optimize systems, administration and operating procedures | Number of Quarterly monitoring sessions on the Implementation of the Municipal Planning Calendar held | 0 | N/a | 4 | 4 | 4 Quarterly monitoring sessions on the Implementation of the Municipal Planning Calendar held by 30 June 2017 | 4 Quarterly monitoring sessions on the Implementation of the Municipal Planning Calendar held through management sessions by 30 June 2017 | Y | 0 | 0 | None | None | Council Resolution | Y | Not Applicable
[17 empty] | Calendar | Y
[17 empty] | Agenda | Y
11.1.5.3 | 1 Performance Management Review | Development of PMS Framework | A3 | Increase performance and efficiency levels | Monitoring and evaluation strategy developed and adopted | 300000 |  | None | None | 1 Monitoring and evaluation strategy developed and adopted by 30 June 2017 | 1 PMS Framework developed and adopted by Council | Y | 300000 | 0 | The budget was no spent due to financial constraints | None | SLA | Y | Not Applicable
11.1.5.4 | 2 SDBIP Monitoring and Evaluation sessions for managers held in a year | SDBIP Monitoring and Evaluation for Management | A3 | Increase performance and efficiency levels | Number of SDBIP Monitoring and Evaluation sessions for managers held annually | 1797500 | 1100044128 | 2 | 4 | 2 SDBIP Monitoring and Evaluation sessions for managers held annually by 30 June 2017 | 2 SDBIP Monitoring and Evaluation sessions for Managers held | Y | 1797500 | 0 | The budget was no spent due to financial constraints | None | Concept Document | Y | Not Applicable
[17 empty] | Invitations | Y
[17 empty] | Attendance Register | Y
[17 empty] | Report | Y
11.1.5.5 | 4 Poverty Alleviation Programmes implemented | Poverty Alleviation | E1 | Promote Public participation and Good Meaningful Governance | Number of Poverty Alleviation Programmes conducted | R 700 000.00 | 1100044212 | 4 | 4 | 4 Poverty Alleviation Programmes conducted by 30 June 2017 | 4 Poverty Alleviation Programmes conducted by 30 June 2017 | Y | R 700 000.00 | R 700 000.00 | None | None | Advert | Y | Not Applicable
11.1.5.7 | 4 Mayoral/ EXCO outreaches held annually | Mayoral/ EXCO Outreaches | E1 | Promote Public participation and Good Meaningful Governance | Number of Mayoral / EXCO outreaches for all four local municipalities within the district | R 500 000.00 | 1100044323 | 4 | 4 | 4 Mayoral / EXCO outreaches for all four local municipalities within the district by 30 June 2017 | 4 Mayoral / EXCO outreaches for all four local municipalities within the district by 30 June 2017 | Y | R 500 000.00 | R 500 000.00 | None | None | Concept Document | Y | Not Applicable
[17 empty] | Implementation Plan | Y
[17 empty] | Attendance Register | Y
11.1.5.8 | 4 Mayoral Intervention programmes held | Mayoral Intervention Programmes | E1 | Promote Public participation and Good Meaningful Governance | Number of Mayoral Intervention Programmes | R 700 000.00 | 1100044322 | 4 | 8 | 4 Mayoral Intervention Programmes by 30 June 2017 | 4 Mayoral Intervention Programmes by 30 June 2017 | Y | R 700 000.00 | R 700 000.00 | None | None | Advert | Y | Not Applicable
[17 empty] | Orders | Y
[17 empty] | Delivery note | Y
11.1.5.9 | 1 SDBIP reports developed and submitted | Development and Implementation of the SDBIP | E2 | Strengthen Governance and reduce risk | Number of SDBIPs Developed for the year | 0 | 0 | 24 | 24 | 4 SDBIPs Developed for the year by 30 June 2017 | 4 SDBIPs Developed for the year by 30 June 2017 | Y | 0 | 0 | None | None | Quarterly reports & Email | Y | Not Applicable
11.1.5.10 | 12 Senior Management meetings held annually | Senior Management Meetings | E2 | Strengthen Governance and reduce risk | Number of Senior Management meetings held annually | 0 | 0 | 24 | 24 | 12 Senior Management meetings held annually | 12 Senior Management meetings held annually | Y | 0 | 0 | None |  | Terms of Reference | Y | Not Applicable
[17 empty] | Invitation Letters | Y
[17 empty] | Attendance Register | Y
[17 empty] | Minutes | Y
11.1.5.11 | 12 Extended Management meetings held | Extended Management Meetings | E2 | Strengthen Governance and reduce risk | Number of Extended Management meetings held annually | 0 | NONE | 12 | 16 | 12 Extended Management meetings held by 30 June 2017 | 12 Extended Management meetings held by 30 June 2017 | Y | 0 | 0 | None | None | Terms of Reference | Y | Not Applicable
[17 empty] | Invitation Letters | Y
[17 empty] | Attendance Register | Y
[17 empty] | Minutes | Y

## 11.1.6 OMM- OFFICE OF THE SPEAK
OFFICE OF THE MUNICIPAL MANAGER
11.1.6. OFFICE OF THE SPEAKER
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/2016 | Actual 2015/2016 | Annual Target 2016/2017 | Actual 2016/2017 | Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.1.6.1 | Four study groups and workshop conducted | Council Study Groups and workshops | A1 | Improve organisation, capacity, knowledge and Transformation | Number of Council Study Groups and workshops conducted | 150000 | 1106044080 | 4 | 4 | 3 Council Study Groups and workshops conducted by 30 June 2017 | 4 Council Study Groups held | Y | 150000 | 0 | None | None | Reports and Attendance register | Y | Not Applicable
11.1.6.2 | Review & print 1 Standing Rules Booklet | Review & Printing 0f Standing Rules | A1 | Improve organisation, capacity, knowledge and Transformation | Number of Standing Rules Booklets reviewed and printed | 0 | 1105044128 | 2 | 0 | 2 Standing Rules Booklets reviewed and printed by 30 June 2017 | The review of Council Rules and Orders not done | N | 0 | 0 | Target could not be done in the last quarter due to lack of funds in the municipality | To be held in the next financial eyar | None | N
[17 empty] | None | N
11.1.6.3 | Coordination of capacity building initiatives for councillors and traditional leaders in Council | Capacity building for councillors | A1 | Improve organisation, capacity, knowledge and Transformation | Number of Workplace Skills Plans submitted for the Training of Councillors | R0,00 | N/a | None | None | 1 Workplace Skills Plans submitted for the Training of Councillors by 30 June 2017 | Skills Aufdit done for the training needs of councillors | Y | R0,00 | 0 | None | None | Skills audit form submitted to form part of the WSP; | Y | Not Applicable
[17 empty] | Copy of the Workplace Skills Plan (WSP) covering councillors | Y
11.1.6.4 | Development of a concept document in preparation for the stakeholder consultative session | Community Structures for Consultation | A2 | Optimise systems, administration and operating procedures | Number of Public participation policy reviewed | 0 | n/a | 1 | 1 | 1 Public participation policy reviewed by 30 June 2017 | Public Participation Policy reviewed during the Policy Review session | Y | 0 | 0 | None | None | Policy template done to identify gaps in current policies | Y | Not Applicable
11.1.6.5 | Council Chamber upgraded | Council Chamber upgarde | B2 | Improve the quality of Municipal Infrastructure services | Number of Council chambers upgraded | 0 | 1105044132 | None | None | 1 Council chambers upgraded by 30 June 2017 | Council Chambers upgraded in the first quarter of the financial year | Y | 0 | R21 750, 00 | None | None | Terms of reference; | Y | Not Applicable
[17 empty] | Purchase order for the fixing of the Council Chambers | Y
11.1.6.6 | Public engagement sessions | Enhance culture of community engagement |  | Enhance Sound Governance through public participation | Number of public engagement sessions held | R0,00 | N/a | None | None | 1 public engagement sessions held by 30 June 2017 | No stakeholder engagement session held | N | R0,00 | 14000 | Target could not be done in the last quarter due to lack of funds in the municipality | To be held in the next financial eyar | None | y | Not Applicable
11.1.6.7 | One Open Council Day held annually | Open Council Day (State of the District Address) | E1 | Promote Public participation and Good Meaningful Governance | Number of Open Council Day held annually | 2750000 | 110544073 | 1 | 1 | 1 Open Council Day held annually by 30 June 2017 | No Open Council Day held | N | 2750000 | 0 | Target could not be done in the last quarter due to lack of funds in the municipality | To be held in the next financial eyar | None | N | Not Applicable
11.1.6.8 | Four community structures engagement held | Round table discussion with specific sector groups | E1 | Promote Public participation and Good Meaningful Governance | Number of community structures engagement held | 0 | N/A | 4 | 4 | 3 community structures engagement held by 30 June 2017 | 2 Community engagement sessions held | N | 0 | 302950 | Target could not be done in the last quarter due to lack of funds in the municipality | To be held in the next financial eyar | Attendance register | Y | Not Applicable
11.1.6.9 | Four Oversight and Service Delivery Monitoring visits held annually | Public Participation | E1 | Promote Public participation and Good Meaningful Governance | Number of Oversight and Service Delivery Monitoring visits of government programmes conducted | 700000 | 1105044082 | 4 | 4 | 3 Public participation and Good Meaningful Governance by 30 June 2017 | Three (3) Oversight visits held | Y | 700000 | 280730 | None | None | Report to Council; Attendance register | Y | Not Applicable
11.1.6.10 | Four Moral Regeneration Workshops Conducted | Moral Regeneration Programmes | E1 | Promote Public participation and Good Meaningful Governance | Number Moral Regeneration Workshops conducted | 150000 | 1105044129 | 4 | 4 | 4 Moral Regeneration Workshops conducted by 30 June 2017 |  | Y | 150000 | R25 870. 00 | None | None | Attendance registers | Y | Not Applicable
11.1.6.11 | 1 Africa Month conducted | Africa Month Programmes | E1 | Promote Public participation and Good Meaningful Governance | Number of Africa Month Programmes coordinated | 100000 | 1105044130 | 1 | 0 | 1 Africa Month Programmes coordinated by 30 June 2017 | No Africa Month Programme held | N | 100000 | 0 | Target could not be done in the last quarter due to lack of funds in the municipality | To be held in the next financial eyar | None | N
11.1.6.12 | Empower citizenry about their rights and government services | Know your services campaign | E1 | Promote Public participation and Good Meaningful Governance | Number of campaigns organised in making the communities aware of their rights and government services | R0,00 | N/a | None | None | 1 campaign organised in making the communities aware of their rights and government services by 30 June 2017 | The campaign wasn’t held by the stipulated timeline | N | R0,00 | 0 | Target could not be done in the last quarter due to lack of funds in the municipality | To be held in the next financial eyar | None | N | Not Applicable
11.1.6.13 | 4 MPAC meetings convened | Municipal public accounts committee | E2 | Strengthen Governance and reduce risk | Number of MPAC meetings held | 200000 | 1105044126 | 4 | 4 | 4 MPAC meetings held by 30 June 2017 | Five (5) Meetings/ workshop held by the MPAC | Y | 200000 | 51051 | Not applicable | N/A | Report, and | Y | Not Applicable
[17 empty] | Attendance register | Y
11.1.6.14 | 4 quarterly Council and Committee sittings held | Council and Committee Sittings | E2 | Strengthen Governance and reduce risk | Number of Council and Committee sittings held | 0 | N/A | 4 | 14 | 4 Council and Committee sittings held by 30 June 2017 | Thirteen (13) Council meetings held | Y | 0 | 0 | An increase in the number of Council meetings was caused by a number of key matters that needed adoption by Council | Target to be revised in the next financial year | Attendance register, Council Resolutions Register and Committee Reports | Y | Not Applicable
11.1.6.15 | 4 Whippery meetings held | Whippery Programmes | E2 | Strengthen Governance and reduce risk | Number of Whippery meetings held. | 45000 | 1106044213 | 4 | 8 | 4 Whippery meetings held by 30 June 2017 | Two (2) Whippery meetings held | N | 45000 | 0 | Target could not be done in the last quarter due to lack of funds in the municipality | Target to be revised in the next financial year | Minutes of the Whippery meetings | Y | Not Applicable
[17 empty] | Attendance register | Y
11.1.6.16 | 4 Council Caucus meetings convened | Council caucus | E2 | Strengthen Governance and reduce risk | Number of Council Caucus meetings held | 100000 | 1106044217 | 4 | 14 | 4 Council Caucus meetings held by 30 June 2017 | Thirteen (13) Caucus meetings held | Y | 100000 | 0 | An increase in the number of Council meetings was caused by a number of key matters that needed adoption by Council | Target to be revised in the next financial year | Attendance registers | Y | Not Applicable
11.1.6.17 | 4 meetings held | District speakers forum | F5 | Strengthen Intergovernmental Relations | Number of District Speakers Forum meetings held | 100000 | 1105044131 | 4 | 3 | 4 District Speakers Forum meetings held by 30 June 2017 | Four (4) District Speakers Forum Meetings held | Y | 100000 | 48044.18 | None | None | Report of the Speakers Forum | Y
[17 empty] | & Attendance register | Y
11.1.6.18 | Four Constituency Work meeting convened | Constituency Work | F5 | Strengthen Intergovernmental Relations | Number of Constituency Work meeting held. | 500000 | 1106044214 | 4 | 4 | 4 Constituency Work meeting held by 30 June 2017 | Fove (5) Constituency meetings held | Y | 500000 | 0 | None | None | Report and Attendance register | Y | Not Applicable
11.1.6.19 | One Councillor Induction Worksop | Induction of Councillors |  | Improve Institutional Development and Municipal Transformation | Number of Councillor Induction Workshops held | 410000 |  | None | None | None | None | N | 410000 | 0 | None | None | None | N | Not Applicable

## 11.1.7 RISK MANAGEMENT
OFFICE OF THE MUNICIPAL MANAGER
11.1.7. RISK MANAGEMENT
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/2016 | Actual 2015/2016 | Annual Target 2016/2017 | Actual 2016/2017 | Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.1.7.1 | 1 Risk Management Software procured | Risk, audit and compliance software | A2 | Optimise systems, administration and operating procedures | Number of Risk Management Software’s procured | R 400 000.00 |  | None | None | 1 Risk Management Software’s procured by 30 June 2017 | Not achieved | N | R 400 000.00 | R0.00 | No funds to fund this project. | Theis project was taken out of the SDBIP for 16/17 and has not been catered for 17/18 until the municipality recover from financial challenges, this project will then reconsidred. | None | N | Not Applicable
11.1.7.2 | Risk Assessment workshop held | Risk Assessment workshop (IT and fraud enterprise) | E2 | Strengthen Governance and reduce risk | Number of Risk assessment workshop held | R200 000.00 | 111044216 | 4 | 1 | 4 Risk assessment workshop held by 2017 | Achieved; risk assessment were conducted as planned. | Y | R200 000.00 | R99 860.00 | None | None | Risk Registers | Y | Project was completed in 2016/2017 financial year
11.1.7.3 | Reviewed Risk Assessment Framework | Review of Risk management framework | E2 | Strengthen Governance and reduce risk | Number of Reviewed Risk assessment framework | R 150 000.00 |  | None | None | 1 Reviewed Risk assessment framework by 30 June 2017 | Achieved, risk management framework was reviewed. | Y | R 150 000.00 | R190 480.00 | None | None | Copy of the reviewed and finanal Risk Management Framework. | Y | Not Applicable
11.1.7.4 | Reviewed Fraud prevention plan | Review of Fraud prevention Plan | E2 | Strengthen Governance and reduce risk | Number of Reviewed Fraud prevention plan | R 150 000.00 | 111044216 | None | None | 1 Reviewed Fraud prevention plan by 30 June 2017 | Not achieved | N | R 150 000.00 | R0.00 | Due to the lack of funds, this project was differed to the next financial year | The project is budgeted in 17/18 financial year and will be implemented as per the SDIP | None | N | Not Applicable
11.1.7.5 | Reviewed Anti-corruption strategy | Development and review of anti-corruption strategy | E2 | Strengthen Governance and reduce risk | Number of Anti – corruption strategy developed | R150 000.00 |  | None | None | 1 Anti – corruption strategy developed by 30 June 2017 | Achieved, Anti-corruption strategy was developed and adopted by Council | Y | R150 000.00 | R198 499.99 | None | None | Anti-corruption strategy | Y | Not Applicable
11.1.7.6 | Completed Business continuity strategy | Development of Business continuity Strategy | E2 | Strengthen Governance and reduce risk | Number of business continuity strategy completed | 0 | N/a | None | None | 1 business continuity strategy completed by 30 June 2017 | Achieved, the draft BCS is in place. | Y | 0 | R0.00 | None | None | Draft Business Continuity Strategy | Y | Not Applicable
11.1.7.7 | Remunerated risk committee members | Remuneration of risk committee members | E2 | Strengthen Governance and reduce risk | Number of Risk Management Committee meetings Convened | R 100 000.00 | 111044216 | None | None | 4 Risk Management Committee meetings Convened by 30 June 2017 | Not Acieved, two Risk Management Committee meeting. | N | R 100 000.00 | R80 220.00 | None payment of the Chairperson of the Risk Management Committee has resulted in the none sitting of the regulated number of meetings. | A proposed remuneration stracture of the Chairperson will be tabled to the Mayoral Committee which will then eliminate the disputing of the claims submitted to BTO. | Minutes of the meeting and attendance register. | Y | Not Applicable

## 11.1.8 OMM_SPU
OFFICE OF THE MUNICIPAL MANAGER
11.1.8. SPECIAL PROGRAMMES UNIT
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/2016 | Actual 2015/2016 | Annual Target 2016/2017 | Actual 2016/2017 | Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.1.8.1 | 10 Financially assisted students | Mayoral Education Intervention Programme | A1 | Improve organisation, capacity, knowledge and Transformation | Number of assisted pupils | R 500 000.00 |  | None | None | 10 Financially assisted students by 30 June 2017 | 10 Financial Assisted students and schools by 30 June 2017 Awarness on Mayoral Busary conducted | Y | R 500 000.00 | 0 | None | None | Draft Policy | Y | Not Applicable
[17 empty] | Concept Document | Y
[17 empty] | List of Beneficiaries | Y
11.1.8.2 | 1 Completed construction of youth office | Completion of Youth office | B1 | Increase access to municipal services | Number of construction completed | 78832.1 |  | None | None | 1 construction completed by 30 Jnue 2017 | TOR's and Specification for 2nd phase done | Y | 78832.1 | 0 | None | None | TOR’s | Y | Not Applicable
11.1.8.3 | 9 Disability programmes coordinated and supported | District Disability programmes, Care Support and Implementation | E2 | Promote Public participation and Good Meaningful Governance | Number of Disability programmes coordinated and supported | R 340 000.00 | 1115044032 | 9 Disability programmes coordinated and supported by 30 June 2016 | 9 Disability programmes coordinated and supported by 30 June 2016 | 8 Disability programmes coordinated and supported by 30 June 2017 | 8 Disability programmes coordinated and supported by 30 June 2017 | Y | R 340 000.00 | 350503.95 | None | None | Report and Attendance register | Y | Not Applicable
11.1.8.4 | 2 Disability forum meetings conducted |  | E2 | Promote Public participation and Good Meaningful Governance | Number of Disability Forum Meetings conducted | [5 empty] | 2 Disability Forum Meetings conducted by 30 June 2017 | Y |  |  | None | None | None | Y | Not Applicable
11.1.8.5 | 4 Special groups initiatives programmes supported | SPU Mainstreaming | E2 | Promote Public participation and Good Meaningful Governance | Number of Special groups initiatives programmes supported | R 610 000.00 | 1115044232 | 4 Special groups initiatives programmes supported by 30 June 2016 | 4 Special groups initiatives programmes supported by 30 June 2016 | 4 Special groups initiatives programmes supported by 30 June 2017 | 4 Special groups initiatives programmes supported by 30 June 2017 | Y | R 610 000.00 | 653244.5 | None | None | Report and attendance register | Y | Not Applicable
11.1.8.6 | 11 Youth development programmes coordinated and supported | Youth Development and transformation programme | E2 | Promote Public participation and Good Meaningful Governance | Number of Youth development programmes coordinated and implemented | 1900000 | 1115044113 | 15 Youth development programmes coordinated and implemented by 30 June 2016 | 15 Youth development programmes coordinated and implemented by 30 June 2016 | 11 Youth development programmes coordinated and implemented by 30 June 2017 | 09 Youth development programmes coordinated and implemented by 30 June 2017 | Y | 1900000 | 1898329.47 | Battle of Talents and MOU with institutions of Hire Leraning not done due to Municiapal Financial challenges | programmes will be done in 2017-2018 financial year | Concept Document; TOR’s; Report; Advert; MOU’s and Attendance register | Y | Not Applicable
11.1.8.7 | 2 District youth council meetings conducted |  | E2 | Promote Public participation and Good Meaningful Governance | Number of District Youth council meetings conducted |  |  | 4 District Youth council meetings conducted by 30 June 2016 | 4 District Youth council meetings conducted by 30 June 2016 | 2 District Youth council meetings conducted by 30 June 2017 | 1 District Youth Policy reviewed conducted by 30 June 2017 | Y |  |  | None | None | Reviwed policy | Y | Not Applicable
11.1.8.8 | 07 Older Persons programmes coordinated | Older Person’s Care and Support | E2 | Promote Public participation and Good Meaningful Governance | Number of Older Persons Programmes supported and coordinated | R 3 00 000.00 | 1115044207 | 7 Older Persons Programmes supported and coordinated by 30 June 2016 | 7 Older Persons Programmes supported and coordinated by 30 June 2016 | 7 Older Persons Programmes supported and coordinated by 30 June 2017 | 6 Older Persons Programmes supported and coordinated by 30 June 2017 | Y | R 3 00 000.00 | 328640.3 | Golden Games not done in Q 4 reason Municipal financial challenges | Programme will be done in Q1 2017-2018 | Report; Concept Document and attendance register | Y | Not Applicable
11.1.8.9 | 2 older person’s forum meeting conducted |  | E2 | Promote Public participation and Good Meaningful Governance | Number of Older Persons Forum Meetings Conducted |  |  | 4 Older Persons Forum Meetings Conducted by 30 June 2016 | 4 Older Persons Forum Meetings Conducted by 30 June 2016 | 2 Older Persons Forum Meetings Conducted by 30 June 2017 | 1 Older Persons Forum Meetings Conducted by 30 June 2017 | Y |  |  | None | None | Attendance register | Y | Not Applicable
11.1.8.10 | 08 children programmes coordinated and supported | Coordination of District Children’s development programmes, care and support | E2 | Promote Public participation and Good Meaningful Governance | Number of Children’s programmes coordinated and supported | R300 000.00 | 1115044230 | 11 Children’s programmes coordinated and supported by 30 June 2016 | 12 Children’s programmes coordinated and supported by 30 June 2016 | 8 Children’s programmes coordinated and supported by 30 June 2017 | 7 Children’s programmes coordinated and supported by 30 June 2017 | Y | R300 000.00 | 220346.5 | Early parenting indaba not done due to instituitional financial challenges | Programme will be done in Q1 2017-2018 | Report; attendance register; Concept Document and attendance register | Y | Not Applicable
11.1.8.11 | 1 Children’s Advisory Council Meetings sat |  | E2 | Promote Public participation and Good Meaningful Governance | Number of Children’s advisory council meetings conducted |  |  | None | None | 1 Children’s advisory council meetings conducted by 30 June 2017 | None | Y |  |  | 1 Advisory Council not sat reason none attendance of members | Annual Schedule be developed and sent to members in the beginning of the Year | None | N | Not Applicable
11.1.8.12 | 07 Gender programmes coordinated and supported | District Gender Programme | E2 | Promote Public participation and Good Meaningful Governance | Number of Gender programmes coordinated and supported | R320 000.00 | 1115044042 | 21 Gender programmes coordinated and supported by 30 June 2016 | 21 Gender programmes coordinated and supported by 30 June 2016 | 7 Gender programmes coordinated and supported by 30 June 2017 | 6 Gender programmes coordinated and supported by 30 June 2017 | Y | R320 000.00 | 277772.18 | Young Women against Gender Based Violence campaign not done due to municipal finacial challenges | will be done in 2017-2018 financial year | Concept Document; Report; and Attendance Register | Y | Not Applicable
11.1.8.13 | 2 Gender Forum Meetings Sat?? |  | E2 | Promote Public participation and Good Meaningful Governance | Number of Gender Forum Meetings conducted |  |  | None | None | 2 Gender Forum Meetings conducted by 30 June 2017 | 2 Gender Forum Meetings conducted by 30 June 2017 | Y |  |  | None | None | Attandance Register | Y | Not Applicable
11.1.8.14 | 8 HIV and AIDS awareness programmes conducted | HIV and AIDS; TB Awareness Programmes | F3 | Improve community and health and safety | Number of HIV and AIDS awareness campaigns conducted | R 100 000.00 | 1115044018 | 9 HIV and AIDS awareness campaigns conducted by 30 June 2016 | 9 HIV and AIDS awareness campaigns conducted by 30 June 2016 | 8 HIV and AIDS awareness campaigns conducted by 30 June 2017 | 8 HIV and AIDS awareness campaigns conducted by 30 June 2017 | Y | R 100 000.00 | 51150 | None | None | Concept document; Report and Attendance register | Y | Not Applicable
11.1.8.15 | 06 HIV and AIDS care and support programmes conducted | HIV and AIDS; TB Coordination Care and Support programmes | F3 | Improve community and health and safety | Number of HIV and AIDS awareness campaigns conducted | R 300 000.00 | 1115044018 | 11 HIV and AIDS awareness campaigns conducted by 30 June 2017 | 11 HIV and AIDS awareness campaigns conducted by 30 June 2016 | 6 HIV and AIDS awareness campaigns conducted by 30 June 2017 | 6 HIV and AIDS awareness campaigns conducted by 30 June 2016 | Y | R 300 000.00 | 265576.25 | None | None | 1 Concept Document; Report and Attendance Register | Y | Not Applicable
11.1.8.16 | 4 District AIDS Council/Consultative Sessions Conducted | HIV and AIDS ; TB Coordination Care and Support programme | F3 | Improve community and health and safety | Number of DAC Consultative sessions conducted |  |  | 4 DAC Consultative sessions conducted by 30 June 2016 | 4 DAC Consultative sessions conducted by 30 June 2016 | 4 DAC Consultative sessions conducted by 30 June 2017 | 3 DAC Consultative sessions conducted by 30 June 2017 | Y |  |  | 1 meeting not sat due to other institutional programmes | Annual Schedule be developed and sent to members in the beginning of the Year | Attendance register | Y | Not Applicable

## OMM PERFORMANCE
OFFICE OF THE MUNICIPAL MANAGER
ACHIEVED TARGETS VS NOT ACHIEVED BY UNIT
Unit | Total No. of targets | No. Achieved | No. Not Achieved | % Achieved | % Not Achieved
Communication | 18 | 17 | 1 | 94% | 6%
IGR | 4 | 4 | 0 | 100% | 0%
Internal Audit | 7 | 4 | 3 | 57% | 43%
Legal Services | 6 | 3 | 3 | 50% | 50%
Office of the Municipal Manager | 10 | 10 | 0 | 100% | 0%
Office of the Speaker | 18 | 10 | 8 | 56% | 44%
Risk Managerment | 7 | 4 | 3 | 57% | 43%
SPU | 16 | 8 | 8 | 50% | 50%
Department | 86 | 60 | 26 | 70% | 30%

## 11.2.1. CPS - ADMIN SUPPORT
11.2. CORPORATE SERVICES
11.2.1. Admin Support
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/2016 | Actual 2015/2016 | Annual Target 2016/2017 | Actual 2016/2017 | Targets Achieved (Y/N) | Annul Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.2.1.1 | A sound paperless information environment and safeguarded institutional memory | Maintenance of Records Management System | A2 | Optimise systems, administration and operating procedures | % of all Municipal documents centralized; scanned and archived in terms of the National Archives Act | R 500 000.00 | 50700154 | None | None | 100% of all Municipal documents centralised by scanned and archived in terms of National Archives Act by 30 June 2017 | Documents were collected to all departments and centralised in registey. Record scanning has not been started due to delays of payment due to them | Y | R 500 000.00 | R0.00 | No files have been purchased in this financial year hence no expenditure incurred | this project will be finalized in 2017-2018 financial year | List of document | Y | Not Applicable
[17 empty] | Reviewed File Plan | Y
11.2.1.2 | Legally compliant records management environment | Review records management policy and develop a records procedure manual | A2 | Optimise systems, administration and operating procedures | Number of records management policy reviewed | 0 | N/A | 1 | 1 | 1Records Management policy reviewed by 30 June 2017 | Records management polcy approved by the Provincial Archives and endorsed by the Council | Y | 0 | R0.00 | None | None | Records Management Policy | Y | Not Applicable
[17 empty] | Council resolution and attendance register | Y
11.2.1.3 | Legally compliant records management environment | Review records management policy and develop a records procedure manual | A2 | Optimise systems, administration and operating procedures | Sorfing of document for disposal and appraisal Number of procedure manual developed | 0 | N/A | None | None | sorting of documents for disposal and appraisal. Procedure manual developed and roll out was done to all satelite and main offfice | documents for to be disposed were sorted accordingly and were ready to to disposed in Q3 of 2018/19 financial year. Procedure manual was approved by Provincial Archives and signed by the Municipal Manager and procedure munual roll out was done | Y | 0 | R0.00 | None | None | list of document to be disposed | Y | Not Applicable
[17 empty] | Signed Procedure Munual attendance register | Y
11.2.1.4 | Hygienic and cleaned municipal environment / buildings | Cleaning Services | A2 | Optimise systems, administration and operating procedures | % of municipal buildings kept clean | 200000 | 1700044020 | None | None | 100% of municipal buildings kept clean by 30 June 2017 | Service provider was appointed to supply material | Y | R500.000 | R498,452.41 | None | None | Terms of Reference | Y | Not Applicable
[17 empty] | Appointment letter | Y
[17 empty] | Draft Policy | Y
11.2.1.5 | Access control system fitted in all municipal buildings | Municipal Access Control System and Maintenance | A2 | Optimise systems, administration and operating procedures | % of municipal buildings fitted with access control system | R 250 000.00 | 5070081 | None | None | 100% of municipal buildings fitted with access control system by 30 June 2017 | None | N | R 250 000.00 | R0.00 | unavalability of funds | budgeted for 2018/19 Financial Year | Tender document | Y | Not Applicable
[17 empty] | Appointment letter | Y
[17 empty] | Terms of Reference | Y
11.2.1.6 | Reduced number of reported incidents | Security Services | D5 | Optimise use of municipal assets | % of buildings and movable assets protected | 12500000 | 1700044095 | 100% | 100% | 100% of buildings and movable assets protected by 30 June 2017 | Monitoring the appointment of service providers | Y | 12500000 | 35538792.7 | During 2015-2016 there were a lot of unrests and protests at Alfred Nzo. The institution was forced to hire additional security services to safe guard the municipal personnel and infrastruture. Some claims have been paid in the2016-2017 financial year hence the over expenditure | The project is budgetted for in 2017-2018 financial year | Signed SLA | Y | Not Applicable
[17 empty] | Security Registers from security companies and monthly report | Y

## 11.2.2. CPS - HRM
CORPORATE SERVICES
11.2.2. Human Resources Management and Development
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/2016 | Actual 2015/2016 | Annual Target 2016/2017 | Actual 2016/2017 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.2.2.1 | Meeting the Employment Equity targets set as per the Employment Equity Plan | Employment Equity Plan Implementation | A1 | Improve organisation, capacity, knowledge and Transformation | % compliance with Municipal Equity Plan | 250000 | 1700044283 | 90% | 90% | 90% compliance with Municipal Equity Plan by 30 June 2017 | 90% complaince with the Municipal Equity Plan by 30 June 2017 | Y | 250000 | 199400 | None | None | Annual EE Report | Y | Not Applicable
[17 empty] | Attendance registers | Y
[17 empty] | Confirmation letter form DoL | Y
[17 empty] | Quarterly reports | Y
11.2.2.2 | Adopted Reviewed organogram | Review and adoption of the Organizational Structure | A1 | Improve organisation, capacity, knowledge and Transformation | 1 adopted organogram | 350000 | 1700044281 | 1 | 1 | 1 Organogram adopted by 30 June 2017 | 1 Adopted organogram in December 2016. | Y | 350000 | 28500 | Organogram was done in house, Expenditure incurred was for Councillors Induction | Not budgeted for in the 2017/2018 | Council Resolution. | Y | Not Applicable
[17 empty] | Attendance registers. | Y
[17 empty] | Organizational Structure document | Y
11.2.2.3 | Number of induction sessions held | Development of structured induction programme | A1 | Improve organisation, capacity, knowledge and Transformation | % of new employees inducted | R 30 000.00 | 1700044170 | 100% | 100% | 100% new employees inducted by 30 June 2017 | 100% new employees inducted | Y | R 30 000.00 | 30000 | None | None | Attendance Registers. | Y | Not Applicable
11.2.2.4 | Number of employees trained | Coordination of all training and development programmes | A1 | Improve organisation, capacity, knowledge and Transformation |  | 2050000 | 1700044145 | 100% | 100% | 100% of worksplace skills plan budget spent by 30 June 2017 | 100% of worksplace skills plan budget spent by 30 June 2017 | Y | 2050000 | 2400000 | None | None | Annual training Plan. | Y | Not Applicable
[17 empty] | Learner Certificates. | Y
[17 empty] | Attendance registers | y
[17 empty] | Skill audit report. | Y
[17 empty] | Proof submission from LGSETA & WSP | Y
11.2.2.5 | All posts evaluated submitted to the Unit | District Job Evaluation Unit | A1 | Improve organisation, capacity, knowledge and Transformation | Number of posts evaluated by the Unit and moderated by the Provincial Audit Committee | R 150 000.00 | 1700044304 | 100 | 23 | 120 posts evaluated by 30 June 2017 | 141 Posts evaluated by the 30June 2017 | Y | R 150 000.00 | 150000 | None | None | Attendance registers | Y | The target for 2016-2017 was increased by an additional 20 to address 2015-2016 under performance.
[17 empty] | Signed ToRs | Y
[17 empty] | Audit report | Y
[17 empty] | e-mail proof | Y
11.2.2.6 | Entrenched the culture of learning with the aim of achieving maximum performance from human capital | Study Assistant Programme | A1 | Improve organisation, capacity, knowledge and Transformation | Number of Employees furthering studies at Institutions of Learning | 790000 | 1700044143 | None | None | 10 employees assisted with furthering their studies by 30 June 2017 | 10 employees assisted with furthering their studies by 30 June 2017 | N | 790000 | 340600 | None | None | Copies of approved study grant applications. | Y | Not Applicable
[17 empty] | Payment to institutions of Higher Learning | Y
11.2.2.7 | Retained and trained employees to succeed those who might leave | Retention and Succession planning of staff | A1 | Improve organisation, capacity, knowledge and Transformation | % of employees that have been retained and groomed to take over when other critical positions become vacant | 0 | N/A | None | None | 100% employees retained and groomed by 30 June 2017 | ongoing monitoring of the retention strategy | Y | 0 | 0 | None | None | Retention Strategy | Y | Not Applicable
[17 empty] | Monthly reports | Y
11.2.2.8 | Employee professionalization support programme | Employee registration with relevant professional bodies | A1 | Improve organisation, capacity, knowledge and Transformation | Number of employees successful registered | R 0. 00 | N/A | None | None | Advert to all employees for registration with relevant professional bodies. Payment to relevant professional bodies | Advert issued for employees in Janaury 2017 | N | R 0. 00 | R0.00 | received applications but not yet processed due to budgetary constraints | Budget provision made for 2017/2018 financial Year | Advert | Y | Not Applicable
[17 empty] | Approved applications | Y
[17 empty] | Proof of registration | Y
11.2.2.9 | Enhanced and harmonised labour relations environment | END YEAR FUNCTION | A1 | Improve organisation, capacity, knowledge and Transformation | Number of year end functions held | 650000 |  | None | None | 1 Year end function held 31 December 2016 | year end function held on the 08 December 2016 | Y | 650000 | 650000 | None | None | Project plan | Y | Not Applicable
[17 empty] | Attendance register | Y
11.2.2.10 | Legislative complaint polices coordinated and adopted by Council | Policy development and review | A2 | Optimise systems, administration and operating procedures | 100% Implementation of all policies | 150000 | 1700044184 | 100% | 90% | HRM poicies adopted by Council | 24 HRM policies adopted by Council | Y | 150000 | 25000 | None | None | Council Resolution | Y | Not Applicable
[17 empty] | Policy documents | Y
[17 empty] | Attendance Registers | Y
11.2.2.11 | Fully utilised payroll Employee Self Service module and all staff leave applications to be applied for, approved and updated electronically | Employee Self Service/VIP Fees | A2 | Optimise systems, administration and operating procedures | Number of transactions performed per user | R 150 000 | 1700044171 | 450 | 450 | 465 Transactions performed by 30 June 2017 | 465 Transactions performed by 30 June 2017 | Y | R 150 000 | 77849 | None | None | Pay Roll Employee Self Services reports | Y | Not Applicable
11.2.2.12 | Operationalize Integrated Wellness Programme. | Integrated Wellness programme | A2 | Optimise systems, administration and operating procedures | Number of Wellness Awareness Campaigns conducted | 650000 | 170044171 | 1 | 1 | 4 Wellness Awareness Campaigns conducted by 30 June 2017 | 4 Wellness Awareness Campaigns conducted by 30 June 2017 | Y | 650000 | 393762 | None | none | Referral reports. | Y | Not Applicable
[17 empty] | Attendance registers | Y
[17 empty] | Confirmation letter from medical practitioner | Y
[17 empty] | Proof of payment | Y
11.2.2.13 | Operationalize Integrated Wellness Programme. | Integrated Wellness programme | A2 | Optimise systems, administration and operating procedures | Number of Heritage and Nutrition programmes conducted | same as | 1700044035 | None | None | I heritage day held | 1 Hereitage day held | Y | 0 | 393762 | None | None | Attendance register , | Y | Not Applicable
[17 empty] | pictures | Y
[17 empty] | Programme | Y
11.2.2.14 | Operationalize Integrated Wellness Programme. | Integrated Wellness programme | A2 | Optimise systems, administration and operating procedures | Number of Occupational health and safety inspections and safety audit | 3000000 | - | 16 | 16 | 16 Occupational Health and Safety inspections and safety audit held by 30 June 2017 | 16 Occupational Health and Safety inspections and safety audit held by 30 June 2017 in Matatiele \; Ntabankulu; Mbizana and Umzimvubu areas | Y | 0 | 0 | None | None | Inspection register | y | Not Applicable
[17 empty] | Appointment letter of the service provider | y
[17 empty] | Indemnity forms | y
[17 empty] | Appointment letter | y
[17 empty] | Compliance report certificates | y
[17 empty] | Proof of submission | y
[17 empty] | Attendance registers | y
[17 empty] | Certificates | y
11.2.2.15 | Broad coverage of all employees by IPMs and electronic PMS up and running | Performance management System | A3 | Increase performance and efficiency levels | % of employees on PMS | 400000 | 1700044066 | 80% | 70% | 80% of IPMS implemented by 30 June 2017 | 80% of IPMS implemented by 30 June 2017 | Y | 400000 | 143412 | None | None | Assessments reports. | y | Since the cuscading donw of the programme to employees in non-managerial positions there has been poor participation whihc lead to not achieving the set target. In the 2016/17 Financial Year, a workshop was held to rase awareness and to improve participation in PMS processes.
[17 empty] | Attendance registers | y
[17 empty] | Approved Project Plan Attendance register for rollout assessments | y
[17 empty] | e-mail proof | y
11.2.2.16 | Imparted skills, knowledge and experience to students; graduates. | Graduate Experiential training programmes | C1 | Strengthen internal & external LED capacity | Number of Graduates successfully exposed to work environment | R 1000 000.00 | 1700044141 | 50 | 50 | 50 Graduates successfully exposed to work environment by 30 June 2017 | ISDG -10; FMG - 4; ANDM - 3; LGSETA WIL -10; SSETA - 7; MISA - 14; SSETA PROJECT MANAGEMENT - 18 | Y | R 1 51 833.00 | 1000000 | None | None | Payroll reports. | Y | Not Applicable
| Infrastructure Skills Development Project | Mentorship Programme |  |  | Number beneficiaries of Mentorship Programme | [9 empty] | None | None | Trainees or graduates contracts | Y | Not Applicable
11.2.2.17 | Number of students registered at tertiary institutions to study scarce/rare skills fields | External Bursary Scheme | C1 | Strengthen internal & external LED capacity | Number of bursaries issued | 1350000 | 700044144 | 10 | 19 | 10 busaries issued by 30 June 2017 | 7 beneficiaries for 2017 academic year | N | 1350000 | 1350000 | Only 7 beneficiaries qualified during 2016-2017 financial year | None | Atatndance registers | Y | Not Applicable
11.2.2.18 | Better knowledge when choosing career choice | CAREER EXPO | E1 | Promote Public participation and Good Meaningful Governance | Number of Career EXPO’s convened | R 250 000.00 | 1700044315 | 100% | 100% | 2 Career Expo held by 30 June 2017 | 2 career EXPO was held on the 10 - 12 April 2017 in Umzimvubu LM and 1 Career expo held in Mbizana on the 25 - 26 May 2017 | N | R 250 000.00 | 372150 | None | None | Reports to Standing Committee | Y | Not Applicable
[17 empty] | Invitations to exhibitors | Y
[17 empty] | Attendance registers | Y
[17 empty] | Approved Project Plan | Y
11.2.2.19 | Enhanced human capital employed and monitored | Payroll Data Cleansing | E2 | Strengthen Governance and reduce risk | Number of payroll transactions cleansed | R 200 000.0 | 1700044303 | 100% | 100% | 100% payroll transactions cleansed by 30 June 2017 | Payroll Data cleasning not achieved. The project has been to Q1 of the 2017/2018 FY to financial constratints | N | R 200 000.0 | 0 | Budget constraints | moved Q1 of 2017/2018 FY | Signed TOR’s | Y | Not Applicable
[17 empty] | Attendance Registers. | Y
[17 empty] | Close out reports | Y

## 11.2.3. CPS - ICT
CORPORATE SERVICES
11.2.3. ICT
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Tarteg 2015/2016 | Actual 2015/2016 | Annual Target 2016/2017 | Actual 2016/2017 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.2.3.1 | Disaster Recovery System Tested | Disaster Recovery and Business Continuity | A2 | Optimise systems, administration and operating procedures | % of Disaster Recovery solution deployed and tested | R 1 500 000.00 | 507000141 | 100% | 100% | 100% Disaster Recovery solution deployed and tested by 30 June 2017 | Business Continuity implementation has been completed, Backup centre and testing environment was also established in Mt Ayliff DMC using the old equipment from the main production site. VMs and storage was upgraded including the hosting hardware. | Y | R 1 500 000.00 | 1292345.04 | None | None | Appointment letter | Y | Not Applicable
[17 empty] | Project inception report | Y
[17 empty] | Project closeout report | Y
[17 empty] | Completion certificate | Y
11.2.3.2 | Internent backup installed and tested | VPN Internet Breakout for ANDM | A2 | Optimise systems, administration and operating procedures | % of alternative internet breakout completed | R 200 000.00 | 170044077 | 1 | 1 | 100% of alternative internet breakout completed by 30 June 2017 | Internet alternative breakout has been implemented successfully through Vodacom solution. This means ANDM will always have access to internet even when Telkom is down Vodacom will take over without business interruptions. | Y | R 200 000.00 | 91402.94 | None | None | TOR, Appointment letter, Invoice, completion certificate | Y | Not Applicable
11.2.3.3 | Internet connectivity to all municipal store sites. | Remote Sites Connectivity | A2 | Optimise systems, administration and operating procedures | % of completion of internet connectivity at all municipal stores | R 200 000.00 | 170044077 | 2 | 1 | 50% completion of internet connectivity at all municipal stores by 30 June 2017 | Internet connectivty to one municipal stores has been completed. Mount Ayliff Stores is connected to the network. | Y | R 200 000.00 | 95000 | Due to unavailabity of funds the service provider did not mange to finish the installation | The service provider will commence once the budget is available, all documentation has been submitted to BTO for acrual | TOR, Appointment letter, Invoice, completion certificate | Y | Service provider installed V set in one site and there was no money to continue with the project hence under performance for 2015-2016
11.2.3.4 | SLA Maintained and renewed Software licenses | Municipal Licenses and SLAs | A2 | Optimise systems, administration and operating procedures | % of Updated licenses and SLAs | 4500000 | Municipal CT Licenses | 6 | 6 | 100% f Updated licenses and SLAs by 30 June 2017 | All ICT licenses for 16/17 financial year were paid and currently up to date.SLA`s were reviewed and signed. All Renewal fees were paid in terms of the SLA`s. | Y | 4500000 | 3265682.69 | None | None | VMware renewed licences proof of payment for MS licenses.; | Y | Not Applicable
[17 empty] | Renewed Licences, Firewall Licences, Sysaid Licences. | Y
11.2.3.5 | SCOA Implementation | mSCOA Implementation and database upgrades | A2 | Optimise systems, administration and operating procedures | % Implementation of SCOA and migration to SCOA | 0 | N/A | None | None | 100% Implementation of SCOA and migration to SCOA by 30 June 2017 | mSCOA post implementation testing for ANDM has been done with list of issue log and incident management processes intensified. Monitoring has been intensified due to number of issues raised and recorded in the issue log and compliance circulars. | Y | 0 | 0 | None | None | Change Management guiding document | Y | Not Applicable
[17 empty] | Data migration plan | Y
[17 empty] | New Chart Tes reports | Y
11.2.3.6 | Laptops and thin clients procured and delivered and server environment upgraded | Hardware infrastructure | A2 | Optimise systems, administration and operating procedures | 20 laptops and tools of trade procured, procured and installed for users | 1400000 | 507000041 | 25 | 25 | 25 laptops and tools of trade procured, procured and installed for users by 30 June 2017 | Seventeen(17) Laptops for Councillors, Eight(8) Laptops for Traditional Leaders and Eighteen (18) Laptops for employees were procured and distributed to users. Procurement of laptops was not executed during Quarter3 and Quarter4 due to non-availability of funds. All submitted requests of the last two quarters were reocrded to be executed on the 17/18 FY. | Y | 1400000 | 1295558.8 | None | None | Signed 12 months SLA | Y | Not Applicable
[17 empty] | Delivery Note. | Y
[17 empty] | Completion certificates. | Y
11.2.3.7 | Upgrded network infrastructure | Upgrade of Network Infrastructure | A2 | Optimise systems, administration and operating procedures | % completion of upgraded network infrastructure | R 1 000 000 | 507000111 | None | None | 100 %completion of upgraded network infrastructure by 30 June 2017 | Network upgrade in the main offices has been completed .This project is entails removing the old network infrastructure(CAT 5) and install new infrastructure (CAT 6)to improve network speed and security. The service provider is still onsite for neatening of cabinets and labelling of network points. | Y | R 1 000 000 | 879991.65 | None | None | TOR, Appointment letter,Closeout repor, Invoice, completion certificate | Y | Not Applicable
[11 empty] | Netwoupgrade for remote sites and Ntabanukulu LM has been completed pending testing of fibre connectvity. | Y | R550 000.00 | 253584.12 | None | None | TOR, Appointment letter, inception reports | Y | Not Applicable
11.2.3.8 | ANDM Records Electronically Filed and backed up | Implementation of EDRMS | A2 | Optimise systems, administration and operating procedures | % implementation of ERDMS | 4500000 | 50700154 | None | None | 85% implementation of ERDMS by 30 June 2017 | EDRMS (Electronic Documents and Records Management System), this project seek to achieve an integrated system for both Document management (paperless workflows) and Records Management (Audit of records and scanning of critical documents for electronic archiving), Data Security (DriveLock), supply and installation of enabling infrastructure and development of Policies and Strategies thereofSeven (7) workflows were implemented and tested through pilot before final implementation and deciding on additional licenses. This process will contribute to paperless work processes. Bulk scanner has been delivered which will be used for scanning of documents. Drivelock: document secuirty deployment has been tested and completed, all policies and change management processes will follow including Policy amendments. Policies and Strategies: Draft Policies and strategies required for this project are also in place pending consultation and final adoption. Records audit methology is in place. Records Scanning: Scanners have been delivered, records scanning has not been started due to delays on payments due to the contractor. | Y | 4500000 | 3345000 | None | None | Progress report as per the Implementation plan | Y | Not Applicable
[17 empty] | Attendance Registers for meetings and Trainings | Y
[17 empty] | Expect report | Y
[17 empty] | Testing Report | Y
[17 empty] | Closeout Report | N
[17 empty] | Maintenance SLA | N
11.2.3.9 | Compliance MCGICTPF Phase 3 | ICT Governance implementation (Phase 3) | A2 | Optimise systems, administration and operating procedures | % of ICT Governance Implementation | 500000 | 170004407 | None | None | 100% of ICT Governance Implementation by 30 June 2017 | MCGICTPF entails the development of policies and procure manuals for ICT, all policies The training of Governance Committee members has been conducted and draft policies as required by MCGICTPF have been presented ICTGC and comments made for amendment. Draft Policies and Procedure Manuals are in place pending signing of procedure manuals by MM and adoption of Policies by Council. | Y | 500000 | R307 000 00 | None | None | ToRs | Y | Not Applicable
[17 empty] | Appointment letter | Y
[17 empty] | Draft MCGICTPF Phase 3 | Y
11.2.3.10 | Compliance MCGICTPF Phase 4 | Assessment and development of Strategies and policies to support mSCOA and District Wide ICT Infrastructure Plan |  | Optimise systems, administration and operating procedures | % of ICT Governance Implementation | R350 000.00 | 170004407 | None | None | 0% f ICT Governance Implementation by 30 June 2017 | None | N | R350 000.00 | 0 | This project has not been implemented due to financial unavailability | This project has been cancelled | ToRs | N | Not Applicable
[17 empty] | Appointment letter | N
11.2.3.11 | Established new ICT centres | Establishment of ICT centre and Deployment of ICT equipment on thusong Centres | A2 | Optimise systems, administration and operating procedures | One (1) ICT centre established and one (1) Thusong Centre | R 400 000 | 507000151 | None | None | One (1) ICT centre established and one (1) Thusong Centre by 30 June 2017 | ICT Community centres equipment has been deployed to Vukuzenzele. Internet access for Matatiele; Vukuzenzele Special School and Nopoyi Thusong centre | Y | R 400 000 | 386595 | None | None | TOR, Appointment letter, Invoice, completion certificate | Y | Not Applicable
11.2.3.12 | Fully functioning and operating Computer Centers | ICT centres Maintenance and support | A2 | Optimise systems, administration and operating procedures | % of Assessment Visits to all ICT Centers conducted | 0 | N/A | None | None | 100% of Assessment Visits to all ICT Centers conducted by 30 June 2017 | All ICT community centres have been visited and assessment reports were submitted. | Y | 0 | 0 | None | None | Sites visit schedule | Y | Not Applicable
[17 empty] | Attendance register | Y
[17 empty] | Site report | Y
11.2.3.13 | Internet installed in thusong centre | Connectivity of thusong centres | A2 | Optimise systems, administration and operating procedures | Number of thusong centres with functional internet connectivity | R 200 000.00 | 1700038003 | None | None | 2 thusong centres with functional internet connectivity by30 June 2017 | Network connectivity in Nophoyi thusong centre and vukuzenzele special school has been completed and they have access to internet | Y | R 200 000.00 | 195746 | None | None | TOR, | Y | Not Applicable
[17 empty] | Appointment letter, | Y
[17 empty] | completion certificate | Y
11.2.3.14 | Efficient data communication and telecommunications | Upgrade and Maintenance of data communication and telecommunications | A2 | Optimise systems, administration and operating procedures | % of maintained data communication and telecommunications | 3100000 | 1700044077 | None | None | 100% of maintained data communication and telecommunications by 30 June 2017 | Telkom account has been maintained for Voice and Data communication (Voice Calls, Internet and VPN). High Telkom bill caused by heavy reliance to telecom services. | Y | 3100000 | 2873837.63 | None | None | Proof of monthly payments | Y | Not Applicable
[17 empty] | Consolidated quarterly usage report | Y
11.2.3.15 | Upgrade of look and feel and hosting SLA | Revamping of Website and Customer care Systems | A2 | Optimise systems, administration and operating procedures | % of ANDM Website and customer Care revamped | R350 000.00 | 1700038003 | None | None | 100% of ANDM Website and customer Care revamped by 30 June 2017 | Website upgrade has been completed and the upgraded web pages are online, new look and feel, face uplifting and search path and information engines changed. Intranet upgrade has been also completed with few amendments to effected as per assessment and testing report. | Y | R350 000.00 | 192128.19 | None | None | ToRs | Y | Not Applicable
[17 empty] | Appointment letter/ Order | Y
[17 empty] | Closeout report | N
[17 empty] | Completion certificate | N
11.2.3.16 | ANDM sites visits | Monthly visit for all ANDM sites | A2 | Optimise systems, administration and operating procedures | % of ANDM remote sites visited for support | 0 | N/A | None | None | 100% of ANDM remote sites visited for support by 30 June 2017 | All ANDM remote sites have been visited for support and all asset were being recorded. | Y | 0 | 0 | None | None | Sites visit schedule | Y | Not Applicable
[17 empty] | Attendance register | Y
[17 empty] | Site report | Y
11.2.3.17 | Duplicated information storages and live files for File Server | Establishment of First Disaster Recovery site within ANDM network at Disaster Management Centre in Mount Ayliff | E2 | Strengthen Governance and reduce risk | % of Live files and VIP system duplicated to Disaster Management center as a first line fail over platform | 0 | None | 100% | 100% | 100% of Live files and VIP system duplicated to Disaster Management center as a first line fail over platform by 30 June 2017 | Live and VIP file has been duplicated to Mt Ayliff DMC on a monthly basis | Y | 0 | 0 | None | None | Project testing report | Y | Not Applicable
[17 empty] | Closeout report and completion certificates | Y
11.2.3.18 | Backup records for the municipal information | Backup Monitoring | E2 | Strengthen Governance and reduce risk | Number of Backups conducted and checklist signed by ICT Manager | 0 | None | 12 | 12 | 12 Backups conducted and checklist signed by ICT Manager by 30 June 2017 | All our (4) Quarterly backup report has been reviewed, signed and filed for audit purposes. All required standard checklists with backup quarterly report are in place as required by Backup Policy. | Y | 0 | 0 | None | None | Backup report signed by ICT Manager for all four quarters Restore tests certificats | Y | Not Applicable
Y
11.2.3.19 | Approved Access control forms for users | Creation of users on business systems | E2 | Strengthen Governance and reduce risk | % of access control forms approved | 0 | None | 100% | 100% | 100% f access control forms approved by 30 June 2017 | All new users for 16/17 FY have been created on the domain controller as per submitted access request forms. | Y | 0 | 0 | None | None | Creation of users report. | Y | Not Applicable
[17 empty] | Access control forms approved by ICT Manager | Y
11.2.3.20 | Roles and responsibilities reviewed and signed by supervisors and approved by ICT Manager | Review and enforcement of Roles and Responsibilities | E2 | Strengthen Governance and reduce risk | % of Roles and responsibilities reviewed for all business systems (VIP, Munsoft, Sebata, Action It) | 0 | None | 100% | 100% | 100% of Roles and responsibilities reviewed for all business systems (VIP, Munsoft) by 30 June 2017 | All four (4) quarterly review report of Roles and Responsibilities has been performed and signed by users and confirmed by supervisors. | Y | 0 | 0 | None | None | Four quarterly reports on roles and responsibilities review approved by ICT Manager | Y | Not Applicable
11.2.3.21 | Minutes of meetings | ICTGSC Meetings | E2 | Strengthen Governance and reduce risk | Number of ICTGSC Meetings conducted | 0 | None | 4 | 4 | 4 ICTGSC Meetings conducted by 30 June 2017 | All ICTGC quarterly meetings were convened for 16/17 Y. section quarterly reports, draft policies; mSCOA progress reports, ERMS progress reports were being presented to the ICTGC. | Y | 0 | 0 | None | None | Notice of Meetings | Y | Not Applicable
[17 empty] | Minutes of quarterly meetings signed by Chairperson | Y

## CPS PERFORMANCE
CORPORATE SERVICES
ACHIEVED TARGETS VS NOT ACHIEVED BY UNIT
Unit | Total No. of targets | No. Achieved | No. Not Achieved | % Achieved | % Not Achieved
Admin Support | 6 | 5 | 1 | 83% | 17%
Human Resources Management | 19 | 15 | 4 | 79% | 21%
ICT | 22 | 21 | 1 | 95% | 5%
Department | 47 | 41 | 6 | 87% | 13%

## 11.3.1. IDMS - WSA
11.3 INFRASTRUCTURE DEVELOPMENT & MANAGEMENT SERVICES
11.3.1. WATER SERVICES AUTHORITY
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.1.1 | Credible indigent register. | Indigent Validation of RDP houses within ANDM | A2 | Optimise systems, administration and operating procedures | Credible indigent database | 150044251 | None | None | 20000 Credible indigent databaseby 30 June 2017 | 10000 households validated in both Mbizana and Ntabankulu | N | 750000 | 340000 | Service provider to validate households in both Matatiele and Umzimvubu LM could be appointed due to municipal financial constraints | The project to be defered to 2019/2020 financial year due to financial constraints within the municipality | ToR, advert,Appointment letter and credible database report | Y | This is new project it only started in 2016/2017 financial year
11.3.1.2 | Number of indigent applications verified | Indigent application verification | A2 | Optimise systems, administration and operating procedures | 40 000 indigent households verified | 150044251 | 60000 indigent households verified by 30 June 2016 | 65 624 | 40000 indigent households verified by 30 June 2017 | None | N | R1 250 000.00 | 0 | Terms of reference (ToR) were submitted to SCM for advertisement, but it was never advertised due to municipal financial contriants, hence no perfomance nor expenditure reported | This project is prioritized in the 2017/2018 financial year | ToR | Y | In 2015/16 more households were verified than the set target, however in 2016/17 target was not met

## 11.3.1.1 IDMS-ENVIRONMENT
11.3 INFRASTRUCTURE DEVELOPMENT & MANAGEMENT SERVICES
11.3.1.1 ENVIRONMENTAL MANAGEMENT
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.1.1.1 | Completed and adopted water safety plan | Water Safety Plan | B3 | Improve the quality and flow of water and sanitation | Water Safety Plan reviewed and adopted by council | 150044123 | 7 | 0 | 7 Water Safety Plan reviewed and adopted by council by 30 June 2017 | 7 Water Safety Plan reviewed | Y | R750 000. 00 | 398863.2 | The appointed services provider charges were lesser than anticipated hence under expenditure | None | Appointment letter ,Invoices and Water Safety Plan | Y | The target was not met in the 2015/2016 due late appointment of service provider, however the target was met in 2016/2017 financial year.
11.3.1.1.2 | Completed and adopted wastewater risk abatement plan | Wastewater risk abatement plan | B3 | Improve the quality and flow of water and sanitation | Wastewater Risk Abatement Plan reviewed and adopted by council | 150044123 | 1 | 0 | 1 Wastewater Risk Abatement Plan reviewed and adopted by council by30 June 2017 | 1 wastewater risk abatement plan reviewed | Y | R750 000.00 | 595311.88 | The appointed services provider charges were lesser than anticipated hence under expenditure | None | Appointment letter ,Invoices and Waste Water Risk Abatment Plan | Y | The target was not met in the 2015/2016 due late appointment of service provider, however the target was met in 2016/2017 financial year.
11.3.1.1.3 | 108 sample points monitored and results submitted to DWS | Water quality monitoring | B3 | Improve the quality and flow of water and sanitation | Number of water quality reports submitted to DWS for BDS &GDS. | 150044134 | 12 | 12 | 12 water quality reports submitted to DWS for BDS &GDS by 30 June 2017 | 12 water quality reports submitted to DWS | Y | 2470000 | 1041619.75 | The initial target was to sample 400 sample points but ended up sampling 108 sample points due to limited personnel to take samples across ANDM, Drying up of water sources due to drought hence under expenditure. | Increase water quality monitoring personnel | Monthly water quality monitoring reports | Y | Not Applicable
11.3.1.1.4 | Auditing of all regional Schemes per SANS 241 | Auditing of Scheme SANS 241 Regulation | B3 | Improve the quality and flow of water and sanitation | Number of SANS 241 reports for all regional water submitted to DWS for BDS &GDS | 150044134 | None | None | 1 SANS 241 reports for all regional water submitted to DWS for BDS &GDS by 30 June 2017 | None | N | 1000000 | 0 | One service provider was appointed for all three wastewater treatment works process audits which was contradictory with ANDM SCM policies and SOPs, hence sent back to SCM for re-evaluation, however, this could not be excecuted due to financial constraints within the municipality , hence no expenditure reported | Project to be implemeted in 2017/18 financial year. | Advert, Purchase Order | Y | Not Applicable
11.3.1.1.5 | 4 awareness WERP outreaches in the ANDM | Waterborne disease emergency response plan | E1 | Improve community health and safety | Number of awareness WERP outreaches in the ANDM | 1500044140 | 4 | 4 | 3 awareness WERP outreaches in the ANDM by 30 June 2017 | Conduct 1 awareness campaign in Matatiele LM by 30 June 2017 | N | R 500 000.00 | 351322.6 | Due to municipal financial constraints promotional material could not be procured, hence no perfomance and expenditure reported -50 percent achieved due to municipal financial constraints. | Umzimvubu awareness to be conducted in the next financial year | Invoice and Purchase orders. | Y | Not Applicable
11.3.1.1.6 | Rehabilitation of Mtsila and Ntabankulu catchment | Environmental Management Unit (Community Based Natural Resource Management System) - Ntabankulu Mbizana and Matatiele | F4 | Improve environmental health and safety. | Number of hectors cleared off wattle in Mtsila and Ntabankulu | 1500444036 | 100% | 0 | 10 hectors cleared off wattle in Mtsila and Ntabankulu catchment | 10 hectors cleared off | Y | R 600 000.00 | 375180 | Working tools were not procured and relevant trainings were not conducted due to financial constraints hence under expenditure. | None | Purchase orders and delivery notes | Y | Terms of Reference were submitted during last quarter of 2015/2016 financial year which led to early appointment of service provider.
11.3.1.1.7 | Fully functional wastewater systems. | Effluent Management (all LMs) | F4 | Improve Environmental Health & Safety | Number of compliance notices issued to ANDM by DWS and DEDEA | 150044131 | 1 | 1 | 1 compliance notices issued to ANDM by DWS and DEDEAby 30 June 2017 | 1 compliance notices issued to ANDM by DWS and DEDEA. | Y | R 500 000.00 | 468000 | None | None | Purchase orders invoices. | Y | Not Applicable
11.3.1.1.8 | Blue flag certification program and compliance | Coastal Management Plan | F4 | Improve Environmental Health & Safety | Number of Mthentu and Mzamba beach water quality samples analyzed every month for compliance with Blue flag certification. | 150044136 | 1 | 1 | 20 Mthentu and Mzamba beach water quality samples analyzed every month for compliance with Blue flag certification by 30 June 2017 | 20 Mthentu and Mzamba beach water quality samples analyzed every month for compliance with Blue flag certification | Y | 50000 | 0 | The initial budget was set for on-site monitoring tools which could not be procured due to financial constraints hence no expenditure | None | water quality reports | Y | Not Applicable

## 11.3.1.2 IDMS - PLANNING
11.3 INFRASTRUCTURE DEVELOPMENT & MANAGEMENT SERVICES
11.3.1.2 PLANNING
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.1.2.1 | WSDP adoption by council | Review of Water Services Development Plan | B1 | Increase access to municipal services | Number of WSDP to be adopted by council | 150044110 | 1 | 1 | WSDP to be adopted by council by 30 June 2017 | draft document submited to DWS for their inputs | N | R 1 000 000.00 | 563079.97 | Slow progress from the appointed service provider hence submitted WSDP to DWS late, hence under expenditure. | Project to be completed during 2017/2018 financial year. | Draft Reviewed WSDP | Y | Not Applicable
11.3.1.2.2 | Completed and adopted Backlog Eradication Strategy for ANDM. | Backlog eradication strategy | B 1 | Increase access to municipal services | Number of Backlog Eradication Strategy to be Adopted by Council | 1500044137 | 1 | 1 | Backlog Eradication Strategy to be Adopted by Council by 30 June 2017 | Final reviwed document submitted for adoption | Y | R 500 000.00 | 500000 | None | None | Reviewed Backlog Eradication Strategy | Y | Not Applicable
11.3.1.2.3 | Feasibility studies to be undertaken in 3 wards | Feasibility Studies for Ntabankulu (Wards 1, 5 and 6) | B2 | Improve the quality of Municipal Infrastructure services | Number of feasibility studies completed and approved by DWS and CoGTA | 505002201 | 30 | 21 | feasibility studies completed and approved by DWS and CoGTA by 30 June 2017 | Draft technical report submitted to ANDM | N | R 4 140 00.00 | 2280000 | Service providserf could not proceed due to non payment of the invoices as a result of municipal financial constraints. | Budget will be made available for 2017/2018 so that we continue with the Studies | draft Technical report submitted to ANDM | Y | Target not met .Progress was slow due to letters of abeyance issued to PSPs
11.3.1.2.4 | Feasibility studies to be undertaken in 2 wards | Feasibility studies for Ntabankulu wards 12 and 14 | B2 | Improve the quality of Municipal Infrastructure services | Number of feasibility studies completed and approved by DWS and CoGTA | 505002201 |  |  | feasibility studies completed and approved by DWS and CoGTA by 30 June 2017 | Final technical reports sumitted to DWS and approved for implementation | Y | R 2 000 000.00 | 1458800 | Service providserf could not be paid due to non paid as a result of financial constraints hence under expenditure | Budget will be made available for 2017/2018 so that we pay the outstanding invoices | DWS recommendation letter | Y | Target not met .Progress was slow due to letters of abeyance issued to PSPs
11.3.1.2.7 | Feasibility studies to be undertaken in 4 wards | Feasibility studies for Mbizana wards 10,12,13 and 15 | B2 | Improve the quality of Municipal Infrastructure services | Number of feasibility studies completed and approved by DWS and CoGTA | N/a |  |  | feasibility studies completed and approved by DWS and CoGTA by 30 June 2017 | Final technical reports sumitted to DWS and approved for implementation | Y | 2000000 | 0 | Service providers could not be paid due to non paid as a result of financial constraints hence under expenditure | Budget will be made available for 2017/2018 so that we pay the outstanding invoices | DWS recommendation letter | Y | Target not met .Progress was slow due to letters of abeyance issued to PSPs
11.3.1.2.13 | Completed concept report completed | RBIG dam feasibility studies for Kinira, Sirhoqobeni, Mkhemane & Ntabankulu bulk. | B3 | Improve the quality of Municipal Infrastructure services | Number of dam feasibility studies completed | N/a | 4 | 0 | dam feasibility studies completed by 30 June 2017 | Undertaking Detailed Technical Feasibility studies | N | 5500000 | 0 | Slow progress due to non payment of service provider by DWS.Limited budget allocation by DWS for these projects inhibit completion of these projects. | Engage DWS for the payment of submitted invoices and future budget allocation for these projects. | Progress report | Y | Target not met.Projects moving slowly due to the delays in payment to PSPs by DWS
11.3.1.2.14 | Completed and adopted DITP document for the ANDM. | District Integrated Transport Plan in the ANDM. | B 2 | Improve the quality of Municipal Infrastructure services | Number of DITP adopted | 150044298 | 1 | 1 | 1DITP adopted by 30 June 2017 | Draft DITP document submitted to ANDM | N | R 1 500 000.00 | 1130880 | Slow progress from PSP due to difficulties in gathering information to finalise the report hence under expenditure. | Engage LMs in the next financial year | Draft DITP Document | Y | Not Applicable
11.3.1.2.15 | Complete rural assessment system | Develop Road Asset Management System (RAMS) | B 2 | Improve the quality of Municipal Infrastructure services | Number of road and asset management system adopted | 5050000221 | 1 | 1 | road and asset management system adopted by 30 June 2017 | Road Asset Management System adopted by council | Y | 2225000 | 1156905.39 | Payment was done however there are outstandong invoices hence under expenditure | BTO to prioritize payment of sumitted invoices | RRAMS System | Y | Not Applicable

## 11.3.1.3. IDMS - WCDM
INFRASTRUCTURE DEVELOPMENT & MANAGEMENT SERVICES
11.3.1.3 WCDM
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.1.3.1 | 20 data logging and telemetric systems installed | Installation of automatic data logging system in all bulk meters and telemetry data logging at the WTW inlet and outlet meters. (Water Conservation and Water DEM) | B2 | Improve the quality of Municipal Infrastructure services | 20 data logging and telemetric system installed | 150044108 | 20 | 0 | 20 data logging and telemetric system installed by 30 June 2017 | None | N | R 250 000.00 | 0 | Targets not met in 2016/17 fy due to unvailabilty of personel for WCDM Unit. WCDM Manager only appointed in 2016/17 fy March 2017 | Project to be implemented in 2017/18 financial year | Advert, and Appointment letters | N | Targets not met in 2015/16 and 2016/17 fy due to unvailabilty of personel for WCDM Unit. WCDM Manager only appointed in 2016/17 fy March 2017
11.3.1.3.2 | 100 water services scheme’s infrastructure assets verified and analyzed | Asset Replacement Plan (Water Conservation and Water DEM) | B2 | Improve the quality of Municipal Infrastructure services | 100 water service scheme’s infrastructure assets verified and analyzed | 150044108 | 100 | 0 | 100 water service scheme’s infrastructure assets verified and analyzed by 30 June 2017 | None | N | R 2 50 000.00 | 0 | Targets not met in 2016/17 fy due to unvailabilty of personel for WCDM Unit. WCDM Manager only appointed in 2016/17 fy March 2017 | Project to be implemented in 2018/19 financial year | Advert, appointment letter and audit report. | N | Targets not met in 2015/16 and 2016/17 fy due to unvailabilty of personel for WCDM Unit. WCDM Manager only appointed in 2016/17 fy March 2018

## 11.3.2. IDMS - PMU
INFRASTRUCTURE DEVELOPMENT & MANAGEMENT SERVICES
11.3.2 PROJECT MANAGEMENT UNIT
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.2.1 | Work Opportunities reported on EPWP MIS system | EPWP Coordination | C3 | Promote earning potential of ANDM Communities | Number of Work Opportunities reported on the MIS System | EPWP INCENTIVE GRANT | 1121 | 1343 | 808 Work Opportunities reported on the MIS Systemby 30 June 2017 | 808 Work Opportunities reported on the MIS System | Y | R6 000 600.00 | 6000600 | None | None | Monthly Attendance registers. | Y | Not Applicable
[16 empty] | MIS System Report. | Y
[16 empty] | Beneficiary Payment Vouchers | Y

## 11.3.2.1. PMU-MATATIELE PROJECT
INFRASTRUCTURE DEVELOPMENT & MANAGEMENT SERVICES
11.3.2.1. MATATIELE PROJECTS
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.2.1.1 | 1120 VIPs constructed | ANDM VIP Sanitation in Matatiele Local Municipality | B1 | Increase access to municipal services | Number of VIP toilets constructed in Matatiele | 50500351 | 300 | 0 | 1120 of VIP toilets constructed in Matatiele by 30 June 2017 | 1200 | Y | R10 000 000.00 | 10752503.92 | Additional toilets done at Ward 10 and the outstanding materials payments for Matatiele Ward 7 was processed. | Stick to budgeted amount for each years expenditure | Copy of VO, Happy Letter and Completion certificate | Y | The 300 VIPs planned for 2015/2016 was done in 2016-2017
11.3.2.1.2 | Construction of the Fobane WTW 100% completed and operational. | Fobane Water Scheme Phase 1 | B1 | Increase access to municipal services | % of Completion of Construction of Fobane Water Treatment Works. | 50500358 | 100% | 90% | 100%of Completion of Construction of Fobane Water Treatment Works by 30 June 2017 | WTW 100% completed, | Y | R 35 000 000.00 | 34136076.352 | The final completion has not been reached as the contractor was still working onm the identified snags after the commissioning was done. | All outstanding snags have been completed and the only thing holding the operations is a leaking rising main pipeline towards the command reservoir. | Progress report | Y | 2015-2016 non achievement was addressed in 2016/2017 financnial year
11.3.2.1.3 | Construction of Tholamela bulk water supply 100% completed | Tholamela Sub-regional Water Supply | B1 | Increase access to municipal services | % completion of Construction of Tholamela water supply | 50500111 | 100% | 0 | 100% completion of Construction of Tholamela water supply by 30 June 2017 | Tholamela WS 100% completed | Y | R5 000 000.00 | 2739784.22 | The bulk water supply is completed but the connection to the existing infrastructure was not part of the scope it will be done in the 2017/18 FY | Connections will be done in 2017-2018 financial year | Progress report and Practical Completion certificate | Y | 2015-2016 non achievement was addressed in 2016/2017 financnial year
11.3.2.1.4 | 100% completion of the Packaged Water Treatment Plant(WTP) | Matatiele Ward 5 (Water) | B1 | Increase access to municipal services | % completion of packaged Water Treatment Plant | 5050961 | 100% | 0 | 100% completion of packaged Water Treatment Plant by 30 June 2017 | No work done | N | R7 473 460.00 | 3387723.76 | Work on WTW, Boreholes & pumpstations could not be started due to non approval of the Water User Licence Application (WULA) by the Department of Water & Sanitation. The expenditure was only incurred for the engineers fees, the costs for blasting about 1000m section of the pipeline towards the boreholes as well as construction of the spring. | Continously follow up with DWS on the status of the application as the delays are impacting negatuvely on the project progress.pusly | Progress report & site meeting minutes | Y | 2015-2016 non achievement was addressed in 2016/2017 financnial year
11.3.2.1.5 | 5 boreholes equipped |  | B1 | Increase access to municipal services | Number of boreholes equipped |  | 5 | 0 | 5 boreholes equipped by 30 June 2017 | No work done | N
11.3.2.1.6 | 6 pump stations constructed |  | B1 | Increase access to municipal services | Number of pump stations Constructed |  | 6 | 0 | 6 pump stations Constructed by 30 June 2017 | No work done | N
11.3.2.1.7 | Construction of village reticulation network and second mains to 6 villages of Ward 7 | Matatiele Ward 7 (Water) | B1 | Increase access to municipal services | Number villages provided with reticulation network and secondary mains plus 5 reservoirs. | 5050971 | None | None | 6 villages provided with reticulation network and secondary mains plus 5 reservoirs by 30 June 2017 | Construction of reticulation in four villages reached 88% | N | R50 000 000.00 | 48967934.41 | Th contractor was stopped on site by the Health & Safety consultnat due to non-compliance with OHS requirements and no work was done for a period of 3 months. | Outstanding work will be completed with the scope to be done in the new financial year. | Progress report, site meeting minutes | Y | Not Applicable
11.3.2.1.8 | Equipping of 9 boreholes completed | Matatiele Ward 15 (Water) | B1 | Increase access to municipal services | Number of boreholes equipped | 5050941 | None | None | 9 boreholes equipped by 30 June 2017 | No physical work done except for procuring of pumps | N | R7 500 000.00 | 4573951.76 | Contractor not paid since December 2016, so no work was done from January till end March 2017. | Equipping of boreholes to commence in Q4 while waiting for Eskom to provide power | Signed Eskom Application Forms, Progress report & site meeting minutes | Y | Not Applicable
11.3.2.1.9 | Construction of 9 pump stations completed |  | B1 | Increase access to municipal services | Number of pump stations completed |  | 9 | 0 | 9 pump stations completed by 30 June 2017 | No work done | N |  |  | Electrification of the borehole waiting for payments from ANDM before the installation of power line can commence | Equipping of boreholes to commence in Q4 while waiting for Eskom to provide power |  |  | 2015-2016 non achievement was addressed in 2016/2017 financnial year
11.3.2.1.10 | Construction of 5 reservoirs completed |  | B1 | Increase access to municipal services | Number of reservoirs constructed |  | 5 | 0 | 5 reservoirs constructed by 30 June 2017 | 3 reservoirs completed | N |  |  | Commissioning & hand over by 30 June 2017 Not achieved | The additional 2 reservoirs will be constructed in the new Financial Year |  |  | 2015-2016 non achievement was addressed in 2016/2017 financnial year
11.3.2.1.11 | Project completed only release of retention | Maluti/Matatiele/Ramohlakoana Water Supply | B1 | Increase access to municipal services | % of retention released | 50500511 | 5 | 5 | 100% retention released by 30 June 2017 | None | Retention not re;leased | R2 000 000.00 | 216576.56 | Retention not released as there are other snags that the contractior has not completed hence under expenditure | Retention to be released in 2017/18 FY | Completion certificate | N | Not Applicable
11.3.2.1.12 | Completion of 12km of bulk rising pipelines | Matatiele RBIG Water Supply Project | B1 | Increase access to municipal services | Kilometres of bulk rising main completed | 50505951 | 12Km | 12Km | 100% kilometres of bulk rising main completed by 30 June 2017 | 95% completed | N | R20 000 000.00 | 22280956.54 | Contractor experienced delayes with replacenent of faulty fittings by the supplier, the project will be completed in 2017-2018 financial year | This project will be completed in 2017-2018 financial year | Progress report & site meeting minutes and letter for extension of time | Y | Not Applicable
11.3.2.1.13 | Construction of 3 Borehole pump stations 100% completed. | Matatiele RBIG Water Supply Project | B1 | Increase access to municipal services | Number of Borehole pump stations completed |  | 3 | 0 | 3 Borehole pump stations completed by 30 June 2017 | None | N |  |  | The delay in paying the supplier between Jnaury and March 2017 delayed the delivery fo the pumps | The payment of the service providers should be prioritised in 2017-2018 financial year |  |  | 2015-2016 non achievement was addressed in 2016/2017 financnial year
11.3.2.1.14 | Construction of one (1) high lift pump station 100% completed | Matatiele RBIG Water Supply Project | B1 | Increase access to municipal services | % of high lift pump station completed |  | 100% | 0 | 1 high lift pump station completed by 30 June 2017 | 80% completed | N |  |  | The delay in paying the supplier between Jnaury and March 2017 delayed the delivery fo the pumps | The payment of the service providers should be prioritised. |  |  | 2015-2016 non achievement was addressed in 2016/2017 financnial year
11.3.2.1.15 | Equipping of 3 boreholes | Matatiele RBIG Water Supply Project | B1 | Increase access to municipal services | Number of boreholes equipped |  | 3 | 0 | 3 boreholes equipped by 30 June 2017 | None | N |  |  | Delays in procurement of pumps by the service provider | Project to be completed in 2017-2018 |  |  | 2015-2016 non achievement was addressed in 2016/2017 financnial year
11.3.2.1.16 | Construction of the 5Ml reservoir | Matatiele RBIG Water Supply Project | B1 | Increase access to municipal services | % Completion of 5Ml Resevour |  | 3 | 0 | % Completion of 5Ml Resevour by 30 June 2017 | 60% completed | N |  |  | The delays experienced in payment between Jnaury and March 2017 impacted negativey on the prigress on the reservoir | The payment of the service providers should be prioritised. |  |  | 2015-2016 non achievement was addressed in 2016/2017 financnial year
11.3.2.1.17 | Installation of approximately 3000m of rising mains, equipping of borehole connector mains form 700Kl and construction of 320Kl reservoir, 100% completed | Matatiele WSIG-Tholang and Buxton Park water project | B1 | Increase access to municipal services | 3000m of rising mains and connector mains | 50500301 | None | None | 100% Installed, equipping of one (1) borehole and construction of reservoir all 100% completed by 30 June 2017 | 100% Completed | Y | R3 500 000.00 | 3481945.16 | None | None | Progress Report | Y | Not Applicable
[5 empty] | Installed, equipping of one (1) borehole and construction of reservoir all 100% completed. |  | None | None
11.3.2.1.18 | Equip existing borehole and install the rising mains to reservoir. | Matatiele WSIG-Mpofini village water supply | B1 | Increase access to municipal services | 1500m of rising mains and connector mains installed, equipping of one (1) borehole. | 50500301 | None | None | 100% 1500m of rising mains and connector mains installed, equipping of one (1) borehole by 30 June 2017 | 1 borehole drilled | N | R1 000 000.00 | 282047 | Unsuitable water quality | Project to be completed in 2017-2018 |  |  | Not Applicable
11.3.2.1.19 | Equipping of three existing boreholes, installation 3500m of rising mains and connection to reservoir 100% completed. | Matatiele WSIG- Khorong Koali Water Supply | B1 | Increase access to municipal services | 3500m of rising mains installed and equipping of 3 boreholes completed. | 50500301 | None | None | 100% 3500m of rising mains installed and equipping of 3 boreholes completed by 30 June 2017 | 100% Completed | Y | R2 000 000.00 | 1341370.96 | None | None |  |  | Not Applicable
11.3.2.1.20 | Equipping of existing borehole, installation 1500m of rising mains and construction of a new storage reservoir 100% completed. | Matatiele WSIG- Sandfontein Water Supply | B1 | Increase access to municipal services | 1500m of rising mains installed, equipping of one borehole and construction of a new reservoir. | 50500301 | None | None | 100% 1500m of rising mains installed, equipping of one borehole and construction of a new reservoir by 30 June 2017 | 100% Completed | Y | R1 000 000.00 | 1093130.67 | None | None |  |  | Not Applicable
11.3.2.1.21 | Equipping of existing borehole, installation 1500m of rising mains and construction of a new storage reservoir 100% completed. | Matatiele WSIG - St. Paul Water Supply | B1 | Increase access to municipal services | 2500m of rising mains installed, equipping of one borehole and construction of a new reservoir. | 50500301 | None | None | 100% 2500m of rising mains installed, equipping of one borehole and construction of a new reservoir by 30 June 2017 | 50% Completed | N | R1 000 000.00 | 50000 | Infrastructure installed but the Spring dried up | New borehole drilled in 2017/2018 to address the challenge |  |  | Not Applicable
11.3.2.1.22 | Equipping of existing borehole, installation 1500m of rising mains and construction of a new storage reservoir 100% completed. | Matatiele WSIG - Gudlintaba Water Supply | B1 | Increase access to municipal services | 1700m of rising mains installed, equipping of one borehole and construction of a new reservoir. | 50500301 | None | None | 100% 1700m of rising mains installed, equipping of one borehole and construction of a new reservoir by 30 June 2017 | 100% Completed | Y | R1 000 000.00 | 1284091.84 | None | None |  |  | Not Applicable
11.3.2.1.23 | Drill & equip one (1) borehole, installation of 4500m gravity & rising mains, protection of spring and construction of a new storage tank 100% completed. | Matatiele WSIG - Mdeni Water Supply | B1 | Increase access to municipal services | 4500m of rising mains installed, drilling & equipping of one borehole and construction of a new reservoir. | 50500301 | None | None | 100% 4500m of rising mains installed, drilling & equipping of one borehole and construction of a new reservoirby 30 June 2017 | 100% Completed | Y | R2 5000 000.00 | 2496271.55 | None | None |  |  | Not Applicable
11.3.2.1.24 | Drill & equip one (1) borehole, installation of 3500m rising mains and building of a new tank 100% completed | Matatiele WSIG - Zingcuka Water Supply | B1 | Increase access to municipal services | 3500m of rising mains installed, drilling & equipping of one borehole and construction of a new reservoir.. | 50500301 | None | None | 100% 3500m of rising mains installed, drilling & equipping of one borehole and construction of a new reservoir by 30 June 2017 | 100% Completed | Y | R3 5000 000.00 | 3243895.73 | None | None |  |  | Not Applicable
11.3.2.1.25 | Drill & equip one (1) borehole, installation of 3500m rising mains and building of a new tank 100% completed | Matatiele WSIG – Ramafole Water Supply | B1 | Increase access to municipal services | 3500m of rising mains installed, drilling and equipping of one borehole and construction a new reservoir | 50500301 | None | None | 100% 3500m of rising mains installed, drilling and equipping of one borehole and construction a new reservoir by 30 June 2017 | 100% Completed | Y | R1 500 000.00 | 1691546.56 | None | None |  |  | Not Applicable

## 11.3.2.2. PMU-MBIZANA PROJECTS
INFRASTRUCTURE DEVELOPMENT & DEVELOPMENT SERVICES
11.3.2.2. MBIZANA PROJECTS
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.2.2.1 | 475 VIPs constructed | Mbizana Ward 26 Construction of VIP Toilets | B1 | Increase access to municipal services | Number of households with access to sanitation facilities in Mbizana ward 26 | 50 503 11 | 585 | 476 | 475 Number of households with access to sanitation facilities in Mbizana ward 26 by 30 June 2017 | 475 VIP Toilets constructed and completed | Y | R 4 410 000.00m | 4336732.75 | None | None | Happy Letter, Completion certificate | Y | 2015-2016 non perfromance will be addressed in 2016-2017 financial year
11.3.2.2.2 | 1003 VIPs constructed | Mbizana Ward 29 Construction of VIP Toilets | B1 | Increase access to municipal services | Number of households with access to sanitation facilities in Mbizana ward 29 | 50 503 21 | 150 | 0 | 1003 Number of households with access to sanitation facilities in Mbizana ward 29 by 30 June 2017 | 1003 VIP Toilets constructed and completed | Y | R11 150 000.00m | 11195222.6 | None | None | Happy Letter, Completion certificate | Y | The contractor was awarded late hence non achievment in 2015-2016 financial year, project to be completed in 2016-2017 financial year
11.3.2.2.3 | 1736 VIPs constructed | Mbizana Ward 30 Construction of VIP Toilets | B1 | Increase access to municipal services | Number of households with access to sanitation facilities in Mbizana 30 | 50 503 31 | 200 | 0 | 1736 Number of households with access to sanitation facilities in Mbizana 30 by 30 June 2017 | 1736 VIP Toilets constructed and completed | Y | R16 700 000.00m | 16027928.59 | None | None | Happy Letter, Completion certificate | Y | The contractor was awarded late hence non achievment in 2015-2016 financial year, project to be completed in 2016-2017 financial year
11.3.2.2.4 | 476 VIPs Constructed | Mbizana Ward 31 Construction of VIP Toilets | B1 | Increase access to municipal services | Number of households with access to sanitation facilities in Mbizana ward 31 | 50 500 551 | None | None | 476Number of households with access to sanitation facilities in Mbizana ward 31 by 30 June 2017 | 479 VIP Toilets constructed and completed | Y | R 4 500 000.00m | 4572823.4 | Contractor appointed at a cost of R 4 372 823.40 and Health and Safety appointed at a cost of R 200 000.00, hence the expenditure is more than allocated budget but the contractor completed the work on site with 3 additional 3 VIP toilets | Work completed on site | Happy Letter, Completion certificate | Y | Not Applicable
11.3.2.2.5 | Completion of Greater Mbizana Water supply four contracts | Greater Mbizana regional scheme reticulation | B1 | Increase access to municipal services | Number of targeted reticulation infrastructure completed | 50 500 3551 | None | None | Completion Reservoirs & Stand pipes by 30 June 2017 | Completion Greater Mbizana Water supply four contract on Reservoirs, Reticulation and Stand Pipes Completed | Y | R 31 200 000.00 | 31110144.23 | None | None | Completion certificate | Y | Not Applicable
11.3.2.2.6 | Construction of 5 km Reticulation pipeline network | Greater Mbizana regional scheme reticulation | B1 | Increase access to municipal services | Number of targeted reticulation infrastructure completed |  | 81Km | 88.3Km | 5kms targeted reticulation infrastructure completed by 30 June 2017 | 16.5km of Reticulation & Bulk pipeline constructed and completed on site | Y |  |  | Contractor have done 16.5km of reticulation and bulk pipeline which is within the scope of work | The project will be completed this financial year 2017-18 and contractor will completed the work within the awarded budget. | Minutes of the Progress Meeting and Progress Report | Y | Not Applicable
11.3.2.2.7 | Construction of Hand Pump and Drilling of Borehole | Construction of Kwamlindazwe Borehole Development | B1 | Increase access to municipal services | % of Hand Pump and Drilling of Borehole Completed | 50 500 271 | None | None | 100% Hand Pump and Drilling of Borehole Completed by 30 June 2017 | 1 Hand Pump is installed and Completed | Y | R2 500 000.00 | 2496645.7 | None | None | Progress Report | Y | Not Applicable
11.3.2.2.8 | Construction of 7 Stand pipes, Reticulation and reservoir | Construction of Sigodlweni Borehole Development | B1 | Increase access to municipal services | Number of targeted reticulation infrastructure completed |  | None | None | 8 targeted reticulation infrastructure completed by 30 June 2017 | Equipping of borehole, Installation of Generator pump, Reservoir, Reticulation, Raising Main and 9 Stand Pipe Completed | Y | R2 400 000.00 | 2397321.25 | None | None | Progress Report, Completion Certificate | Y | Not Applicable
11.3.2.2.9 | Construction of 6 stand pipes, Reticulation and reservoir | Construction of Lundini Borehole Development | B1 | Increase access to municipal services | Number of targeted reticulation infrastructure completed |  | None | None | 7 targeted reticulation infrastructure completed by 30 June 2017 | Equipping of borehole, Installation of Generator pump, Reservoir, Reticulation, Raising Main and 6 Stand Pipe Completed | Y | R2 200 000.00 | 2200000 | None | None | Progress Report, Completion Certificate | Y | Not Applicable
11.3.2.2.10 | Construction of 7 stand pipes, Reticulation and reservoir | Construction of Maqongwane Borehole Development | B1 | Increase access to municipal services | Number of targeted reticulation infrastructure completed |  | None | None | 8 targeted reticulation infrastructure completed by 30 June 2017 | Equipping of borehole, Installation of Generator pump, Reservoir, Reticulation, Raising Main and 7 Stand Pipe Completed | Y | R2 000 000.00 | 2000000 | None | None | Progress Report, Completion Certificate | Y | Not Applicable
11.3.2.2.11 | Construction of 10 stand pipes, Reticulation and reservoir | Construction of Plangeni Ext and Sea View Borehole Development | B1 | Increase access to municipal services | Number of targeted reticulation infrastructure completed |  | 12 | 12 | 11targeted reticulation infrastructure completed by 30 June 2017 | Equipping of borehole, Installation of Generator pump, Reservoir, Reticulation, Raising Main and 10 Stand Pipe Completed | Y | R2 300 000.00 | 2296918.1 | None | None | Progress Report, Completion Certificate | Y | Not Applicable
11.3.2.2.12 | Construction of Reticulation and 15 Stand Pipes | Construction of Mzamba and Kimberly Reticulation Scheme Development | B1 | Increase access to municipal services | Number of targeted reticulation infrastructure completed |  | None | None | 16 targeted reticulation infrastructure completed by 30 June 2017 | Equipping of borehole, Installation of Generator pump, Reservoir, Reticulation, Raising Main and 15 Stand Pipe Completed | Y | R6 500 000.00 | 6421544.94 | None | None | Progress Report, Completion Certificate | Y | Not Applicable
11.3.2.2.13 | Construction of 6 stand pipes and reservoir | Construction of Mganko Borehole Development | B1 | Increase access to municipal services | Number of targeted reticulation infrastructure completed |  | None | None | 7 targeted reticulation infrastructure completed by 30 June 2017 | Equipping of borehole, Installation of Generator pump, Reservoir, Reticulation, Raising Main and 6 Stand Pipe Completed | Y | R2 900 000.00 | 2899846.41 | None | None | Progress Report, Completion Certificate | Y | Not Applicable
11.3.2.2.14 | Construction of 7 stand pipes, Reticulation and reservoir | Construction of Ku-Bha Borehole Development | B1 | Increase access to municipal services | Number of targeted reticulation infrastructure completed |  | None | None | 8 targeted reticulation infrastructure completed | Drilling of borehole, Equipping of borehole, Installation of Generator pump, Reservoir, Reticulation, Raising Main and 10 Stand Pipe Completed | Y | R2 200 000.00 | 2194874.29 | None | None | Progress Report, Completion Certificate | Y | Not Applicable
11.3.2.2.15 | Construction of 5 stand pipes and reservoir | Construction of Dayimane Borehole Development | B1 | Increase access to municipal services | Number of targeted reticulation infrastructure completed |  | None | None | 7 targeted reticulation infrastructure completed by 30 June 2017 | Drilling of borehole, Equipping of borehole, Installation of Generator pump, Reservoir, Reticulation, Raising Main and 5 Stand Pipe Completed | Y | R2 000 000.00 | 2088193.65 | The drilled borehole Colapse and the contractor had to do drill another borehole in order the borehole to function, hence the expenditure is too high | Project is Completed and scheme is functioing well on site | Progress Report, Completion Certificate | Y | Not Applicable

## 11.3.2.3. PMU-NTABANKULU
INFRASTRUCTURE DEVELOPMENT & MUNICIPAL SERVICES
11.3.2.3. NTABANKULU PROJECTS
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.2.3.1 | 400 VIPs constructed | ANDM VIP SANITATION NTABANKULU WARD 3&7 | B1 | Increase access to municipal services | Number of households with access to sanitation facilities in Ntabankulu ward 3&7 | 50503011 | 120 | 0 | 400households with access to sanitation facilities in Ntabankulu ward 3&7 by 30 June 2017 | 370 households with access to sanitation facilities in Ntabankulu ward 7 by 30 June 2017 | N | R 4 108 179.00 | 3958109.14 | 30 units were not constructed in ward 3 because Ward 3 needed more than 400 VIP units hence olny Ward 7 could be compeleted | Ward 3 to be implemented in 2017/2018 FY | Happy Letters & Completion certificate | Y | 2015-2016 non achievement to be completed in 2016/2017 financial year
11.3.2.3.2 | Mechanical and Electrical works and village reticulation | Nyokweni / Bomvini Regional Water Supply Scheme | B1 | Increase access to municipal services | % of Nyokweni / Bomvini Regional Water Supply Scheme Completed | 50 504 901 | 100% | 100% | 100% Nyokweni / Bomvini Regional Water Supply Scheme Completed by 30 June 2017 | Civil works is at 95 % complete and ordering of Mechanical & Electrical components is underway | N | R 20 500 000.00 | 19805668.21 | Slow manufacturing of the Mechanical Components | Contractor was urged to speed up the work and update the client if there is any problem | Minutes of the Progress Meeting and Progress Report | Y | 2015-2016 non achievement to be completed in 2016/2017 financial year
11.3.2.3.3 | Water and Sewer connection | Upgrading of Ntabankulu Sewer | B1 | Increase access to municipal services | % of Ntabankulu Sewer Upgrade completed | 50500291 | 100% | 80% | 100% Ntabankulu Sewer Upgrade completed by 30 June 2017 | Civil works is at 95 % complete and ordering of Mechanical & Electrical components is underway | N | R 26 000 000.00 | 34970110 | Project could not be completed due to delays caused by the community | Project will be completd in 2017-2018 financial year. | Minutes of the Progress Meeting and Progress Report | Y | 2015-2016 non achievement to be completed in 2016/2017 financial year
11.3.2.3.4 | Water and Sewer connection to 471 RDP houses | Upgrading of Ntabankulu Sewer | B1 | Increase access to municipal services | Water and Sewer connection to 471 RDP Houses | 50 500 | None | None | 471 Water and Sewer connection to 471 RDP Houses by 30 June 2017 | Water and Sewer pipe line 90% Complete | N |  |  | Project could not be completed due to delays caused by the community, Budget fundingt that was meant to come from DOH was unavailble hence there is over expenditure | ANDM is still having bilateral with DOH and the project will be completed in 2017-2018 financial year | Minutes of the Progress Meeting and Progress Report | Y | Not Applicable
11.3.2.3.5 | Construction of Village Reticulation pipeline network, drilling of Boreholes and construction of Reservoirs | Implementation of WSIG (MWIG) Programme in Ntabankulu LM | B1 | Increase access to municipal services | % Implementation of Ntabankulu WSIG programme completed | 50 500 356 | 100% | 100% | 100% Implementation of Ntabankulu WSIG programme completed by 30 June 2017 | Construction of Village Reticulation pipeline network, drilling of Boreholes and construction of Reservoirs have been completed. | Y | R 32 171 000.00 | R 32 171 000.00 | None | None | Completion Certiface & Close-out Reports | Y | Not Applicable

## 11.3.2.4. PMU-UMZIMVUBU
INFRASTRUCTURE DEVELOPMENT & MUNICIPAL SERVICES
11.3.2.4. UMZIMVUBU PROJECTS
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.2.4.1 | 1000 VIPs constructed | ANDM VIP SANITATION MZIMVUBU WARD 2 & 21 | B1 | Increase access to municipal services | Number of households with access to sanitation facilities in Mzimvubu ward 02 & 21 | 50503011 | 180 | 180 | 1000 households with access to sanitation facilities in Mzimvubu ward 02 & 21 by 30 June 2017 | 1010 households with access to sanitation facilities in Mzimvubu ward 02 & 21 by 30 June 2017 | Y | R 8 381 485.20 | 8381485.2 | None | None | Completion Certificate | Y | Not Applicable
11.3.2.4.2 | Construction of 15 km Reticulation pipeline network | Cabazana Bulk Water Supply | B1 | Increase access to municipal services | Km’s of Cabazana reticulation pipeline completed | 50 500 471 | 5Km | 5Km | 15Kms Cabazana reticulation pipeline completed by 30 June 2017 | Project reached pratical completion, only comissioning outstading | N | R 11 000 000.00 | 10266939.5 | Slow progress by contractor | Contrator to expedite comissioning | Progress Report | Y | Not Applicable
11.3.2.4.3 | Construction of 2 km Reticulation pipeline network | Hlane water Supply - phase 2 | B1 | Increase access to municipal services | Km’s of Hlane reticulation pipeline completed | 50 500 131 | 100% | 0 | 2Kms Hlane reticulation pipeline completed by 30 June 2017 | Project completed | Y | R 1 500 000.00 | 1327656.82 | None | None | Completion Certificate | Y | Project will be completed in 2016-2017 financial year
11.3.2.4.4 | Completed Designs and working Drawings | KwaBhaca Regional BWSS | B1 | Increase access to municipal services | Number of Kwabaca Regional BWSS Designs and working Drawings Approved | 50 500 431 | 100% | 0 | 1 Kwabaca Regional BWSS Designs and working Drawings Approved by 30 June 2017 | Design and working drawings approved, Two Reservior 100% complete, and 5 km pipiline laid. Site Eblished at the WTW and Operators ohuses is at foundation level | Y | 39026540 | 39741893.94 | None | None | Progress Report | Y | Project will be completed in 2016-2017 financial year
11.3.2.4.5 | Construction of 8 km Reticulation pipeline network | Ntibane Water supply Scheme: Phase 2 | B1 | Increase access to municipal services | Km’s of Ntibane reticulation pipeline completed | 50 500 3081 | 10% | 0 | 8Kms Ntibane reticulation pipeline completed by 30 June 2017 | 14 km of pipeline have been laid | Y | R 21 330 000.00 | 19668075.35 | None | None | Minutes of the Progress Meeting and Progress Report | Y | Project will be completed in 2016-2017 financial year
11.3.2.4.6 | Construction of Village reticulation with associated works | Qwidlana water supply - Area 3&4 | B1 | Increase access to municipal services | % of targeted reticulation infrastructure completed | 50 500 441 | 100% | 0 | 100% of targeted reticulation infrastructure completed by 30 June 2017 | 95% of targeted reticulation infrastructure completed | N | R 4 500 000.00 | 275513.14 | Contractor worked for 4 months without Supervision due to none pamynet of consultant by ANDM. Contractor subsequnlty left the site without cretfication of work done in orer to complete project. | Contractor returned to site to complete the works during 2017-2018 financial year | Email and Progress Report | Y | Project will be completed in 2016-2017 financial year
11.3.2.4.7 | Construction of 12 km Reticulation pipeline network | Umzimvubu ward 13 water supply | B1 | Increase access to municipal services | Km’s of Ward 13 reticulation pipeline completed | 50 500 359 | 7Km | 7Km | 12Kms of Ward 13 reticulation pipeline completed by 30 June 2017 | 12Kms of Ward 13 reticulation pipeline completed | Y | R3 000 000.00 | 2977349.61 | Eskom has not been connected in order to see project to completion | ANDM ot make follow up with Eksom | None | N | Not Applicable
11.3.2.4.8 | Construction of 12 km Reticulation pipeline network | Umzimvubu ward 14 water supply | B1 | Increase access to municipal services | Km’s of Ward 14 reticulation pipeline completed | 50 500 563 | 12Km | 19Km | 12Kms of Ward 14 reticulation pipeline completedby 30June 2017 | 15Kms of reticulation pipeline completed,Pump house is 70% complete & 46 Stand taps completed | Y | R 7 500 000.00 | 5466641.11 | Slow progress by contractor, Contracotr has not claimed in Q4 intends claiming in Q 1 of 17/18 FY when he moves out of site | Contrator to expedite project completion and submit final claim | Progress Report , minutes | Y | Not Applicable
11.3.2.4.9 | Construction of 10 km Reticulation pipeline network | Umzimvubu ward 22 water supply scheme | B1 | Increase access to municipal services | Km’s of Ward 22 reticulation pipeline completed | 50 504 901 | 3Km | 3Km | 10Kms of Ward 22 reticulation pipeline completed by 30 June 2017 | Project completed | Y | R 2 500 000.00 | 1303173.26 | Project over budgeted | None | Completion Certificate | Y | Not Applicable
11.3.2.4.10 | Construction of Village Reticulation pipeline network, drilling of Boreholes and construction of Reservoirs | Implementation of WSIG (MWIG) Programme in Umzimvubu LM | B1 | Increase access to municipal services | Number of targeted reticulation infrastructure completed | 50 500 311 | 100% | 80% | 61 of targeted reticulation infrastructure completed by 30 June 2017 | 7 out of 7 Projects completed. | Y | R 12 500 000.00 | 14649918.34 | Scope extended to cater for incomplete project from previous FY ( Additional funding soruced from Kwabaca WSOG) | None | Completion Certificate. | Y | Project will be completed in 2016-2017 financial year
11.3.2.4.11 | Construction of Water Treatment works, Bulk mains and associated works | Mount Ayliff Peri-Urban Water Project | B1 | Increase access to municipal services | % Completion of Mount Ayliff Water Project | 50 500 321 | None | None | 100% Completion of Mount Ayliff Water Projectby 30 June 2017 | WTW Overall Progres is 12% and Bulk Mainsand Reserviors progress is avarage | N | R 41 594 655.00 | 41167054 | Inaccurate target and budget limitation | An application for funding has been submitted to DWS and project to be completed in 2020 | Progress Reports | Y | Not Applicable
11.3.2.4.12 | KwaBhaca South Le water project complete | KwaBhaca South Leg Augmentation | B1 | Increase access to municipal services | Number of targeted reticulation infrastructure completed | 50509931 | 100% | 100% | 100% Completion of Kwabhaca Southern Leg Project by 30 June 2017 | Kwabhaca Southern Leg Project 97% Complete | N | R10 000 000.00 | 7132256.49 | Continued late delivery of materials during the course of the contract has resulted in slower than expected progress of the works | Contractor to expedite completion of project | Progress Reports | Y | Not Applicable

## 11.3.2.5 PMU-ISD-PROJECTS
INFRASTRUCTURE DEVELOPMENT & MUNICIPAL SERVICES
11.3.2.5. ISD PROJECTS
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.2.5.1 | Implementation of ISD Guidelines. | Strengthening of District ISD services | A2 | Optimize systems, administration and operating procedures | Number of ISD Forum Meetings held | N/a | 4 ISD Forum Meetings held by 30 June 2016 | 4 ISD Forum Meeting held | 4 ISD Forum Meetings held by 30 June 2017 | 4 ISD Forum Meeting held | Y | 0 | 0 | None | None | Minutes Attendance Register and Agenda | Y | Not Applicable
11.3.2.5.2 | Implementation of ISD Guidelines. | Strengthening of District ISD services | A2 | Optimize systems, administration and operating procedures | Number of meetings held with service delivery units | N/a | 4 meetings held with service delivery units by 30 June 2016 | 4 Meetings held with service delivery units | 4 meetings held with service delivery units by 30 June 2017 | 4 Meetings held with service delivery units | Y | 0 | 0 | None | None | Minutes Attendance Register and Agenda | Y | Not Applicable
11.3.2.5.3 | Protective clothing and equipment delivered and distributed to all Unit staff members | Procurement of protective clothing | A2 | Optimize systems, administration and operating procedures | % of Staff supplied with protective clothing | N/a | 100% staff supplied with protective clothing by 30 June 2016 | 100% staff supplied with protective clothing by 30 June 2016 | 100% staff supplied with protective clothing by 30 June 2017 | None | N | 0 | 0 | The ISD Section staff were not part of IDMS when the business plan was drawn, therefore they are not budgeted | None | Order and Invoices | N | Not Applicable
11.3.2.5.4 | ISD Public Education and Awareness Workshops held in 4 LMs | ISD Public Education and Community Awareness Programme | E1 | Promote public participation and meaningful good governance | Number of LMs workshopped on water usage, health and hygiene | N/a | 4 LMs workshopped on water usage, health and hygiene by 30 June 2016 | Coordinated Water usage, health and hygiene workshopin 4 LMs | 4 LMs workshopped on water usage, health and hygiene by 30 June 2017 | Coordinated Water usage, health and hygiene workshopin 4 LMs | Y | 0 | 0 | None | None | Program, Register, Report and Educational Material | Y | Not Applicable
11.3.2.5.5 | Implementation of ANDM Terms of Reference for ISD Work | ISD Coordination | E1 | Promote public participation and meaningful good governance | Number of Communities updated on all approved projects within their area | N/a | 24 Communities updated on all approved projects within their area by 30 June 2016 | 24 Communities updated on all approved projects within their area | 24 Communities updated on all approved projects within their area by 30 June 2017 | 24 Communities updated on all approved projects within their area | Y | 0 | 0 | None | None | Minutes and Attendace registers | Y | Not Applicable
11.3.2.5.6 | Implementation of ANDM Terms of Reference for ISD Work | ISD Coordination | E1 | Promote public participation and meaningful good governance | Number of projects capacitated with PSCs and VHWs with relevant training | N/a | 4 projects capacitated with PSCs and VHWs with relevant training by 30 June 2016 | 4 projects capacitated with PSCs and VHWs with relevant training | 4 projects capacitated with PSCs and VHWs with relevant training by 30 June 2017 | 4 projects capacitated with PSCs and VHWs with relevant training | Y | 0 | 0 | None | None | Training Report and Attendance Registers | Y | Not Applicable
11.3.2.5.7 | Implementation of ANDM Terms of Reference for ISD Work | ISD Coordination | E1 | Promote public participation and meaningful good governance | Number of Functional PSCs | N/a | 17 Functional PSCs by 30 June 2016 | 17 Functional PSCs coordinated | 17 Functional PSCs by 30 June 2017 | 17 Functional PSCs coordinated | Y | 0 | 0 | None | None | Meeting Minute, Attendance Registers and PSC List | Y | Not Applicable
11.3.2.5.8 | Implementation of ANDM Terms of Reference for ISD Work | ISD Coordination | E1 | Promote public participation and meaningful good governance | Number of Communities visited for inputs after project completion | N/a | 16 Communities visited for inputs after project completion by 30 June 2016 | 16 Communities visited for inputs after project completion | 16 Communities visited for inputs after project completion by 30 June 2017 | 16 Communities visited for inputs after project completion | Y | 0 | 0 | None | None | Meeting Minutes, Attendance Registers and Close-out Report | Y | Not Applicable
11.3.2.5.9 | Implementation of ANDM Terms of Reference for ISD Work | ISD Coordination | E2 | Strengthening Governance and reduce risk | Number of financial MIG reports reconciled, drafted and submitted | N/a | 12 financial MIG reports reconciled, drafted and submitted by30 June 2016 | 12 financial MIG reports reconciled, drafted and submitted | 12 financial MIG reports reconciled, drafted and submitted by30 June 2017 | 12 financial MIG reports reconciled, drafted and submitted | Y | 0 | 0 | None | None | Non-Financial MIG Reports | Y | Not Applicable

## 11.3.3 IDMS-WSP
INFRASTRUCTURE DEVELEOPMENT & MUNICIPAL SERVICES
11.3.3. WATER SERVICES PROVISION
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.3.1 | Increased availability to vehicles for technical staff | Vehicles Leasing | A2 | Optimize systems, administration and operating procedures | Number of vehicles leased | 1500044263 | 24 | 24 | 24 vehicles leased by 30 June 2017 | 24 vehicles leased by 30 June 2017 | Y | 24000000 | 2518768.88 | The budget incorporates the leased water services trucks and the expenditure reflects the 24 vehicles leased which excludes the leased trucks hence under expenditure | None | Invoices, and Monthly Reports from fleets | Y | Not Applicable
11.3.3.2 | 6 municipal buildings and structural components maintained | BUILDING MAINTENANCE | B2 | Improve the quality of Municipal Infrastructure services | Number of Municipal buildings and structural components maintained | 1500038001 | 6 | 6 | 6 Municipal buildings and structural components maintained by 30 June 2017 | 6 Municipal buildings and structural components maintained by 30 June 2017 | Y | R 2 000 000.00 | 1894780.81 | None | None | Works Order / Appointment letter and Progress Report | Y | Not Applicable
11.3.3.3 | Ensure the payment of electricity for the operation of pumps. | Electricity | D2 | Improve expenditure management and controls | Number of Invoices submitted for payment. | 1500044033 | 32 | 32 | 32 Invoices submitted for payment by 30 June 2017 | 32 Invoices submitted for payment by 30 June 2017 | Y | 11000000 | 11469067.27 | None | None | Invoices proof of payments | Y | Not Applicable
11.3.3.4 | The payment of bulk water | Bulk Water Purchases | D2 | Improve expenditure management and controls | Number of Invoices submitted for payment. | 1500041001 | 24 | 24 | 24 Invoices submitted for payment by 30 June 2017 | 24 Invoices submitted for payment by 30 June 2017 | Y | R6 500 000.00 | 7094920.08 | None | None | Invoices proof of payments | Y | Not Applicable
11.3.3.5 | 10 Drought relief schemes completed, which constitutes drilling and testing of boreholes | Drought Relief Intervention | F2 | Improve Disaster Management and Prevention | Number of Drought relief schemes provided | 5050300111 | 18 | 35 | 10 Drought relief schemes provided by30 June 2017 | 5 Drought relief schemes provided by30 June 2017 | N | 5639330 | 2000000 | The institution experienced budget constraints and the drilling and testing of boreholes programme was put on hold for the 2016/17 Fy | The programme cntinues in 2017 /18 Fy | Work Instructions and Payment Certificates | Y | Not Applicable

## 11.3.3.1. WSP-MATATIELE PROV
INFRASTRUCTURE DEVELOPMENT & MUNICIPAL SERVICES
11.3.3.1. MATATIELE PROVISION
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.3.1.1 | 2 Matatiele Water services infrastructure refurbished and operational | Refurbishment and Replacement of Water Infrastructure - Matatiele | B2 | Improve the quality of Municipal Infrastructure services | Number of water services infrastructure refurbished | 505090851 | 5 | 3 | 1water services infrastructure refurbished by 30 June 2017 | 1water services infrastructure refurbished by 30 June 2017 | Y | R10 348 491.00 | R10 348 491.00 | None | None | Work instruction and completion reports | Y | The budget for 2015-2016 was divated to address drought impact in Matatiele hence under performance in 2015-2016 financial year, however the project was achieved in 2016-2017 financial year
11.3.3.1.2 | 47 Matatiele water and sanitation schemes fully operational | Maintenance and Repairs of Matatiele Water & Sanitation Infrastructure schemes | B3 | Improve the quality and flow of water and sanitation | Number of water schemes maintained with 100% adherence to maintenance plan | 1500038014 | 47 | 47 | 47 water schemes maintained with 100% adherence to maintenance plan by 30 June 2017 | 47 water schemes maintained with 100% adherence to maintenance plan by 30 June 2017 | Y | R 18 600 000.00 | 24492505.92 | Water services Infrastruct is ageing and demands more budget on repairs & maintennce hence over expenditure | The ANDM has to increase the repairs & maintence budget | Water and Sanatation maintenance Monthly reports | Y | Not Applicable

## 11.3.3.3. MBIZANA PROV
INFRASTRUCTURE DEVELOPMENT & MUNICIPAL SERVICES
11.3.3.2. MBIZANA PROVISION
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.3.2.1 | 1 Mbizana Water services (Cluster of villages) infrastructure refurbished and operational | Refurbishment and Replacement of Water Infrastructure -Mbizana | B2 | Improve the quality of Municipal Infrastructure services | Number of water services infrastructure refurbished | 505090831 | 1 | 0 | 1 water services infrastructure refurbished by 30 June 2017 | 1 water services infrastructure refurbished by 30 June 2017 | Y | R1 500 000.00 | 946376.45 | The institution experiences financial or budgetary constraints resulting in this programme to be placed on hold | The refurbishment project is being fast-tracked for completion in Q1 of 2017 /18 Fy | Appointment Letter, Progress Reports | Y | The budget for 2015-2016 was divated to address the impact of drought in Mbizana, however the project was achieved in 2016-2017 financial year.
11.3.3.2.2 | 1Mbizana Pond refurbished | Refurbishment and Replacement of Sanitation Infrastructure - Mbizana Ponds | B2 | Improve the quality of Municipal Infrastructure services | Number of Sanitation schemes refurbished | 505000251 | 1 | 0 | 1 Sanitation schemes refurbished by 30 June 2017 | 1 Sanitation schemes refurbished by 30 June 2017 | Y | R3 200 000.00 | 3146588.75 | The institution experiences financial or budgetary constraints resulting in this programme to be on hold | The refurbishment project is being fast-tracked for completion in Q1 of 2017 /18 Fy | Progress Reports and payment Certificate | Y | The budget for 2015-2016 was divated to address the impact of drought in Mbizana however the project was achieved in 2016-2017 financial year.
11.3.3.2.3 | 32 Mbizana water and sanitation schemes fully operational | Repairs and Maintenance of Water & Sanitation Infrastructure schemes -Mbizana | B3 | Improve the quality and flow of water and sanitation | Number of water schemes maintained with 100% adherence to maintenance plan | 1500038012 | 32 | 32 | 32 water schemes maintained with 100% adherence to maintenance plan by 30 June 2017 | 32 water schemes maintained with 100% adherence to maintenance plan by 30 June 2017 | Y | R5 400 000.00 | 6654335.87 | Water services Infrastruct is ageing and demands more budget on repairs & maintennce | The ANDM has to increase the repairs & maintence budget | Water and Sanitation maintanance monthly reports | Y | Not Applicable

## 11.3.3.4. NTABANKULU PROV
INFRASTRUCTURE DEVELOMENT & MUNICIPAL SERVICES
11.3.3.3. NTABANKULU PROVISION
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.3.3.1 | 1 Ntabankulu Water services infrastructure refurbished and operational | Refurbishment and Replacement of Water Infrastructure -Ntabankulu | B2 | Improve the quality of Municipal Infrastructure services | Number of water services infrastructure refurbished | 505090871 | 1 | 0 | 1water services infrastructure refurbished by 30 June 2017 | 1water services infrastructure refurbished by 30 June 2017 | Y | 2000000 | 921970 | The institution experiences financial or budgetary constraints resulting in this programme to be placed on hold hence under expenditure | The refurbishment project is being fast-tracked for completion in Q1 of 2017 /18 Fy | Appointment Letter, Progress Reports | Y | The budget for 2015-2016 was divated to address the impact of drought in Ntabankulu, however the project was achieved in 2016-2017 financial year.
11.3.3.3.2 | 1Ntabankulu Pond refurbished | Refurbishment and Replacement of Sanitation Infrastructure – Ntabankulu Ponds | B2 | Improve the quality of Municipal Infrastructure services | Number of Sanitation schemes refurbished | 505000361 | 1 | 1 | 1 Number of Sanitation schemes refurbished by 30 June 2017 | 1 Number of Sanitation schemes refurbished by 30 June 2017 | Y | 860670 | 860670 | None | None | Progress Reports and payment Certificate | Y | Not Applicable
11.3.3.3.3 | 1 Mnceba Water services (Cluster of villages) infrastructure refurbished and operational | Refurbishment and Replacement of Water Infrastructure – Mnceba Water Scheme | B2 | Improve the quality of Municipal Infrastructure services | Number of water services infrastructure refurbished | 505090881 | 1 | 0 | 1water services infrastructure refurbished by 30 June 2017 | 1water services infrastructure refurbished by 30 June 2017 | Y | R1 500 000.00 | 650000 | The institution experiences financial or budgetary constraints resulting in this programme to be on hold | The refurbishment project is being fast-tracked for completion in Q1 of 2017 /18 Fy | Payment certificate progress Report and Completion certificates | Y | The budget for 2015-2016 was divated to address the impact of drought in Ntabankulu, however the project was achieved in 2016-2017 financial year.
11.3.3.3.4 | 33 Ntabankulu water and sanitation schemes fully operational | Repairs and Maintenance of Water & Sanitation Infrastructure schemes - Ntabankulu | B3 | Improve the quality and flow of water and sanitation | Number of water schemes maintained with 100% adherence to maintenance plan | 1500038015 | 33 | 33 | 33 water schemes maintained with 100% adherence to maintenance plan by 30 June 2017 | 33 water schemes maintained with 100% adherence to maintenance plan by 30 June 2017 | Y | R7 000 000.00 | 5677953.57 | None | None | Water and Sanitation maintanance monthly reports | Y | Not Applicable

## 11.3.3.5. UMZIMVUBU PROV
INFRASTRUCTURE DEVELEOPMENT & MUNCICPAL SERVICES
11.3.3.4. UMZIMVUBU PROVISION
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.3.3.4.1 | 1 Umzimvubu Water services infrastructure refurbished and operational | Refurbishment and Replacement of Water Infrastructure in Umzimvubu | B2 | Improve the quality of Municipal Infrastructure services | Number of water services infrastructure refurbished | 505090841 | 4 | 1 | 1 water services infrastructure refurbished by 30 June 2017 | 1 water services infrastructure refurbished by 30 June 2017 | Y | R2 300 000.00 | 2328849.78 | None | None | Work instruction and completion reports | Y | The budget for 2015-2016 was divated to address the impact of drought in Mzimvubu, however the project was achieved in 2016-2017 financial year.
11.3.3.4.2 | 1 Mnceba Water services (Cluster of villages) infrastructure refurbished and operational | Refurbishment and Replacement of Water Infrastructure – Mnceba Water Scheme | B2 | Improve the quality of Municipal Infrastructure services | Number of water services infrastructure refurbished | 505090881 | 1 | 0 | 1water services infrastructure refurbished by 30 June 2016 | 1water services infrastructure refurbished by 30 June 2016 | Y | R1 500 000.00 | 550000 | The institution experiences financial or budgetary constraints resulting in this programme to be placed on hold | The refurbishment project is being fast-tracked for completion in Q1 of 2017 /18 Fy | Payment certificate progress Report and Completion certificates | Y | The budget for 2015-2016 was divated to address the impact of drought in Mzimvubu, however the project was achieved in 2016-2017 financial year.
11.3.3.4.3 | 75 Umzimvubu water and sanitation schemes fully operational | Maintenance and Repairs of Umzimvubu Water & Sanitation Infrastructure schemes | B3 | Improve the quality and flow of water and sanitation | Number of water schemes maintained with 100% adherence to maintenance plan | 1500038013 | 75 | 75 | 75water schemes maintained with 100% adherence to maintenance plan by 30 June 2017. | 75water schemes maintained with 100% adherence to maintenance plan by 30 June 2017. | Y | R11 000 000.00 | 17157995.94 | Water services Infrastruct is ageing and demands more budget for repairs & maintennce | The ANDM has to increase the repairs & maintence budget | Water and Sanitation maintanance monthly reports | Y | Not Applicable

## IDMS PERFORMANCE
INFRASTRUCTURE DEVELOPMENT & MUNICIPAL SERVICES
ACHIEVED TARGETS VS NOT ACHIEVED BY UNIT
Unit | Total No. of targets | No. Achieved | No. Not Achieved | % Achieved | % Not Achieved
WSA | 18 | 12 | 6 | 67% | 33%
WCDM | 2 | 0 | 2 | 0% | 100%
PMU | 67 | 33 | 34 | 49% | 51%
WSP | 17 | 16 | 1 | 94% | 6%
Department | 104 | 61 | 43 | 59% | 41%

## 11.4.1 CUSTOMER CARE
COMMUNITY DEVELOPMENT SERVICES
11.4.1. Customer Care
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.4.1.1 | Customer care day for all ANDM employees held | customer care day | E1 | Promote Public participation and Good Meaningful Governance | Number of Customer care day for all ANDM employees held | R 300 000.00 | OPEX | 1 | 1 | 1 Customer Care day held by 30 June 2017 | 1 customer care day held on the 20 Nomber 2016 | Y | R 300 000.00 | R365 865 ,00 | Rapid increase in the number Of ANDM employees | None | Attendance registers | Y | The project has been succesfully achieved even in the previous financial year
11.4.1.2 | Increased number of ANDM Customer Care line Users | Customer Care Centre Marketing | E1 | Promote Public participation and Good Meaningful Governance | Number of road shows conducted | R120 000.00 | OPEX | 4 | 5 | 4 road shows conducted by 30 June 2017 | 5 roadshows were conducted in all Lms within the district | Y | R120 000.00 | 88000 | The number of roadshows conducted was more that planned number based on the demand by communities | None | Attendance registers | Y | Previous years pergomnace had been good as well, the municipality will keep this project as information keeps on developing and updated year by year
11.4.1.3 | All ANDM Service Stakeholders, LM’s and units with prioritized Batho Pele flagship programs | Batho Pele Championship Programme (Implementation) | E1 | Promote Public participation and Good Meaningful Governance | Number of municipalities supported of Batho Pele initiatives | R 40 000.00 | OPEX | 4 | 3 | 4 municipalities supported of Batho Pele initiatives by 30 June 2017 | 1 local municipality municipality was supported | N | R 40 000.00 | 10000 | Munipal wide finacial challenges made it impossible to meet the target | Proper planning and budgetting by the municipalityto ensure that planned projects are implemented | Copy of order requisition | Y | Under performnace for 2015-2016 was not addressed due to financial constraints
11.4.1.4 | All ANDM Service Stakeholders, LM’s and units with prioritized Batho Pele flagship programs | Batho Pele Championship Programme (Implementation) | E1 | Promote Public participation and Good Meaningful Governance | To strengthen Customer Care Unit/s within the district | R 160 000.00 | 1600 0 | 4 | 3 | 5 Capacity building of customer care offices within the district | None | N | R 160 000.00 | 0 | Target could not be achieved as it had financial implications attached and yet the municipality was facing fincial challenges | Proper planning and budgetting by the munipality | None | N | Under performnace for 2015-2016 was not addressed due to financial constraints
11.4.1.5 | Customer satisfaction surveys conducted for all LMs | Customer Satisfaction Surveys | E1 | Promote Public participation and Good Meaningful Governance | Number of customer satisfactory surveys devices procured | 680000 | Vote: OPEX | 1 | 0 | 3 customer satisfactory surveys devices procured by 30 June 2017 | 3 Customer satisfaction survey devices were procured and a aservice provider was appointed to conduct customer satsfaction survey ( research) | Y | 680000 | 681000 | None | None | Copy of order requisition | Y | Customer satifaction survey project could not completely achieved in the previous year but this year we managed to appoint a service provider to do research and to procure customer satisfaction survey devices
11.4.1.6 | Effective and efficient management of all ANDM customers through ANDM reception office and Call centre | Customer Service | E1 | Promote Public participation and Good Meaningful Governance | % of customers assisted | 0 | Opex | None | None | 100% customers assisted by 30 June 2017 | 100% assisted by 30 June 2017 | Y | 0 | 0 | None | None | Visitors register | Y | Performane is the same as the previous year's.
11.4.1.7 | Ensure prompt and efficient management of all presidential Hotline cases | Customer Service | E1 | Promote Public participation and Good Meaningful Governance | % of presidential hotline cases attended | 0 | Opex | None | None | 100% presidential hotline cases attended by 30 June 2017 | 85% | N | 0 | R0 00 | Provincial wide system challenges | System upgrade | Complaints/queries register | Y | Not Applicable
11.4.1.8 | All local Community Safety Fora operational and effective | Implementation of district Crime Prevention Programme | F2 | Improve community and social safety of the district | Number of active community safety forums | R 0 | Vote: OPEX | 4 | 4 | 4 active community safety forums he by 30 June 2017 | 4 local municipalities were supported in their community safety programmes | Y | 0 | 0 | None | None | Attendance registers | Y | Perfomance is the same as the previous year's.

## 11.4.2 CDS - DISASTER
COMMUNITY DEVELOPMENT SERVICES
11.4.2. DISASTER RISK MANAGEMENT SERVICES
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.4.2.1 | Reviewed and adopted Disaster Management policy and framework | Disaster Management Plans and policy framework for the whole ANDM area of jurisdiction- Local Municipalities | A2 | Optimize systems, administration and operating procedures | Number of Disaster management plan and policy framework reviewed | 0 | 16000-44030 | 4 | 4 | 4 Disaster management plan and policy framework reviewed by 30 June 2017 | four disaster management plans have been crafted for LM and implementations plans | Y | 0 | 0 | None | None | copy of plans | Y | Not Applicable
11.4.2.2 | Improvement in support and relief | Disaster Management response, recovery and rehabilitation | B1 | Increase access to municipal services | Number of disaster affected households receiving support and relief | 2900000 | 16000-44273 | 100% | 100% | 100% disaster affected households receiving support and relief by 30 June 2017 | 100 % reponse to reported incident & disasters ( 1948 Households assisted) | Y | 2900000 | 2312910 | None | None | list of assisted house holds | Y | Not Applicable
11.4.2.3 | Awareness campaigns conducted in vulnerable communities on mitigation of disasters | Disaster Management Public Education & Community Awareness Programme | E1 | Promote Public participation and Good Meaningful Governance | Number of Disaster Management awareness campaigns conducted | R200 000.00 | 16000-44030 | 16 | 28 | 40 Disaster Management awareness campaigns conducted by 30 June 2017 | 41 awareness campaigns were conducted | Y | R200 000.00 | 170822.28 | None | None | attandance registers | Y | Not Applicable
11.4.2.4 | Completed Disaster Management Plan | Disaster Management Plan | F2 | Improve Disaster Management and Prevention | Number of completed Disaster Management Plan | 400000 | 16000-44030 | None | None | 1 completed Disaster Management Plan 30 June 2017 | 1 plan commpleted | Y | 400000 | 389107 | None | None | attanandance register and copy of plan | Y | Not Applicable
11.4.2.5 | people capacitated on disaster management KPAs | Disaster Management Capacity Building | F2 | Improve Disaster Management and Prevention | Number of people capacitated on disaster management KPAs | 200000 | 16000-44030 | 40 | 43 | 60 people capacitated on disaster management KPAs 30 June 2017 | the project was placed in abeyance due to financial constraints | Not Achieved | 200000 | 0 | the municipality had finaincial challenges and the project has been placed in abayance | the project will be implemented once the financial status of the municipality change | None | N | Not Applicable
11.4.2.6 | To decentralize disaster management centers closer to the people. | Satellite center establishment in Bizana | F2 | Improve Disaster Management and Prevention | Improve Disaster Management and Prevention | R 3 500 000.00 | 506000-161 | 2% | 2% | 1 satellite disaster center constructed 30 June 2017 | the project was placed in abeyance due to financial constraints | Not Achieved | R 3 500 000.00 | 0 | the municipality had finaincial challenges and the project has been placed in abayance | the project will be implemented once the financial status of the municipality change | None | N | Not Applicable
11.4.2.7 |  | Disaster Management Volunteer Programme (Disaster Man Response and Recovery |  | Improve Disaster Management and Prevention | Improve Disaster Management Volunteers | 0 | 16000-44273 | 4 | 4 |  | the project was placed in abeyance due to financial constraints | 0 | 0 | 0 | due to financial constraints the project has been shunned | the project will be implemented once the financial status of the municipality change | project stopped | Y | Not Applicable
11.4.2.8 |  | Procurement of protective equipment & clothing |  | Improve Disaster Management and Prevention | Safety of operational staff | R1 500 000.00 | 16000-44081 | 100% | 100% | 54 protective equipment & clothing procured 30 June 2017 | protective clothing and uniform has been delivered and utilsed by operational staff | Y | R1 500 000.00 | 1500000 | None | None | delivery note | Y | Not Applicable

## 11.4.3. CDS - FIRE AND RESCUE
COMMUNITY DEVELOPMENT SERVICES
11.4.3. Fire and Rescue Services
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.4.3.1 | Maintenance of personnel strength on 20 shifts at 5 stations. | Facilitate the recruitment and support to key Fire & Rescue Service objective | A2 | Optimise systems, administration and operating procedures | Number of fire and rescue shifts maintained. | 0 | N/a | 37 | 37 | 20 fire and rescue shifts maintained by 30 June 2017 | 20 fire and Rescue shifts maintained by 30 June 2017 | Y | 0 | 0 | None | None | shift Rosters | Y | Not Applicable
11.4.3.2 | Availability of equipment | Procurement of Fire and Rescue Services equipment | A3 | Increase performance and efficiency levels | % of required equipment procured | 800000 | 50600181 | 100% | 100% | 100% of required equipment procuredby 30 June 2017 | 0% equipment procured by 30 June 2017 | N | 800000 | 0 | project was advertised but could not be finalised due to Institutional financial crisis | budget allocated to a unit must be utilised by such unit not used to fund unfunded projects | Advert | Y | Not Applicable
11.4.3.3 | Availability of fire engines | Refurbishment of fire engine FCC 829 EC | A3 | Increase performance and efficiency levels | Number of fire engines refurbished | R 350 000.00 | 16000440037 | None | None | 1 fire engines refurbished by 30 June 2017 | No fire engine refurbished by 30 June 2017 | N | 300000 | 0 | project was advertised but could not be finalised due to Institutional financial crisis | budget allocated to a unit must be utilised by such unit not used to fund unfunded projects | Advert | Y | Not Applicable
11.4.3.4 | Functioning upgraded control centre | Control Center Equipment | B2 | Improve the quality of fire ground communications | Number of Control Centres upgraded | 340000 | 5060081 | 1 | 1 | 1 Control Centres upgraded by 30 June 2017 | 1 Control Center upgraded by 30 June 2017 | Y | 340000 | 340000 | None | None | Reports produced from the system | Y | Not Applicable
Invoices
11.4.3.5 |  | Fire and Rescue Internal Capacity building | F3 | Improve the quality of fire ground communications | Number of capacitated employees | 0 | 1600044037 | None | None | 56 capacitated employees | 56 employees capacitated | No | 0 | 0 | None | None | Training attendance Registers and certificates | Y | Not Applicable

## 11.4.4. CDS-MHS
COMMUNITY DEVELOPMENT SERVICES
11.4.4. Municipal Health Services
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.4.4.1 | Employees registered with professional bod by 30 June 2017. | Employee registration with HPCSA | A1 | Improve organization, capacity, knowledge and transformation | Number of employees registered | R30,000.00 | 1600044406 | 100% | 100% | 27 employees registered by 30 June 2017 | 26 employees with renewed annual subscription fees & in good standing | N | R20,000.00 | R32,968.00 | One of the EHPs absconded. Also the payment is usually due by the end of March in each year, but this year it ahs been paid late in May 2017 due to the fct that the municipality has some financial challenges | Once the financial status of the municipality is in order, then the payments will be done as required by HPCSA | Current Practice Cards | Y | Not Applicable
11.4.4.2 | EHPs capacitated in scrutinizing building plans by 30 June 2017 | Surveillance of premises | A1 | Improve organization, capacity, knowledge and transformation | Number of EHPs capacitated in building plans scrutinization | 0 | N/a | 32 | 32 | 21EHPs capacitated in building plans scrutinizatio by 30 June 2017 | 35 EHPs capacitated | Y | 0 | 0 | None | None | Training Schedule | Y | Not Applicable
11.4.4.3 | 100% Building plans received and scrutinized by 30 June 2017 | Surveillance of premises | A1 | Improve organization, capacity, knowledge and transformation | % of building plans scrutinized | 0 | N/a | 100% | 100% | 100% of building plans scrutinized by 30 June 2017 | 100% (88) building plans that were received were scrutinised, and comments communicated through the Building Unit of 4 LMs | YES | 0 | 0 | None | None | Building Plans Register | Y | Not Applicable
11.4.4.4 | Sampling equipment for 5 offices procured by 30 June 2017 | Procurement of sampling equipment | A2 | Optimize systems, administration and operating procedures | Number of Offices provided with sampling equipment and associated re-agents | R400,000.00 | 1600044052 | 5 | 0 | 5 Offices provided with sampling equipment and associated re-agents by 30 June 2017 | No sampling equipment was procured | NO | R400,000.00 | 0 | The unsound financial status of the municipality forced this program to be postponed | Awaiting financial stability of the municipality | Memo and Specification | Y | The project will be completed in 2016/2017 financial year
11.4.4.5 | All satellite offices with office furniture and equipment by 30 June 2017 | Procurement of office furniture and equipment | A2 | Optimize systems, administration and operating procedures | % of required office furniture & equipment procured | 0 | N/a | 100% | 100% | 100% required office furniture & equipment procured by 30 June 2017 | Facilitate the procurement of laptops from ICT | Y | 0 | 0 | None | None | Memo to ICT | Y | Not Applicable
11.4.4.6 | Availability of protective equipment and clothing by 30 June 2017 | Procurement of protective equipment and clothing | A2 | Optimize systems, administration and operating procedures | % of protective equipment and clothing procured 1 | 0 | 1600044065 | 100% | 100% | 100% of protective equipment and clothing procured 30 June 2017 | No procurement was conducted | N | 0 | 0 | None | None | None | N | Not Applicable
11.4.4.7 | 960 water samples taken and analyzed by 30 June 2017 | Water and food samples analysis. | F2 | Improve community and environmental health and safety | Number of Samples taken and analyzed form Health facilities | 548340 | 1600044052 | 744 | 752 | 958 Samples taken and analyzed form Health facilities by 30 June 2017 | 962 water samples taken, analysed and results communicated back to the facilities | Y | 548340 | 196270.96 | None | None | Sample results | Y | Not Applicable
11.4.4.8 | 890 Food samples taken 30 June 2017. | Water and food samples analysis. | F2 | Improve community and environmental health and safety | Number of food samples taken and analyzed |  |  | 1020 | 934 | 890 Number of food samples taken and analyzed 30 June 2017 | 944 food samples (inclusive of environmental swabs) were taken, analysed and communicated | Y |  |  | None | None | Sample results | Y | Not Applicable
11.4.4.9 | 60 food and water safety Awareness conducted in food handlers by 30 June 2017. | Awareness campaigns on quality of water and food safety. | F2 | Improve community and environmental health and safety | Number of food safety awareness campaigns conducted | 50000 | 1600044065 | 66 | 72 | 64 food safety awareness campaigns conducted by 30 June 2017 | 117 food safety awarenesses conducted | Y | 50000 | 45,000.00 | From the raids that were conducted and the results were unsound foodstuffs sold in our stores, it was deemed fit to strngthen awareness on food safety issues (so that communities know what they're purchasing) | To keep up with the challenges, and be ahead of them | Reports | Y
11.4.4.10 | 40 chemical safety awareness conducted by 30 June 2017 | Awareness campaigns on quality of water and food safety. | F2 | Improve community and environmental health and safety | Number of chemical safety awareness programmes conducted |  |  | 40 | 118 | 44 chemical safety awareness programmes conducted by 30 June 2017 | 72 chemical safety awarenesses conducted | Y |  |  | Arising from the deaths from ingestion of Organo-phosphate pill, it was imperative that we respond to each and every notification received with a follow-up awareness | Prevention is far better thatn cure | Reports Attendance registers | Y | Not Applicable
11.4.4.11 | 120 awarenesses on communicable diseases | Strengthening of Municipal Health Services | F2 | Improve community and environmental health and safety | Number of awarenesses conducted on prevention and control of communicable diseases |  |  | 128 | 166 | 120 awareness conductedby 30 June 2017 | 132 awarenesses on communicable diseases conducted | Y |  |  | It has been something unexpected to receive notifications on hepatitis and rabies, hence the intensification of these kinds of information sharing sessions | Information is the best tool we can offer our communitiesfr | Reports, Attendance registers | Y | Not Applicable
11.4.4.12 | 120 awarenesses on communicable diseases by 30 June 2017 | Strengthening of Municipal Health Services | F2 | Improve community and environmental health and safety | Number of cemeteries evaluated |  |  | None | None | 28 Cementries evaluated by 30 June 2017 | 28 cemeteries inspected | Y | 0 | 0 | None | None | Reports | Y | Not Applicable
11.4.4.13 | Indoor & Ambient air quality awareness | Strengthening of Municipal Health Services | F2 | Improve community and environmental health and safety | Number of air quality awarenesses conducted |  |  | 40 | 30 | 40 awarenesses conducted by June 2017 | 59 awarenesses conducted on air quality (indoor & ambient) | Y | 0 |  | The international theme for this year is Indoor and Outdor Air Quality, which gives us more reason to focus on preventing the occurrence of respiratory diseases for our communities as much as we possibly can | Research has shown that our area is more susceptible to conditions that are curable if we embark on monitoring and prevention | Reports, Photos | Y | Not Applicable
11.4.4.14 | 900 food handling and preparing premises to be evaluated | Awareness campaigns on quality of water and food safety. | F2 | Improve community and environmental health and safety | Number of Health surveillance of food handling and preparing premises conducted | 0 | N/a | 960 | 960 | 900 health surveillance of food handling conducted by 30 June 2017 | 967 food premises evaluated | Y | 0 | 0 | None | None | Reports | Y | Not Applicable
11.4.4.15 | 100% Monitoring of caterers for events | Strengthening of Municipal Health Services | F2 | Improve community and environmental health and safety | % of caterers monitored for events | 0 | N/a | 100% | 100% | 100% of caterers monitored for events by 30 June 2017 | 100% (143) caterers monitored before & during the events | Y | 0 | 0 | None | None | Reports | Y | Not Applicable
11.4.4.16 | 360 health care waste generators evaluated | Evaluations of businesses (rural & urban) (MHS) | F2 | Improve community and environmental health and safety | Number of health care waste generators evaluated. | 70000 | N/a | 372 | 372 | 360 of health care waste generators evaluated by 30 June 2017 | 374 HCRW generators evaluated (inclusive of health facilities, private mortuaries, forensic pathology labs, private doctors) | Y | 70000 | 0 | None | None | Reports | Y | Not Applicable
11.4.4.17 | 100% reported notifiable medical conditions are investigated | Strengthening of Municipal Health Services | F2 | Improve community and environmental health and safety | % of notifiable medical conditions reported and investigated | 0 | N/a | 100% | 100% | 100% of notifiable medical conditions reported and investigated by 30 June 2017 | 100% (92) NMC incusive of rabies, dog bites, scabies, food poisoning, chicken pox & hepatitis B, were investigated | Y |  |  | None | None | Investigation reports | Y | Not Applicable
11.4.4.18 | 540 food and non-food businesses (F. Parlour, Hardware etc. and Govt institutions inspected | Evaluations of businesses (rural & urban) (MHS) | F2 | Improve community and environmental health and safety | Number of food and non-food businesses and Govt. institutions inspected | 0 | 1600044065 | 558 | 570 | 540food and non-food businesses and Govt. institutions inspected by 30 June 2017 | 585 non-food premises inspected | Y |  |  | None | None | Inspection reports, CoAs, Health Certificates | Y | Not Applicable
11.4.4.19 | Attend and honour the National WEHD | World Envorinmental Health Day | F2 | Improve community and environmental health and safety | Number of the World Environmental Health Day Commemorated | 350000 | 160004465 | 1 | 1 | 1 World Environmental Health Day Commemorated | Prepared, adjudicated & submitted 1 ANEHEA Project on hazardous substances prevention Commemorated District WEHD event at Nophoyi, Mt Frere Attended National WEHD in Mpumalanga Province (Ehlanzeni DM) Attended Alfred Nzo Environmental Health Excellence Awards and came 1st runner up in Community Project The HPCSA EHP Stakeholder Engagement was held in Port Alfred, This was conducted for the EHPs in the Eastern Cape. Out of the efforts of the employers (Metropolitan and District Municipalities, ECDoH, DRDAR) the attendance was supposed1 project on IAQM prepared for the ANEH Excellence Awards responding to the theme for 2017 WEHD |  | 350000 | 304,903.00 | None | None | Abstracts, reports, project presentations | Y | Not Applicable
| Enter MHS Projects into Alfred Nzo Awards competitions for National WEHD | [17 empty] | Not Applicable

## 11.4.5 SPORTS
COMMUNITY DEVELOPMENT SERVICES
11.4.5. Sport, Art, Culture, Heritage & Libraries
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.4.5.1 | Alfred Nzo legacy programme conducted | Development of Heritage and Museum programmes | E1 | Promote Public participation and Good Meaningful Governance | Number of legacy programmes conducted | 100000 | 160044287 | 1 | 1 | To conduct one legacy programme by 30 June 2017 | None | N | 100000 | R 0.00 | The programme was put in abayance | The programme to be considered in the next financial year | Project report | N | Not Applicable
| Sport development conducted | Development of sport programme |  | Promote public participation and good meaningful governance | Number of sport development programme conduced | 900000 | 1600044289 | 3 | 2 | To conducte sport development programme | 2 | Y | 900000 | 800962.86 | None | None | Project report and visual aid | Y | 2015-2016 under performance will be addressed in 2016-2017 financial year.
| Support Traditional leaders initiatives | Development of arts and culture programme |  | Promote public participation and good meaningful governance | Number of arts and culture programmes conducted | 800000 | 1600044402 | 4 | 4 | to support Traditional leaders initiatives | 4 | Y | 800000 | 771500 | None | None | Project report and visual aid | Y | Not Applicable
| Conduct cultural festival | Development and of arts and culture programme |  | Promote public participation and good meanigful governance | Number of cultural festival conducted |  |  | 1 | 1 | To conduct cultural festival | 1 | Y |  |  | Budget was put to support O.R. Tambo legacy programme | Programme to be conducted in the next financial year | Project report | N | Not Applicable
| Conduct O.R. Tambo legacy programm | Development of heritage programme |  | Promote public participation and good meaningful governance | Number of O.R. Tambo legacy programmes conducted | 400000 | 160044287 | 1 | 1 | To conduct O.R. Tambo legacy programm | 1 | Y | 400000 | 982595.66 | Budget for Alfred Nzo development programme and cultural festiva was put to O.R. Tambo centenary | Unattended programmes to be conducted in the next financial year | Project report | Y | Not Applicable
11.4.5.2 | Awareness campaigns on initiation conducted by 30 June 2017 | Arts and Culture Development programme | E1 | Promote Public participation and Good Meaningful Governance | Number of awareness campaign conducted | 200000 | 160044402 | 4 | 4 | 1awareness campaign conductedby 30 June 2017 | 4 | Y | 200000 | R 0.00 | Budget was put to the unveiling of the O.R. Tambo statue | Budget allocation for initiation programme will be utilised in the next financial year | Project report and attendance registers | Y | Not Applicable

## 11.4.6. CDS-THUSONG SERVICES
COMMUNITY DEVELOPMENT SERVICES
11.4.6 THUSONG SERVICES
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/2017 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.4.6.1 | Establishment of an effective and efficient Centre management structures by 30 June 2017. | Institutional Development of Thosong Centers | A1 | Improve organization, capacity, knowledge and Transformation | Number of Centre management Committees established | 0 | N/a | 2 | 2 | 1Centre management Committees established by 30 June 2017 | No CMC established | N | 0 | 0 | Project cancelled this financial year due to financial challenges facing the Municipality | Project was deferred to the next fianncial year which is 17/18 | None | N | Not Applicable
11.4.6.2 | Training on key roles and responsibilities of the Center Management Committee by 30 June 2017. |  | A1 | Improve organization, capacity, knowledge and Transformation | Number of Center Management Committee trainings conducted | 0 | N/a | 1 | 1 | 1 Center Management Committee trainings conducted by 30 June 2017 | No CMC trainings conducted | N | 0 | 0 | Project cancelled this financial year due to financial challenges facing the Municipality | Project was deferred to the next fianncial year which is 17/18 | None | N | Not Applicable
11.4.6.3 | Establishment of an effective and efficient Centre management structures by 30 June 2017. | Institutional Development of Thosong Centers | A1 | Improve organization, capacity, knowledge and Transformation | Number of CMC meetings attended | 0 | N/a | 2 | 2 | 4 CMC meetings attended by 30 June 2017 | 4 CMC's attended | Y | 0 | 0 | None | None | Report | Y | Not Applicable
11.4.6.4 | Monitoring of developmental programmes within Thusong Service Centers by 30 June 2017 | Thusong Service Centers | A2 | Optimize systems, administration and operating procedures | Number of War room meetings attended | 0 | N/a | None | None | 4 War room meetings attended by 30 June 2017 | 6 War rooms attended | Y | 0 | 0 | More wards within Thosongs launched War Rooms | None | Report | N | Not Applicable
11.4.6.5 | Thusong Center construction (Nkantolo) monitored by 30 June 2017 | Monitoring of construction of Nkantolo Thusong Service Centers | A2 | Optimize systems, administration and operating procedures | Number of Monthly site meetings attended | External Funding | N/a | 12 | 12 | 4Monthly site meetings attended by 30 June 2017 | 0 Site meetings attended | N | External Funding | 0 | Project halted in February 2016 due to a number of challenges ranging from community infightings and underperformance by the contractor | A new contractor was appointed in June 2017 and construction commenced in July 2017 | Report | Y | Not Applicable
11.4.6.6 | Services on wheels coordinated by 30 June 2017. | Strengthen of Community access to governmental and non-governmental services | E1 | Promote Public participation and Good Meaningful Governance | Number Services on wheels brought to people who have no access | 0 | 1600044103 | 4 | 10 | 4 Services on wheels brought to people who have no access byJune 2017 | 3 Services on wheels conducted | Y | 0 | 70000 | After Mid Term the Budget was adjusted to R…. Leading to less services held | More Services on wheels to be conducted in the next financial year | Report, Visual aids | Y
11.4.6.7 | Information sharing sessions coordianted by 30 June 2017 | Strengthen of Community access to governmental and non-governmental services | E1 | Promote Public participation and Good Meaningful Governance | Number of information sharing sessions brought to people who have no access | 0 | 1600044103 | 4 | 10 | 4 information sharing sessions brought to people who have no access by 30 June 2017 | 4 Information sharing sessions conducted | Y | 0 | 0 | None | None | Report, Visual aids | Y | Not Applicable
11.4.6.8 | A service delivery community guide for Nophoyi Thusong dveloped by 30 June 2017 | Conducting of a Community service delivery profile for Nophoyi in order to plan and respond to their needs | A2 | Optimise systems, administration and operating procedures | Number of Profiles conducted and developed | 0 | N/a | None | None | 1Profiles conducted and developedby30 June 2017 | No profiles conducted | N | 0 | 0 | Project cancelled this financial year due to financial challenges facing the Municipality | Project cancelled indefinately | None | N | Not Applicable
11.4.6.9 | Consultative engagement with conducted by 30 June 2017 | Improvement of government access to information and services by governmental and non-governmental by communities | F5 | Strengthen Intergovernmental Relations | Number of Signed letters of commitment | 0 | N/a | 4 | 0 | 2 Signed letters of commitment by 30 June 2017 | No signed letters of commitements | N | 0 | 0 | No commitement from various government departments to offer permanent services to Thusong Centers within Alfred Nzo District Municipality | Political leadership intervention sought | Letters of commitments | N | No commitement from various government departments to offer permanent services to Thusong Centers within Alfred Nzo District Municipality
11.4.6.10 | Purchase and installation of burglar guards in Nophoyi by 30 June 2017 | Upgrade of Nophoyi Thusong center | B2 | Improve the quality of Municipal Infrastructure Services | Installation of burglar guards in Nophoyi | R20 000 | 5060911 | 1 | 0 | 1 burglar guards in Nophoyi by 30 June 2017 | No burglar guards purchased | N | R20 000 | 0 | Mobile office to be fitted with burglar guards was destroyed in a disaster incident in April 2017 | Awaiting a new mobile office to be replaced by ANDM insurance. | Order | N | Project defferred to next financial year due to financial constratints
11.4.6.11 | Purchase and installation of burglar guards in Thabachicha by 30 June 2017 | Upgrade of Thabachicha Thusong Center | B2 | Improve the quality of Municipal infrastructure services | Installation of burglar guards in Thabachicha | R20 000 | 5060911 | None | None | 1Installation of burglar guards in Thabachicha by 30 June 2017 | Burglars were fitted in Thabachicha | Y | R20 000 | 65000 | None | None | Order | Y | Not Applicable
11.4.6.12 | Purchase / construction of guard room in Nophoyi by 30 June 2017 | Upgrade of Nophoyi Thusong Center | B2 | Improve the quality of Municipal Infrastructure Services | Construction / purchase of guard room | 0 | N/a | 1 | 0 | 1Construction / purchase of guard roomby 30 June 2017 | No guard room purchased | N | 0 | 0 | Project cancelled this financial year due to financial challenges facing the Municipality | Project cancelled indefinately | None | N | Project was deffered to next financila year due to financial constraints
11.4.6.13 | Handing over of Thabachicha Thusong Center by 30 June 2017 | Strengthen of Community access to governmental and non-governmental services | E1 | Promote Public participation and Good Meaningful Governance | Handing over of Thabachicha Thusong Center | 0 | 5060911 | None | None | 1Handing over of Thabachicha Thusong Center by 30 June 2017 | 1 Handing Over conducted in 14 July 2016 | Y | 0 | 0 | Project cancelled this financial year due to financial challenges facing the Municipality | Project cancelled indefinately | None | N | Not Applicable
11.4.6.14 | Handing over of Nophoyi ICT Center by 30 June 2017 | Strengthen of Community access to governmental and non-governmental services | E1 | Promote Public participation and Good Meaningful Governance |  | R210 000 | 5060911 | None | None | 1Handing over of Nophoyi ICT Center by 30 June 2017 | No ICT center handed over | N | 210000 | 0 | ICT center was destroyed by strong winds destroying all computers and therefore no handing over to be conducted | Project cancelled indefinately | None | N | Not Applicable

## CDS PERFORMANCE
COMMUNITY DEVELOPMENT SERVICES
ACHIEVED TARGETS VS NOT ACHIEVED BY UNIT
Unit | Total No. of targets | No. Achieved | No. Not Achieved | % Achieved | % Not Achieved
Customer Care | 8 | 5 | 3 | 63% | 43%
Disaster Risk Management | 8 | 5 | 3 | 63% | 37%
Fire nd Rescue | 5 | 3 | 2 | 60% | 40%
Municipal Health Services | 19 | 16 | 3 | 84% | 16%
SPORTS, ARTS, CULTURE, RECREATION, HERITAGE AND MUSEUMS | 6 | 5 | 1 | 83% | 17%
Thusong Services | 14 | 5 | 9 | 36% | 64%
Department | 60 | 39 | 21 | 65% | 35%

## 11.5.1 PED LED
PLANNING & ECONOMIC DEVELOPMENT
LED
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual target 2015/2016 | Annual actaul 2015/2016 | Annual Target 2016/2017 | Annual actual 2016/2017 | Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.5.1.1 | 4 quarterly LED fora meetings held: 4 DST, LED Forum Tourism Forum Meetings | Institutional Arrangements and Partnerships | C1 | Strengthen internal & external LED capacity | Number of LED meetings coordinated | R0.00 | N/A | 8 | 12 | 12 LED meetings coordinated by 30 June 2017 | 12 LED meeting coordinated | Y | 0 | 0 | None | None | Meeting Invitations, Agendas, Meeting Minutes and Attendance Register | Y | Not Applicable
11.5.1.2 | Number of businesses informed about funding opportunities | District Resource Mobilisation Project | C1 | Strengthen internal & external LED capacity | Numbers of road shows held | R0.00 | N/A | 4 | 4 | 4 road shows held by 30 June 2017 | 5 roadshows held by 30 June 2017 | Y | 0 | 0 | None | None | Attendance Registers. | Y | Not Applicable
11.5.1.3 | Creating institutional partnerships with potential funders | District Resource Mobilisation Project | C1 | Strengthen internal & external LED capacity | Numbers of SMME Engagement Sessions held | R0.00 | N/A | 1 | 1 | 2 SMME Engagement Sessions held by 30 June 2017 | 1 SMME engagement session held on the 20th of October 2016. | Y | R0.00 | 0 | Post Business breakfast was not held due to municipal financial constraints. | To undertake post business breakfast in the next financial year. | Attendance Register, Report. | Y | Not Applicable
11.5.1.4 | Informed business plans developed | District Resource Mobilisation Project | C1 | Strengthen internal & external LED capacity | Numbers of business plan enrichment sessions | R0.00 | N/A | 1 | 1 | 4 business plan enrichment sessions held by 30 June 2017 | 3 business plan enrichment session held by 30 June 2017 | Y | R0.00 | 0 | In Q1, the session was not held due to Lekgotla | None | Attendance Register | Y | Not Applicable
11.5.1.5 | Creating Sustainable Enterprises through meaningful partnerships | District Resource Mobilisation Project | C1 | Strengthen internal & external LED capacity | Number of SMME/Cooperatives Conferences held | R0.00 | N/A | 1 | 1 | 2 SMME/Cooperatives Conferences held by 30 June 2017 | 1 SMME/Cooperative held by 30 June 2017 | Y | R0.00 | 0 | None | None | Attendance Register, Report. | Y | Not Applicable
11.5.1.6 | ANDM Craftwork marketed | District Resource Mobilisation Project | C1 | Promote the earnings potential of ANDM Communities | Number of SMMES supported with access to markets and exhibitions. | 500000 | 13000 44187 | None | None | 20 SMMES supported mobilised for Grahamstown Arts Festival by 30 June 2017 | 6 ANDM SMMEs assisted to attend the Grahamstown Arts Festival by stakeholder partner; Seda. | Y | 500000 | 0 | Due to funding limitations, ANDM could not assist the targeted number of beneficiaries, and will not be in a position to continue with this programme in the next financial year. | This programme will not be budgeted for in the next financial year | Project Report | Y | Not Applicable
11.5.1.7 | SMMEs capacitated | SMME Capacity Building | C1 | Promote the earnings potential of ANDM Communities | Number of capacity building programmes secured | R0.00 | N/A | None | None | 4 capacity building programmes secured by 30 June 2017 | 4 capacity building programmes were secured from the following departments: Agri SETA, ECPTA,ECDC and CATHSETA | Y | R0.00 | 0 | None | None | Funding proposals | Y | Not Applicable
11.5.1.8 | SMMEs capacitated | SMME Capacity Building | C3 | Promote the earnings potential of ANDM Communities | Number of SMMEs and or cooperatives trained and mentored on product development in the tourism sector | 2500000 | 13000 44150 | None | None | 10 SMMEs and or cooperatives trained and mentored on product development in the tourism sector by 30 June 2017 | The implementation of training and mentorship on tourism sector was not successful. | Y | 2500000 | 1798489.34 | Project has been delayed significantly due to finances; Service Provider was not willing to continue with the training without payment for inception. | Project implementation to continue in the 2017/18 Financial Year | Terms of Reference Advert Tender Document Appointment Letter Project Reports | Y | Not Applicable
[5 empty] | Number of SMMEs and or cooperatives mentored in the agricultural sector |  |  | 12 | 12 | 12 SMMEs and or cooperatives mentored in the agricultural sector by 30 June 2017 | 12 SMMEs /Cooperatives were mentored by 30 June 2017 | Y |  |  | The under-expenditure results from the ANDM funds that ran out before implementation was finalised. It was then agreed that a provision would be made through accruals. | Finalise implemtentation in the 2017/18 FY | Terms of Reference Advert Tender Document Appointment Letter Project Reports | Y | Not Applicable
Not Applicable
11.5.1.9 | Workshop/Training for ANDM contractors | ANDM Contractor Development Programme | C3 | Promote the earnings potential of ANDM Communities | Number of Contractors within ANDM that have been developed | R 0.00 | N/A | None | None | 30 Contractors within ANDM that have been developed by 30 June 2017 | Engagememnts have been undertaken with the Department of Roads and Public Works for possible funding for the revitalisation of the Zone Centres | N | R0.00 | 0 | Contractors have not been trained as there was no funding for the programme | In quarter 3 the department opted to develop funding proposal and submitted to DRPW | Funding Proposals | Y | Not Applicable
11.5.1.10 | Collaborative initiatives supported and partnerships created | Collaborative initiatives and partnerships | C3 | Promote the earnings potential of ANDM Communities | Number of LM projects supported | R 600 000.00 | 1300044307 | None | None | 5 LM projects supported by 30 June 2017 | 3 projects were supported. | N | 600000 | 431500 | Due to municpal financial constrains other projects could not be supported | None | None | N/A | Not Applicable
11.5.1.11 | Project Implementation of projects within the B2B corridor development plan | Implementation of tourism Sector Plan Beach to Berg Corridor development plan | C3 | Promote the earnings potential of ANDM Communities | % of implementation of the beach to berg corridor development plan | R 600 000.00 | 13000 44158 | 1 | 1 | 30% implementation of the beach to berg corridor development plan by 30 June 2017 | Development of infrastrucrture work schedule for Matatiele and Umzimvubu Local Municipalities successfully undertaken | Y | R 600 000.00 | 361175 | The under-expenditure results from the Unit's ability to implement the project with less budget. | LED will budget accordingly for the implementation of the remaining 2 Local Municiaplities (Mbizana and Ntabankulu). | Terms of Reference, Project progress reportsand funding proposal | Y | Not Applicable
11.5.1.12 | Completed fencing of identified arable land | District Agri- Parks Programme | C3 | Promote the earnings potential of ANDM Communities | Number of hectares of arable land fenced | R 5 900 000.00 | 13000 | None | None | 30 ha hectares of arable land fenced by 30 June 2017 | The implementation of fencing of arable land was not successful. | Y | R 5 900 000.00 | 3232876.82 | The project could not be completed within the stipulated time due financial constraints | The project will be finalised in the 2017/18 Financial Year | Terms of Reference, Project progress report | Y | This project was was not completed in the previous financial year due to technical challenges on the ground. It was thus planned for completion in the 2016/17 period, however due to cash flow challenges within ANDM, only a portion of the project could be completed. This project has once again been planned for implementation in the 2017/18 Financial Year.
| Completed Mechanization and Harvesting of Maize produce | District Agri- Parks Programme | C3 | Promote the earnings potential of ANDM Communities | Number of hectares ploughed |  |  | None | None | 120 ha hectares ploughed by 30 June 2017 | 125 hectares ploughed and harvested, and markets secured for the Ntabankulu and Umzimvubu Cooperatives. | Y |  |  | In Matatiele Local Municipality the produce was poor due to weather conditions. There was therefore no yield in Matatiele. | The Matatiele area needs to be planted earlier than other Locals in order to avoid the early Winter /frost that affects produce | Project Progress Reports and SLA | Y | In the 2015/16 Financial Year, performamce in this project was poor due to drought conditions that prevailed narionally, where Alfred Nzo District was one of the affected areas.The project was therefore budgeted and planned for implementation in the 2016/17 Financial Year
11.5.1.13 | Number of Vuka Alfred Nzo initiatives supported | Vuka Alfred Nzo Fund |  | Promote the earnings potential of ANDM Communities | Number of Vuka Alfred Nzo initiatives Projects supported to participate in the mainstream Economy | 0 |  | None | None | Number of Vuka Alfred Nzo Enterprises supported to participate in the mainstream Economy | Vuka Alfred Nzo was not implemented | Y | 0 | 13650 | Vuka Alfred Nzo Fund was not implemented due to municipal financial constraints. The expenditure results from advertising | To undertake implementation of the project in 2017/18 financial year | Spreadsheet, advert,TOR, beneficiary list. | Y | Not Applicable

## 11.5.2 PED SPATIAL PLANNING
PLANNING AND ECONOMIC DEVELOPMENT
11.5.2. SPATIAL PLANNING
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/2016 | Annual Actual 2015/2016 | Annual Target 2016/2017 | Annual Actual 2016/2017 | Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.5.2.1 | Adopt 1 Municipal Planning tools in line with the district Suite of Plans. | Spatial Planning (Capacity Support to all LMs) | A2 | Optimize systems, administration and operating procedures | Number of planning tools developed | 0 | N/a | 1 | 1 | 1 Municipal Planning tools developed by 30 June 2017 | This project did not materialise and never kickstarted due to limited buget. It was taken out of the SDBIP during the Mid-term review. | N | R0.00 | R0.00 | The project was taken out of the SDBIP during the Mid-term review due to limited budget (Shortage of funds). | Capacity support to LMs will only be limited and focus on technical support only in future. Financial support will be suspended up until the budget (financial resources) is available at ANDM | None | N | In 2015 / 2016 Financial Year the project was over-achieved, however in 2016 / 2017 Financial Year it was taken out of the SDBIP during the Mid-term review due to the shortage of funding.
11.5.2.2 | Establishment of a Joint Development tribunal for all 4 LM`s within the District. | SPLUMA Implementation | A2 | Optimize systems, administration and operating procedures | Number of SPLUMA Implementation Delegations framework Completed | R0.00 | N/a | 4 | 1 | 1 Joint Municipal Planning Tribunal (MPT) established by 30 June 2017 | Only the signing of the MOU / SLA with member municipality (Ntabankulu LM) to form the Joint MPT with ANDM was done and issuing out of the advertisement calling for nominations of members of the MPT | Not Achieved | R0.00 | R0.00 | Very few responses (only two) were received from the advertisement for calling of nominations for MPT members | The establishment of the MPT will be done in the next Financial Year (2017 - 2018 FY), starting with the re-advertisement for calling of nomination of MPT members | Advert calling for nominations of MPT members, signed SLA with LM's forming part of the MPT and Established MPT | Y | The project has been moving very slowly due to the challenges facing the implementation of SPLUMA. Certain Chapters of the Act have been put on hold, hence the regulations took time to be adopted by stakeholders and role players. The Act was passed by Parliament in 2013, however the legislation initially was not implemented fully and extention was granted for the estasblishment of the MPT
11.5.2.3 | Completed and adopted Land use Management Framework. | Land Use Management Framework (LUMF) | A2 | Optimize systems, administration and operating procedures | Number of Land use Management Framework for the whole district completed and adopted | R 500 000.00 | 1300044237 | 1 | 0 | 1 Land Use Management Framework completed by 30 June 2017 | Situational Analysis, Strategy, Land Use Framework, Development Parameters and Scheme Map (Land Use Coding)were completed | Not Achieved | R 500 000.00 | R0.00 | The Budget was never spent due to shortage of funds | The project will be transferred in the next Financial Year (2017 - 2018 FY). Public Participation and Adoption of completed draft LUMF will be done in 2017 - 2018 FY | Complete Land use Management Framework | Y | The project has been moving very slowly due to challenges facing the inplementation of SPLUMA. The consultant also was faced with challenges due to the turnover of staff. Permission was granted to extend the time period for the completion of the project into the next financial year 2017 - 2018.
11.5.2.4 | 4 district planners forum meeting held | District Planning Forum Establishment | F3 | Strengthen Intergovernmental Relations | Number of meetings held with quorum | R 0.00 | N/a | 4 | 6 | 4 District Planners Forum meetings held by 30 June 2017 | Six (6) Planners Forum meetings were held | Y | R0.00 | R0.00 | The meetings held exceeded the planned target due to high demand (many issues transpired pertaining to information sharing ) | The Terms of Reference for the establishment of the Planners forum to be reviewed and in future the forum will sit monthly (more frequently) | Meeting attendance register and Meeting Minutes | Y | Not Applicable

## 11.5.2.1 PED-GIS
PLANNING AND ECONOMIC DEVELOPMENT
11.5.2.1. GIS
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/2016 | Annual Actual 2015/2016 | Annual Target 2016/2017 | Annual Actual 2016/2017 | Achieved (Y/N) | Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.5.2.1.1 | 1 GIS Awareness programme. | GIS Strategy Development | E1 | Promote Public participation and Good Meaningful Governance | Number of awareness programmes | 200000 | 1300044163 | None | None | 1 GIS awareness programme held by 30 June 2017 | The GIS awareness material (pamphlets) was procured. GIS unit personnel participated in customer care road shows that were held in Ntabankulu and Umzimvubu LMs. | Y | 20000 | R19 950.00 | None | None | None | Y | Not Applicable
11.5.2.1.2 | Data Captured for: | GIS Data Maintenance | F1 | Improve Municipal Planning and spatial development | Number of Wards with rural sanitation data captured | R900 000.00 | 1300044260 | 4 | 4 | 4 GIS data captured by 30 June 2017 | Rural sanitation implementation status quo was assessed. TORs were developed. Service providers were appointed to capture rural sanitation data at Umzimvubu (ward 23& 24) and Mbizana (ward 5 & 6). -Desktop capture of VIPs from Happy Letters was conducted. | Y | R900 000.00 | 553272.81 | Inhouse sanitation data capture could not take place due to municipal budget constraints. | The exercise will be facilitated in the next financial year (2017 / 2018 FY) | , Invoice, Report, Maps, Happy letters | Y | Not Applicable
Rural Sanitation for 8 Wards
11.5.2.1.3 | Environmental Information System | GIS Data Maintenance | F1 | Improve Municipal Planning and spatial development | Number of towns with environmental information captured |  |  |  |  | 2 towns with environmental information captured by 30 June 2017 | Terms of Reference were developed. Service provider was appointed to capture environmental data for Umzimvubu and Mbizana towns. -Project implementation was monitored. -Inception and progress meetings were held. The captured data was verified for accuracy and was incoporated into the municipal database. | Y |  |  | None | None | Invoice, Report | Y | Not Applicable
[8 empty] | 1 | 1
11.5.2.1.4 | Water Infrastructure data for completed schemes. | GIS Data Maintenance | F1 | Improve Municipal Planning and spatial development | Number of Water Supply Schemes Captured |  |  | 4 | 4 | 4 water supply schemes captured by 30 June 2017 | Sourcing of as built plans from the service providers implementing water schemes was done. -Four sections for Cabazana water sheme were captured into the municipal GIS database. The captured data was physically verified for accuracy. | Y |  |  | None | None | As-built Plans,Maps. | Y | Not Applicable

## 11.5.2.2 PED - IDP-PMS
PLANNING AND ECONOMIC DEVELOPMENT
11.5.2.2. IDP AND PMS
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.5.2.2.1 | Well informed and equipped personnel on PMS | Organizational Performance Management Systems (OPMS) | A3 | Increase performance and efficiency levels | Number of Organisational Quarterly Performance reports submitted to council | R0.00 | 1300044243 | 4 | 4 | 4 Quarterly Performance Reports sumitted to Council by 30 June 2017 | 4 Quarterly Performance Reports sumitted to Council by 30 June 2017 | Y | R0.00 | R0.00 | None | None | Quarterly Report, Annual Perfomance Report and Council Resolution | Y | Not Applicable
11.5.2.2.2 | Well informed and equipped personnel on PMS | Organizational Performance Management Systems (OPMS) | A3 | Increase performance and efficiency levels | Number of Consolidated SDBIP documents submitted timeously |  |  | 1 | 1 | 1 SDBIP consolidated by 30 June 2017 | 1 SDBIP consolidated by 30 June 2017 | Y | R0.00 | R 0.00 | None | None | SDBIP document | Y | Not Applicable
Up to date annual performance information
11.5.2.2.3 | IDP developed with stakeholder engagement | IDP Review | F1 | Improve Municipal planning and spatial development | Number of meetings held | R 600 000.00 | 1300044047 | 4 | 4 | 4 IDP meetings held by 30 June 2017 | 3 meetings held by 30 June 2017 | N | 600000 | 249012 | 1 meeting was not held due to poor attendance by relevant stakeholders | None | Meeting minutes, Reports and Attendance Registers and Proof of payment | Y | Not Applicable
11.5.2.2.4 | 1 adopted IDP document by the Council | IDP Review | F1 | Improve Municipal planning and spatial development | Number of IDPs adopted by 31 May 2017 |  |  | 1 | 1 | 1 IDP document adopted by Council by 30 June 2017 | 1 IDP document adopted by Council by 30 June 2017 | Y | R0.00 | R0.00 | None | None | IDP documentand Council Resolutions | Y | Not Applicable
11.5.2.2.5 | 4 LMs consulted on District IDP development | IDP Review | F3 | Strengthen Intergovernmental Relations | Number of LMs consulted on District IDP development |  |  | 4 | 4 | 4 LMs consulted on the District IDP development by 30 June 2017 | 4 LMs consulted on the District IDP development by 30 June 2017 | Y | R0.00 | R0.00 | None | None | IDP documentand Council Resolutions | Y | Not Applicable

## PED PERFORMANCE
PLANNING & ECONOMIC DEVELOPMENT
ACHIEVED TARGETS VS NOT ACHIEVED BY UNIT
Unit | Total No. of targets | No. Achieved | No. Not Achieved | % Achieved | % Not Achieved
Economic Development | 15 | 13 | 2 | 87% | 13%
Spatial Planning | 4 | 1 | 3 | 25% | 75%
GIS | 4 | 4 | 0 | 100% | 0%
IDP and OPMS | 5 | 4 | 1 | 80% | 20%
Department | 28 | 22 | 6 | 79% | 21%

## 11.6.1.1. BTO-GENERAL EXPENDITU
11.6. Budget & Treasury Office
11.6.1 Expenditure Reporting & AFS
11.6.1.1. General Expenditure
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Exepnditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.6.1.1 | Timely and accurate payment of Salaries | Payroll Management | D2 | Improve expenditure management and controls | Number of payroll calendar | 0 | N/A | 24 | 24 | 2 payroll calender by 30 June 2017 | 2 Payroll Calendar were developed up to 30 June 2017 | Y | 0 | 0 | None | None | Approved Payroll calendar | y | Not Applicable
11.6.1.2 | Payroll reconciliations. Timely payment of 3rd parties | Payroll Management | D2 | Improve expenditure management and controls | Number of payroll runs processed. | 0 | N/A | 24 | 24 | 24 payroll runs processed by 30 June 2017 | 24 Payroll runs processed by the 30 June 2017 | Y | 0 | 0 | None | None | Monthly Payroll Runs | y | Not Applicable
11.6.1.3 | Payroll reconciliations. Timely payment of 3rd parties | Payroll Management | D2 | Improve expenditure management and controls | Number of reconciliations performed | 0 | N/A |  |  | 14 reconciliatios performed by 30 June 2017 | 12 Payroll reconciliations done | Y | 0 | 0 | None | None | Payroll Recons | y | Not Applicable
[8 empty] | 14 | 14 |  | 2 Provisional EMP 501 reconciliation done and submitted to SARS | [5 empty] | EMP 501
11.6.1.4 | Payroll reconciliations. Timely payment of 3rd parties | Payroll Management | D2 | Improve expenditure management and controls | % of 3rd party payments made on time | 0 | N/A | 100% 3rd Party payments made | 100% 3rd Party payments made | 100% of 3rd party payments made on time by 30 June 2017 | 3rd party payments are paid before the 7th of the month | N | 0 | 0 | 100% 3rd party payments were made by the 30th June 2017 | There must be an additional signatory as a backup | POP 3rd parties | Y | The municipality must have atleast 3 bank signatories to avoid delays if one resigns or unavailable
11.6.1.5 | Timely and accurate payment of creditors | Creditors Management | D2 | Improve expenditure management and controls | % of Creditors paid within 30 days from receipt of invoice. | 0 | N/a |  |  | 100% of Creditors paid within 30 days from receipt of invoice. | Payments are made on the 15th and 30th of the month. 60 % of payments were made within 30 days of receiving an invoice | Partialy acheived | 0 | 0 | payments were not made within 30 days of receiving an invoice due to non availabilty of funds | None | Creditors age analysis report | Y | This taget is not achieved , % of payments made within 30 days have reduced from80% to 60% due to financial constraints within the municipality. The municipality must reduce on procurement of goods and services in 17/18 financial year and focus more on paying the accruals for 16/17 financial year.
[8 empty] | 100% | 80%
| Timely and accurate payment of creditors | Creditors Management | D2 | Improve expenditure management and controls | Number of Quarterly reports on withdrawal performed by 31 December 2016 | 0 | N/A | 100% | 100% | 4 Quarterly reports on withdrawal performed | 4 quarterly withdrawal reports produced by the 30 June 2017 | y | 0 | 0 | None | None | Quarterly withdrawal Report | y | Not Applicable
11.6.1.6 | Timely and accurate payment of creditors | Creditors Management | D2 | Improve expenditure management and controls | Number of monthly reconciliations performed | 0 | N/a |  |  | 12 monthly reconciliationsperformed by 30 June 2017 | 12 Creditors reconciliation were performed | y | 0 | 0 | MSCOA Challenge on peforming monthly reconcilliations | Munsoft must ensure that the system is operating smootly and quickly attend to our queries | Creditors’ statements to sub-ledger reconciliation | y
[8 empty] | 12 | 12 |  | credit notes were processed where applicable | [5 empty] | Credit notes passed |  | Extensive support and training is required from Munsoft.
11.6.1.7 | Ensure fully implemented Vat controls and recovery. | VAT Recovery | E2 | Strengthen Governance and reduce risk and to maximize VAT collection | Number of VAT returns submitted monthly. | R11 125 569.00 | 140044125 | 12 | 12 | 24 VAT returns submitted monthly | 12 VAT returns submitted to SARS by 30 June 2017 | y | 11125569 | 19841247.29 | None | None | VAT201 | y | Not Applicable
[11 empty] | 12 Vat reconcilliation done | [5 empty] | SARS Statement
Monthly Vat Recon.

## 11.6.1.2. BTO-PROJECT EXPENDITU
11.6.1.2. Project Expenditure
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2016/17 | Actual 2016/17 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Exepnditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.6.1.2.1 | Timely and accurate payment of creditors. | Capital Project Expenditure Management and Reporting | D2 | Improve expenditure management and controls | % of Creditors paid within 30 days from receipt of invoice | 0 | N/a | 10 | 10 | Payments processed within 30 days of receipt of invoice by 30 June 2017 | Partially achieved due to financial constraints | Y | 0 | 0 | Cash Flow constraints | Cost cutting measures to be fully implemented | Creditors Listing Age Analysis |  | 15/16 not yet appointed and performance partially achieved in 16/17 due to cash flow challenges
11.6.1.2.2 |  |  | D2 | Improve expenditure management and controls | No of Fruitless and wasteful expenditure report | 0 | N/a | 10 | 10 | Fruitless and wasteful expenditure report done by the 30 June 2017 | Achieved as no fruitless and wasteful expenditure has been incurred | Y |  | 0 | None | None | Fruitless and wasteful expenditure report |  | N/A
11.6.1.2.3 | Timely and accurate Expenditure reports |  | D2 | Improve expenditure management and controls | % of Expenditure reports performed and submitted. | 0 | N/a | 10 | 10 | 10 Months reconciliations perform and capital project monthly reports submitted by the 4th and 7th of each month. | Achied reports submitted on the 4th and 7th monthly as at the 30 June 2017 | Y | 0 | 0 | None | None | MIG ; WSOG; EPWP; RBIG |  | N/A
11.6.1.2.4 |  |  | D2 | Improve expenditure management and controls | Number of monthly reconciliations performed | 0 | N/a |  |  | Perform Creditors monthly reconciliations. Perform Capital Votes Recon | achieved monthly reconciliations of creditors are done monthly | Y | 0 | 0 | None | None | Creditors statements to sub ledge reconciliation reports |  | N/A
[8 empty] | 10 | 10 | Quarterly report of Credit note processed | Report of Credit note processed monthly
| Capital Project Management Accounting |  |  | Improve expenditure management and controls | 100% project files updated by 30 June 2017 |  |  | 100% | 100% | Project Files updated monthly Monthly reconciliation and updating of annual capital commitment schedule | achieved Project files updated monthly and reconciliation of annual commitment schedule performed by 30 June 2017 | Y |  | 0 | None | None | Project Files; Commitment register; WIP schedule, Retention Register |  | N/A
[10 empty] | Monthly reconciliation of Retention register by 30 June 2017 | achieved Retention schedule reconciliation performed by 30 June 2017
[10 empty] | Annual reconciliation of Work- in-progress (WIP) by 30 June 2017 | achieved annual reconciliations of Work -in -nProgress performed by 30 June 2017

## 11.6.1.3. BTO-BUDGET&REPORTING
11.6.1.3 Budgeting & Reporting
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/ 16 | Actual 2015/16 | Annual Target 2016/ 17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.6.1.3.1 | Reports submitted timeously and presented accurately. | Budget management and Reporting | D4 | Improve budgeting, reporting and compliance. | Number of reports submitted | 0 | N/a |  |  | 41 reports submitted by 30 June 2017 | Achieved, reports have been prepared and submitted to Treasury | Y | 0 | 0 | None | None | Section 71 reports, Section 72 reports, Section 66 reports, Section 52 reports, Management accounts | Y | Not Applicable
[8 empty] | 41 | 41
11.6.1.3.2 | mSCOA consultation | mSCOA Rollout | D4 | Improve budgeting, reporting and compliance. | % of mSCOA Implementation and Chart of Accounts produced | 0 | N/a | 100% | 50% | 100% f mSCOA Implementation and Chart of Accounts produced by 30 June 2017 | Achieved, mSCOA has been implemented and the chart of accounts has been produced | Y | 0 | 0 | None | None | mSCOA chart of accounts | Y | For this target, the municipality took a huge step by opting for early adoption for the implementation of mSCOA, even though Treasury set a deadline for all the municipalities to be compliant by July 2017, as a result ANDM was amongst the top 5 municipalities that implemented mSCOA even though it was not a pilot municipality. There were so many challenges and risks that the municipality has experienced in the implementation of this project but with perseverance of the staff so far those has been overcome. Comparing to the previous year there is a great improvement on this project.
11.6.1.3.3 | mSCOA consultation | mSCOA Rollout | D4 | Improve budgeting, reporting and compliance. | No of training held for Staff | 0 | N/a | None | None | 4 training held for Staff by 30 June 2017 | Partially achieved, 3 trainings have been achieved | Y | 0 | 0 | Due to the mSCOA challenges that we were facing on the system the trainings could not be done | To re-arange the trainings for staff. | None | Y | Not Applicable
11.6.1.3.4 | mSCOA Compliant Financial Management System | mSCOA Rollout | D4 | Improve budgeting, reporting and compliance. | % of Charts of Accounts updated | 0 | N/a | None | None | 100% of Charts of Accounts updated by 30 June 2017 | Achieved, chart of accounts has been updated from version 5.4 to 6.1 | Y | 0 | 0 | None | None | updated mSCOA chart of accounts | Y | Not Applicable
11.6.1.3.5 | Annual Financial Statement to be Prepared and Submitted to Auditor General. | Preparation of Annual Financial Statements and submission to AG. | D4 | Improve budgeting, reporting and compliance. | Number of financial statements submitted. | R 6 000 000.00 | 1400044027 |  |  | 5 financial statements submittedby 30 June 2017 |  | Y | R 6 000 000.00 | 5331774.26 | Due to mSCOA implementation challenges the mid-term AFS could not be produced | To produce the mid term AFS the following financial year. | ANDM Audited AFS, Consolidated AFS including ANDA | Y | Not Applicable
[8 empty] | 1 | 1 |  | Partially achieved, 4 sets of financial statements have been produced
11.6.1.3.6 | Audit queries resolved | Follow up and resolve Audit Queries | E2 | Strengthen governance and reduce risk. | Number of audit queries resolved | 0 | N/a |  |  | 100% of audit queries resolved |  |  | 0 | 0 | The audit steering committee does not sit as a result audit queries from other sections/departments have not been addressed completely. | Audit steering committee to sit regularly in order to discuss the progress on resolving audit queries | AG Audit Report |  | This project has been a challenge since the steering committee hasn't been sitting regularly for the previous years in order to resolve the outstanding queries. This financial year there is an improvement from the previous year as the departments are being followed up to resolve their actions and update their audit action plans in order to improve the audit report.
[8 empty] | 100% | 25% |  | Partially achieved, not all the audit queries have been resolved | [6 empty] | Y
11.6.1.3.7 | Tabled and Implemented IDP/Budget Process for 2016/2017 financial year | Develop an IDP/Budget Process Plan | F1 | Improve Municipal Planning and spatial development | Number of IDP/budget process plans developed and tabled to Council | 0 | N/a | 1 | 1 | 1 of IDP/budget process plans developed and tabled to Council by 30 June 2017 | Achieved, IDP/Budget process plan has been developed and tabled to Council | Y | 0 | 0 | None | None | Council resolutions: IDP budget process plan, | Y | Not Applicable
11.6.1.3.8 | Tabled and Implemented IDP/Budget Process for 2016/2017 financial year | Approved Municipal budget and IDP | F1 | Improve Municipal Planning and spatial development | Number of budget tabled & approved by Council | 0 | N/a |  |  | 4 budgets tabled and approved by Council by 30 June 2017 | Partially Achieved, 3 budgets - mid-term budget, draft annual budget and final annual budget have been tabled and adopted by Council | Y | 0 | 0 | The budget in respect of rollovers was not performed due to the late approval of rollover application by Treasury | Rollover applications approved by Treasury to be included in the mid-term adjustments budget | Council Resolution, adjustments budget, tabled budget and adopted budget | Y | Not Applicable
[8 empty] | None | None

## 11.6.2.1 BTO Revenue
11.6.2. Revenue and Debt Management
11.6.2.1. Revenue Management
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.6.2.1.1 | Allocation of free basic services to qualifying consumers on a monthly basis. | Indigent Support | B1 | Increase access to Municipal Services | % of approved indigent debtors billed with allocation of free basic water and sanitation | 0 | N/a |  |  | 100% of approved indigent debtors billed with allocation of free basic water and sanitation by 30 June 2017 | Achieved-No Customers qualified to free 6000kl residing in urban areas.Indigent registers were reconciled against Valuation rolls | Y | 0 | 0 | None | None | Indigent Register | Y | The base line of this function depends solely from IDMS, in order for us to be able to complete this task, approved and updated indigent register with reconcilitions did not have a qualified indigent individuals customers qualified for free bases services in the register.
[8 empty] | 100% | 100% |  | Achieved-No Customers qualified to free 6000kl residing in urban areas.Indigent registers were reconciled against Valuation rolls | Y | 0 | 0 | None | None | Indigent Register | Y | The base line of this function depends solely from IDMS, in order for us to be able to complete this task, approved and updated indigent register with reconcilitions did not have a qualified indigent individuals customers qualified for free bases services in the register.
11.6.2.1.2 | Ensure that the municipality is financial viable | Revenue enhancement strategies | D1 | Increase revenue collection | % Revenue collection rate as measured in accordance with the MSA performance Regulations | R700 000.00 | 14000 44091/1400044324/50400 111 | 100% | 100% | 100% evenue collection rate as measured in accordance with the MSA performance Regulations by 30 June 2017 | Achieved-Revenue Management as well as sec71 are done on a monthly basis | Y | R700 000.00 | R2,186,372,00 | None | None | Monthly revenue Management Reports including Sec71 Reports | Y | ANDM revenue unit has implemented the revenue enhancement strategy, which cover the water meter installations and prepaid water meters, there is therefore an improvement in revenue collection but still need improvement further, by develop and priotise a clear Asset Management plan as well Asset replacement plan
11.6.2.1.3 | Accurate and timeous monthly billing before the 7th of every Month. | Consumer management and billing | D1 | Increase revenue collection | Number of accounts billed and meters read | 0 | 47001/30-14000/10 | 40536 | 40536 | 12 months | Achieved-Meter are read from 15-25 of every month | Y | 0 | 0 | None | None | Meter Reading Report ,RegisterFaulty Meters | Y | Not Applicable
11.6.2.1.4 | Accurate and timeous monthly billing before the 7th of every Month. | Consumer management and billing | D1 | Increase revenue collection | Number of exception Reports printed | 0 | 47001/30-14000/10 | None | None | None | Achieved-Meters are downloaded from meterman to Billing after the book is completed | Y | 0 | 0 | None | None | Exception report | Y | Not Applicable
11.6.2.1.5 | Accurate and timeous monthly billing before the 7th of every Month. | Consumer management and billing | D1 | Increase revenue collection | % of Reported meter leaks reported to IDMS | 0 | 47001/30-14000/10 | None | None | None | Achieved-Fualty meters are sent to IDMS on a monthly basis. | Y | 0 | 0 | None | None | Faulty Meters | Y | Not Applicable
11.6.2.1.6 | Accurate and timeous monthly billing before the 7th of every Month. | Consumer management and billing | D1 | Increase revenue collection | Number of Billings Performed and sent to customers by the 7th of each Month | R13,000 000.00 | 1440017010 |  |  | 12 Billings Performed and sent to customers by the 7th of each Month by 30 June 2017 | Achieved-Billing are performed on a monthly basis and closed beforethe 10th of every month. | Y | R13,000 000.00 | R10,598,705,23 | None | None | Billing Report, Age Analysis,Consumer statements | Y
[8 empty] | None | None | [9 empty] | Credit and Debt collection policy are implemented on a daily basis through telephone reminders,visiting Customers and application of 50:50 incentiveand there is a great improvement as compared to to 2015/16 financial year.The actual collection for Credit meters 2015/16 was R3,9m and the 2016/17 is R10m
11.6.2.1.7 | Improved collection ratio and reduction of debtors book by 15% | Consumer Management | D1 | Increase revenue collection | Number of non-paying consumers referred to IDMS for restriction and disconnections | 0 | N/a | None | None | 24 non-paying consumers referred to IDMS for restriction and disconnections by 30 June 2017 | Achieved-No system available for restriction | Y | 0 | 0 | Absence of dipping system for restriction | Installation of prepaid sales to non paying residential customers | Non-paying Consumers report/Restrictions report | Y | Not Applicable
11.6.2.1.8 | Improved collection ratio and reduction of debtors book by 15% | Consumer Management | D1 | Increase revenue collection | Number of Debtors and votes recons performed | 0 | N/a | None | None | 12 Debtors and votes recons performed by 30 June 2017 | Achieved-Monthly Debtors reconciliation are performed | Y | 0 | 0 | None | None | Debtors reconciliations,Revenue reconciliations,Billing vs Valuation rolls | Y | Not Applicable
11.6.2.1.9 | Improved collection ratio and reduction of debtors book by 15% | Consumer Management | D1 | Increase revenue collection | Number of Monthly revenue collection reports submitted | 0 | N/a | None | None | 12 Monthly revenue collection reports submitted by 30 June 2017 | Achieved- Monthly revenue reports are done on a monthly basis | Y | 0 | 0 | None | None | Monthly revenue Management Reports including Sec71 Reports,Collection levels | Y | Not Applicable
11.6.2.1.10 | Improved collection ratio and reduction of debtors book by 15% | Consumer Management | D1 | Increase revenue collection | % Implementation of credit control and debt management policy | 0 | N/a | None | None | 100% Implementation of credit control and debt management policy by 30 June 2017 | Achieved-Revenue collection was increased on a monthly basis | Y | 0 | 0 | None | None | Mohly reports including Collection levels | Y | Not Applicable
11.6.2.1.11 | Updated Customer data | Consumer data cleansing | D1 | Increase revenue collection | % of Customer information updated. | 1000000 | 1400044091 | 100% | 100% | 100% Customer information updated by 30 June 2017 | Achieved-Reconciliation between valuation rolls and billing reports | Y | 1000000 | 0 | Service Provider was not appointed due financial constraints.Reconciliations were done in house. | Daa cleansing is needed since there is difficult to perform debt management due to lack of contact details. | Reconciliation between Valuation rolls and Billing system | Y | Not Applicable
11.6.2.1.12 | Identify discrepancies between bank and Cashbook on time | Cash management and Investment | D1 | Increase revenue collection | % of daily banking processed | 0 | N/a | 100% | 100% | 100% of daily banking processed by 30 June 2017 | Achieved-Cash are dropped on a daily basis and reconciled on a monthly basis | Y | 0 | 0 | None | None | Daily cash reconciliations,Bank statement,cash reconciliations | Y | Not Applicable
11.6.2.1.13 | Revenue received from grants, investments made and subsidies | Cash management and Investment | D1 | Increase revenue collection | % of grants received, updated and reconciled | 0 | N/a | 100% | 100% | 12 | Achieved-Grants are reconciled on a monthly basis and acknowledgement letter are done on monthly basis | Y | 0 | 0 | None | None | Grants register | Y | Not Applicable
11.6.2.1.14 | Revenue received from grants, investments made and subsidies | Cash management and Investment | D1 | Increase revenue collection | No of grants register updated and reconciled to DORA | 0 | N/a | None | None | 12 | Achieved Grants are reconciled to DORA and GL on a monthly basis | Y | 0 | 0 | None | None | Grants register | Y | Not Applicable
11.6.2.1.15 | Ensure that the municipality if financial viable | Cash management and Investment | D1 | Increase revenue collection | No. of bank reconciliations performed | 0 | N/a | 12 | 12 | 12 | Achieved-Bank reconciliation are performed on a monthly basis | Y | 0 | 0 | None | None | Bank reconciliation,Cash book,Bank register | Y | Not Applicable
11.6.2.1.16 | Updated Investment Register | Cash management and Investment | D1 | Increase revenue collection | No. investment register updated and reconciled | 0 | N/a | 12 | 12 | 12 investment register updated and reconciled by 30 June 2017 | Achieved-Investment procuders agrees to GL except opening balance | Y | 0 | 0 | None | None | Investment Register and procedures | Y | Not Applicable
11.6.2.1.17 | Updated interest register | Cash management and Investment | D1 | Increase revenue collection | No. of updated interest register | 0 | N/a | 12 | 12 | 12 updated interest register by 30 June 2017 | Achieved-Interest register is updated on a monthly basis and agrees to the general ledger |  | 0 | 0 | None | None | Investment Register and procedures | Y | Not Applicable

## 11.6.2.2 BTO_SCM
11.6.2.2. Supply Chain Management
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annul Budget | Annual Exepnditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.6.2.2.1 | Updated Contracts Register. | Development of SCM and contract management SOP's | A2 | Optimize systems, administration and operating procedures | Number of Contracts Register | R100 000.00 | 14000 44326 044326 | 4 | 4 | 4 Contracts Register by 30 June 2017 | One Decetralised Contract Register Produced in June 2017. | Y | R100 000.00 | 100000 | Cotract officer been suspended , as result the contract register was not timeously updated. | A temp was employed to assist, also contract register was decentralised, which was easy for SCM , is to consolidate from Departments. | Contract Register as 30 June 2017. | Y | The contract register is available completed and achieved, the quality and Completeness of the report accomplished. And aslo with the assistance of service provider.
11.6.2.2.2 | Updated Contracts Register. | Contract ManagementDevelopment of SCM and contract management SOP's | A2 | Optimize systems, administration and operating procedures | % of SLA’s updated. | 0 | N/a | 100% | 85% | 100% of SLA’s updated 30 June 2017 | 20% Of Contract that Has SLA | N | 0 | 0 | Cotract officer been suspended , as result the contract register was not timeously updated. | Legal Department, has taken function once service provider is appointed, letter of appoint with terms of refernce will sent to Legal Department,. | None | N | Not Applicable
11.6.2.2.4 | BID Committee recommendation for the appointment of Service providers | Co-ordinate and provide support on BID committee -Training and SCM Training | A3 | Increase performance and efficiency levels | % of bids awarded within 90 days | 0 | N/a | 100% | 80% | 100% of bids awarded within 90 days by 30 June 2017 | 99% Bids been awarded with 90 Days by 30 June 2017 |  | 0 | 0 | None | None | None | Y | Not Applicable
11.6.2.2.5 | BID Committee recommendation for the appointment of Service providers | Co-ordinate and provide support on BID committee -Training and SCM Training | A3 | Increase performance and efficiency levels | Number of Bid Trainings to be conducted | R 123 530.00 | 1400044333 | None | None | 2 Bid Trainings were conducted by 30 June 2017 | None | None | R 123 530.00 | 123530 | None | None | None | N | Not Applicable
11.6.2.2.6 | Approved procurement plans. | Annual procurement plan | D3 | Maximize economies of scale and value for money by complying with SCM policies. | Number of procurement plans approved. | 0 | N/a | 1 | 1 | 1 procurement plans approved by 30 June 2017 | I Procurement Plan for the District is produced. |  | 0 | 0 | None | None | None | Y | Not Applicable
11.6.2.2.7 | Approved procurement plans. | Implementation of Supply Chain Management Policy | D3 | Maximize economies of scale and value for money by complying with SCM policies. | No of SCM Deviations from SCM policy | 0 | N/a | 0 | 0 | 12 SCM Deviations from SCM policy by 30 June 2017 | Deviation were reported in Each month if they were incurred, are part of SCM Monthly reports . |  | 0 | 0 | None | None | Attendnace Register | yes | Not Applicable
11.6.2.2.8 | Supplier Database updated | Supplier Database Management | D3 | Maximize economies of scale and value for money by complying with SCM policies. | % of supplier database updated | R0.00 | 14000 | 100% | 100% | 100% supplier database updated by 30 June | Not Achieved since Jully 2017 Service Provider are required to register only to National Central Database(CSD) . We no longer take database application , we import from Central Supplier Datase once register with CSD. |  | R0.00 | 0 |  |  | no | no | Not Applicable
11.6.2.2.9 | Timely and accurate Implementation of Council Approved SCM Policy and Reports | Implementation of Supply Chain Management Policy | D3 | Maximize economies of scale and value for money by complying with SCM policies. | Number of SCM report produced on a monthly and Quarterly report | 0 | N/a | None | None | 12 SCM report produced on a monthly and 4 Quarterly report by 30 June 2017 | 12 Monthly and and 4 Qauterly Reports were procused by 30 June 2017 | None | 0 | none |  |  | yes | yes | Not Applicable
11.6.2.2.10 | Reviewed SOP, BTO delegations and fully fledged contract management unit | BTO SOP`s delegations and contract management | D3 | Maximize economies of scale and value for money by complying with SCM policies. | % SOP`s delegations and contract management developed | R100 000.00 | 1400044326 | 100% | 100% | 100% SOP`s delegations and contract management developed by 30 June 2017 | Completed during 2015 /16 |  | R100 000.00 | 100000 |  |  |  |  | Not Applicable

## 11.6.2.3 BTO - ASSET MANAGEMENT
11.6.2.3. Asset Management
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Exepndituere | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.6.2.3.1 | Updated and GRAP Compliant fixed asset register | Update fixed asset register. | D5 | Optimize use of municipal assets | % of GRAP compliance fixed assets register updated | R 1 550 000.00 | 14000/44345 | 80% | 80% | 12 engineers SP appointed for updating of FAR by 30 June 2017 | Achieved - Engineers appointed | Y | 1550000 | 489000 | Engineers appointed late | None | Apointment letter | Y | Not Applicable
11.6.2.3.2 | Insurance contract | Safeguarding and maintenance of assets | D5 | Optimize use of municipal assets | % of assets exposed to risk safeguarded. | R0.00 | 1400044049 | 100% | 100% | 100% of assets exposed to risk safeguarded by 30 June 2017 | Achieved - Insurance company was appointed and claims submitted | Y | 604691 | 588929.82 | There were less accidents in the year, hence less excess to be paid | None | Insurance claims | Y | Not Applicable
11.6.2.3.3 | Updated Fleet register | Fleet Management | D5 | Optimize use of municipal assets | % of Council vehicles maintained. | R0.00 | 1400038007 | 100% | 100% | 100% of Council vehicles maintained by 30 June 2017 | Partially achieved - vehicles taken for service and repairs | Y | 558000 | 412175.72 | Some of the service providers were paid late due to the cashflow constraints | None | Fleet register |  | Not Applicable
11.6.2.3.4 | Effective and efficient supply of consumables | Inventory Management | D5 | Optimize use of municipal assets | Number of stock managed and reconciled. | 0 | N/a | 100% | 100% | 12 stock managed and reconciled by 30 June 2017 | Achieved - stock managed | Y | 0 | 0 | None | None | Quartely recons | Y | Not Applicable
11.6.2.3.5 | Stores Constructed | Stores Construction | D5 | Optimize use of municipal assets | % of Stores Constructed | R 1 500 000.00 | 50400181 | None | None | 100% of Stores Constructed by 30 June 2017 | 90% ACHIEVED | Y | 1500000 |  | Stores could not be finished due to the cashflow contraints | None | Progress report | y | Not Applicable
11.6.2.3.6 | Long-term liability management | Management of Long-term Liabilities | E2 | Strengthen Governance and reduce risk | % of long-term Liabilities managed | R591 858.00 | 1400036002 | 100% | 100% | 100% of long-term Liabilities managed by 30 June 2017 | Achived all recons performed and liability paid | Y | 591858 | 591858 | None | None | RECONS | Y | Not Applicable

## 11.6.2.4 BTO_FIS
BTO
11.6.2.4. Financial Information Systems
SDBIP Number | Output | IDP Project | IDP Ref | Strategic Objective | KPI | Total Budget | Vote | Annual Target 2015/ 16 | Actual 2015/16 | Annual Target 2016/17 | Actual 2016/17 | Targets Achieved (Y/N) | Annual Budget | Annual Expenditure | Reason for Variance | Corrective Action | POE | POE Submitted (Y/N) | The performance of a municipality during that financial year. A comparison of the perfomances referred to in paragraph (a) with targets set for and perfomances in the previous financial year, and measures taken to improve performance
11.6.2.4.1 | To Ensure that municipal Financial System is SCOA compliant | M SCOA Rollout | A2 | Optimise systems, administration and operating procedures | % Implementation of SCOA and migration to SCOA | R850 000.00 | 14000 | None | None | 100% Implementation of SCOA and migration to SCOA by 30 June 2016 | Achieved based on Version 5.4 however a new version has been released by treasury Version 6.1 from July 2017 | Y | R850 000.00 | R552 618 | None | None | General Ledger and Trial Balance in terms of mSCOA |  | Not Applicable
11.6.2.4.2 | To ensure that financial management system is healthy and effective | Financial Management System support and maintenance | A2 | Optimise systems, administration and operating procedures | Number of Munsoft modules implemented as per request | R0.00 | 14000 44242 | None | None | 100% of Munsoft modules implemented as per request by 30 June 2017 | 80% Modules Implemented | Y | R0.00 |  | Assets Module still being developed by Munsoft based on the changes required by treasury | None - Service provider in process of developing system to comply with requirements. Assets Module to be Implememented next Quarter | Reports from Modules |  | Assets Register sent to Service Provider and follow up made . Seems as if the experiencing challenge with asset register module
11.6.2.4.3 | Reduced number of errors on the financial management | Maintenance of Financial Management System | A2 | Optimise systems, administration and operating procedures | % of parameters and vote structures maintained | R0.00 | N/a | None | None | 100% parameters and vote structures maintained by 30 June 2017 | Achived based on mscoa version 5.4 | Y | R0.00 | 0 | None | None | Vote master Listing |  | Not Applicable
11.6.2.4.4 | Approved Access control forms for users | Maintenance of Financial Management System | A2 | Optimise systems, administration and operating procedures | % of access control forms approved | R0.00 | N/a | None | None | 100% of access control forms approved by 30 June 2017 | All users were created in line with approved access control forms | Y | R0.00 | 0 | None | none | Creation of users report. |  | Not Applicable
11.6.2.4.5 | Roles and responsibilities reviewed and signed by supervisors and approved by ICT Manager | Review and enforcement of Roles and Responsibilities | A2 | Optimise systems, administration and operating procedures | Roles and responsibilities reviewed for all business systems (VIP, Munsoft, Sebata, Action It) | R0.00 | N/a | None | None | 4 Roles and responsibilities reviewed for all business systems (VIP, Munsoft, Sebata, Action It by 30 June 2017 | All 4 Quarter Roles and responsibilities has been reviewed and signed | Y | R0.00 | 0 | None | None | Four quarterly reports on roles and responsibilities review approved by ICT Manager |  | Not Applicable
11.6.2.4.6 | Timeously and accurate presentation of reports | Maintenance of accurate state of business systems | A2 | Optimise systems, administration and operating procedures | Number of Reports sent to management | R0.00 | N/a | None | None | 36 Reports sent to management by 30 June 2017 | All reports were made avalaible | Y | R0.00 | 0 | None | None | Trial Balance , General Ledger |  | Not Applicable
11.6.2.4.7 | Updated and renewed SLA | Annual renewal of Licences | A2 | Optimise systems, administration and operating procedures | % of support fees paid. | R921 217.00 | 1 4000 044242 | None | None | 100% of support fees paid by 30 June 2017 | Not Achieved | Y | R921 217.00 | R532 000 | Financial Constraints Experienced by District Council. | Pay outstanding fees by first quarter | POP - Monthly support fees as per SLA for Munsoft and Sebata |  | Due to financial contraints it was not possible to pay on time
11.6.2.4.8 | Resolve all user error, incident and challenges within no time | Incident Management Monitoring System | A2 | Optimise systems, administration and operating procedures | % of calls or reports logged for financial management system | R0.00 | R0.00 | None | None | 100% of calls or reports logged for financial management system by 30 June 2017 | 100% of calls logged but not resolved within 24 hrs | Y | R0.00 | 0 | Due to early adoption we experienced same problems as pilot sites hence most of the loggs raised had to do with programming issues | With rollover from 5.4 to 6.1 most of challenges would be resolved . Prompt roll-over to 6.1 will assist | Incident Report |  | Not Applicable
11.6.2.4.9 | Ensure that financial system is Balanced, reconciled and Closed timeously | Month-end Procedure | A2 | Optimise systems, administration and operating procedures | Number of Month ends performed | R0.00 | N/a | None | None | 12 Month ends performedby 30 June 2017 | 11 month ends were done on time , June has been a challenge | N | R0.00 | 0 | Early adoption of mSCOA and challenges experienced in moving from vote structure to version 5.4 then having to move to 6.1 | Ensure all year end processes are followed. Ensure all transactions for the yr are captured in 5.4 Ensure that budget is in 6.1 and balanced before roll over can happen | Trial Balance , General Ledger |  | Since mSCOA was new to all users and we experience challenges with moving from pre-scoa to 5.4 to 6.1 it was not possible to close June on time

## BTO PERFORMANCE
BUDGET & TREASURY OFFICE
ACHIEVED TARGETS VS NOT ACHIEVED BY UNIT
Unit | Total No. of targets | No. Achieved | No. Not Achieved | % Achieved | % Not Achieved
General Expenditure | 7 | 5 | 2 | 71% | 29%
Project Expenditure | 5 | 4 | 1 | 80% | 20%
Budget & Reporting | 8 | 4 | 4 | 50% | 50%
Revenue Management | 15 | 15 | 0 | 100% | 0%
Supply Chain Management | 9 | 5 | 4 | 56% | 44%
ASSET MANAGEMENT | 6 | 4 | 2 | 67% | 33%
FIS | 9 | 7 | 2 | 78% | 22%
Department | 59 | 44 | 15 | 75% | 25%