## IDMS
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R200 001 and ABOVE- INCLUDING ALL APPLICABLE TAXES) FOR THE 2016 / 2017 FINANCIAL YEAR
+
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE (1)
Review Electricity Sector Plan | 1000000 | NEW VOTE | 22-08-2019 | 15-09-2016 | 15-10-2016 |  | 30-10-2016 |  | WSA | Advertised and closed but the BAC and BEC have not yet sitted
Sanitation Master Plan | 250000 | NEW VOTE | 22-08-2017 | 15-09-2016 | 14-10-2016 |  | 28-10-2016 |  | WSA | Advertised and closed but the BAC and BEC have not yet sitted
Sanitation Technologies | 1500000 | NEW VOTE | 22-08-2018 | 15-09-2016 | 14-10-2016 |  | 28-10-2016 |  | WSA | Not yet advertised due to unavailabilty of funds
Credible Indigent Register | 1500000 | 150044251 | 31-08-2016 | 08-09-2016 | 25-09-2016 |  | 15-10-2016 |  | WSA | Not advertised because no TOR have been received up to date
Number Indigent application verified |  | 150044251 | 31-08-2016 | 08-09-2016 | 25-09-2016 |  | 15-10-2016 |  | WSA | Not yet advertised
Indigent househol framework | 75000 | 150044251 | 31-08-2016 | 08-09-2016 | 25-09-2016 |  | 15-10-2016 |  | WSA | Not advertised because no TOR have been received up to date
Water services schemes | 62500 | 150044108 | 31-08-2016 | 08-09-2016 | 25-09-2016 |  | 15-10-2016 |  | WSA | Not advertised because no TOR have been received up to date
Water Safety Plan | 1500000 | 150044123 | 31-08-2016 | 08-09-2016 | 25-09-2016 |  | 15-10-2016 |  | WSA | Not advertised because no TOR have been received up to date
Wastewater Risk Abatement Plan |  | 150044123 | 31-08-2016 | 08-09-2016 | 25-09-2016 |  | 15-10-2016 |  | WSA | Not advertised because no TOR have been received up to date
auding of all regional schemes | 250000 | 150044134 | 31-08-2016 | 08-09-2016 | 25-09-2016 |  | 15-10-2016 |  | WSA | Advertised and awarded, closing date 04/10/2016
Water services schemes | 62500 | 150044108 | 31-08-2016 | 08-09-2016 | 25-09-2016 |  | 15-10-2016 |  | WSA | Not advertised because no TOR have been received up to date
Auditing of all regional schemes | 250000 | 150044134 | 31-08-2016 | 08-09-2016 | 25-09-2016 |  | L |  | WSA | Advertised and awarded, closing date 04/10/2016
Construction of VIP in Mbizana Ward 31 | 4500000 | 50500551 | 02-08-2016 | 19-08-2016 | 1-09-2016 |  | 16-09-2016 |  | IDMS - PMU | Advertised and BAC sitted . Awarded to Mvumeza Trading Construction
Greater Mbizana Water Supply-Phase 1A: RETICULATION SYSTEM | 60000000 | 50500357 | 09-09-2016 | 19-09-2016 | 3-10-2016 |  | 17-10-2016 |  | IDMS - PMU | Advertised and BAC sitted. Tender awarded to E.G Pipping
Ntibane Water supply Scheme: Phase 2 | 21500000 | 505003081 | 13-07-2016 | 16-08-2016 | 17-09-2016 |  | 03-10-2016 |  | IDMS - PMU | Advertised and BAC sitted. Tender awarded to IPM Plant Hire
Mount Ayliff Peri-Urban Water Project | 80000000 | 50500 | 29-06-2016 | 25-08-2016 | 16-09-2016 |  | 30-07-2016 |  | IDMS - PMU | Advertised and BAC sitted, tender was awarded as per Recommendation of BEC
1. Tools and Equipment | 1000000 | 505001081 | 15-08-2016 | 30-09-2016 | 30-10-2016 |  | 30-11-2016 |  | IDMS-WSP | Not yet advertised and TOR not yet received
3. Refurbishment and Augmentation of Matatiele WTW | 1000000 | 505090811 | 30-08-2016 | 30-09-2016 | 30-10-2016 |  | 30-11-2016 |  | IDMS-WSP | Not yet advertised and TOR not yet received
17. Refurbishment and Replacement of Water Infrastructure - Umzimvubu | 1500000 | 505090841 | 30-08-2016 | 30-09-2016 | 30-10-2016 |  |  |  | IDMS-WSP | Not yet advertised and TOR not yet received
18. Refurbishment and Replacement of Water Infrastructure - Mnceba (Umzimvubu) | 1000000 | 505090881 | 30-08-2016 | 30-09-2016 | 30-10-2016 |  | 30-11-2016 |  | IDMS-WSP | Not yet advertised and TOR not yet received
Umzimvubu ward 22 water supply | 7500000 | 50504961 | 20-01-2017 | 03-02-2017 | 03-03-2017 |  | 31-03-2017 |  | IDMS - PMU | Not yet advertised and TOR not yet received
QUARTER TWO (2)
Review Water Services Developmnt Plan | 1000000 | 150044110 | 15-10-2016 | 21-10-2016 | 15-11-2016 |  |  |  | WSA | Not advertised due to no Cash Flow/ cash in the Bank
Develop Water Services Master Plan | 500000 |  | 15-10-2016 | 21-10-2016 | 15-11-2016 |  | 30-11-2016 |  | WSA | Not advertised due to no Cash Flow/ cash in the Bank
Developm Storm Water Management Plan | 250000 |  | 15-10-2016 | 21-10-2016 | 15-11-2016 |  | 30-11-2016 |  |  | Not advertised due to no Cash Flow/ cash in the Bank
Review Intergrated Transport Plan | 500000 |  | 15-10-2016 | 21-10-2016 | 15-11-2016 |  | 30-11-2016 |  | WSA | Not advertised due to no Cash Flow/ cash in the Bank
Umzimvubu ward 13 water supply | 10000000 | 50500359 | 03-10-2016 | 21-10-2016 | 25-11-2016 |  | 04-12-2016 |  | IDMS - PMU | Not advertised due to no Cash Flow/ cash in the Bank
Umzimvubu ward 14 water supply | 10000000 | 50500363 | 03-10-2016 | 21-10-2016 | 25-11-2016 |  | 04-12-2016 |  | IDMS - PMU | Not advertised due to no Cash Flow/ cash in the Bank
Cabazana Bulk Water Supply | 18000000 | 50500471 | 03-10-2016 | 21-10-2016 | 25-11-2016 |  | 04-12-2016 |  | IDMS - PMU | Not advertised due to no Cash Flow/ cash in the Bank
Not advertised due to no Cash Flow/ cash in the Bank
1. Tools and Equipment | 1000000 | 505001081 | 03-10-2016 | 21-10-2016 | 30-10-2016 |  | 30-11-2016 |  | IDMS-WSP | Not advertised due to no Cash Flow/ cash in the Bank
3. Refurbishment and Augmentation of Matatiele WTW | 1000000 | 505090811 | 03-10-2016 | 21-10-2016 | 30-10-2016 |  | 30-11-2016 |  | IDMS-WSP | Not advertised due to no Cash Flow/ cash in the Bank
8. Refurbishment and Replacement of Water Infrastructure - Matatiele | 1500000 | 505090851 | 03-10-2016 | 21-10-2016 | 30-10-2016 |  | 30-11-2016 |  | IDMS-WSP | Not advertised due to no Cash Flow/ cash in the Bank
17. Refurbishment and Replacement of Water Infrastructure - Umzimvubu | 1500000 | 505090841 |  | 21-10-2016 | 30-10-2016 |  | 30-11-2016 |  | IDMS-WSP | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER THREE (3)
Approved By:……………………………
Signature:…………………………………
Date:………………………………………

## Speaker's Office
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R30 000-R200 000 INCLUDING ALL APPLICABLE TAXES) FOR THE 2016/2017 FINANCIAL YEAR
DEPARTMENT:- OFFICE OF THE SPEAKER & CHIEF WHIP
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Actual date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Actual date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE
District Speakers Forum | 50000 | 1105044130 | 2016-07-01 | 2016-08-01 | 2016-08-31 |  | 2016-09-09 |  | 2016-09-30 |  | Speakers Office | Not yet advertised and TOR not yet received
Public Participation (Taking Government to People) | 137500 | 1105044082 | 2016-07-01 | 2016-08-01 | 2016-08-31 |  | 2016-09-09 |  | 2016-09-30 |  | Speakers Office | Not yet advertised and TOR not yet received
Municpal Public Accounts | 37500 | 1105044126 | 2016-07-01 | 2016-08-01 | 2016-08-31 |  | 2016-09-09 |  | 2016-09-30 |  | Speakers Office | Not yet advertised and TOR not yet received
Moral Regeneration Movement | 50000 | 1105044129 | 2016-07-01 | 2016-08-01 | 2016-08-31 |  | 2016-09-09 |  | 2016-09-30 |  | Speakers Office | Not yet advertised and TOR not yet received
Whippery Programmes | 25000 | 1106044213 | 2016-07-01 | 2016-08-01 | 2016-08-31 |  | 2016-09-09 |  | 2016-09-30 |  | Speakers Office | Not yet advertised and TOR not yet received
Constituency Work | 125000 | 1106044214 | 2016-07-01 | 2016-08-01 | 2016-08-31 |  | 2016-09-09 |  | 2016-09-30 |  | Speakers Office | Not yet advertised and TOR not yet received
Council Caucus | 12500 | 1106044217 | 2016-07-01 | 2016-08-01 | 2016-08-31 |  | 2016-09-09 |  | 2016-09-30 |  | Speakers Office | Awarded in 3 Quotes
Council Study Groups & Workshop | 212500 | 1106044080 | 2016-07-01 | 2016-08-01 | 2016-08-31 |  | 2016-09-09 |  | 2016-09-30 |  | Speakers Office | Not yet advertised and TOR not yet received
Upgrade of the Council Chamber & Boardrooms | 200000 | 1105044132 | 2016-07-01 | 2016-08-01 | 2016-08-31 |  | 2016-09-09 |  | 2016-09-30 |  | Speakers Office | Advertised, closed and awarded as per Evaluation Report
QUARTER TWO (2)
District Speakers Forum | 50000 | 1105044130 | 2016-10-03 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | Speakers Office | Not yet advertised and TOR not yet received
Public Participation (Taking Government to People) | 137500 | 1105044082 | 2016-10-03 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | Speakers Office | Not yet advertised and TOR not yet received
Municpal Public Accounts | 37500 | 1105044126 | 2016-10-03 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | Speakers Office | Not yet advertised and TOR not yet received
Moral Regeneration Movement | 50000 | 1105044129 | 2016-10-03 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | Speakers Office | Not yet advertised and TOR not yet received
Whippery Programmes | 25000 | 1106044213 | 2016-10-03 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | Speakers Office | Not yet advertised and TOR not yet received
Constituancy Work | 125000 | 1106044214 | 2016-10-03 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | Speakers Office | Not yet advertised and TOR not yet received
Council Caucus | 12500 | 1106044217 | 2016-10-03 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | Speakers Office | Not yet advertised and TOR not yet received
Council Study Groups & Workshop | 212500 | 1106044080 | 2016-10-03 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | Speakers Office | Not yet advertised and TOR not yet received
QUARTER THREE (3)
Open Council Day - State of the District Address | 800000 | 1105044073 | 2017-01-09 |  | 2017-01-16 |  | 2017-02-20 |  | 2017-03-06 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
District Speakers Forum | 50000 | 1105044130 | 2017-01-09 |  | 2017-01-16 |  | 2017-02-20 |  | 2017-03-06 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Public Participation (Taking Government to People) | 137500 | 1105044082 | 2017-01-09 |  | 2017-01-16 |  | 2017-02-20 |  | 2017-03-06 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Municpal Public Accounts | 37500 | 1105044126 | 2017-01-09 |  | 2017-01-16 |  | 2017-02-20 |  | 2017-03-06 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Moral Regeneration Movement | 50000 | 1105044129 | 2017-01-09 |  | 2017-01-16 |  | 2017-02-20 |  | 2017-03-06 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Whippery Programmes | 25000 | 1106044213 | 2017-01-09 |  | 2017-01-16 |  | 2017-02-20 |  | 2017-03-06 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Constituency Work | 125000 | 1106044214 | 2017-01-09 |  | 2017-01-16 |  | 2017-02-20 |  | 2017-03-06 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Council Caucus | 12500 | 1106044217 | 2017-01-09 |  | 2017-01-16 |  | 2017-02-20 |  | 2017-03-06 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Council Study Groups & Workshop | 212500 | 1106044080 | 2017-01-09 |  | 2017-01-16 |  | 2017-02-20 |  | 2017-03-06 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER FOUR (4)
District Speakers Forum | 50000 | 1105044130 | 2017-04-03 |  | 2017-04-10 |  | 2017-04-28 |  | 2017-05-15 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Public Participation (Taking Government to People) | 137500 | 1105044082 | 2017-04-03 |  | 2017-04-10 |  | 2017-04-28 |  | 2017-05-15 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Municpal Public Accounts | 37500 | 1105044126 | 2017-04-03 |  | 2017-04-10 |  | 2017-04-28 |  | 2017-05-15 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Moral Regeneration Movement | 50000 | 1105044129 | 2017-04-03 |  | 2017-04-10 |  | 2017-04-28 |  | 2017-05-15 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Africa Month Programmes | 150000 | 1105044130 | 2017-04-03 |  | 2017-04-10 |  | 2017-04-28 |  | 2017-05-15 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Whippery Programmes | 25000 | 1106044213 | 2017-04-03 |  | 2017-04-10 |  | 2017-04-28 |  | 2017-05-15 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Constituency Work | 125000 | 1106044214 | 2017-04-03 |  | 2017-04-10 |  | 2017-04-28 |  | 2017-05-15 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Council Caucus | 12500 | 1106044217 | 2017-04-03 |  | 2017-04-10 |  | 2017-04-28 |  | 2017-05-15 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Council Study Groups & Workshop | 212500 | 1106044080 | 2017-04-03 |  | 2017-04-10 |  | 2017-04-28 |  | 2017-05-15 |  | Speakers Office | Not advertised due to no Cash Flow/ cash in the Bank
Approved By:……………………………
Signature:…………………………………
Date:………………………………………

## SPU
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R30 000-R200 000 INCLUDING ALL APPLICABLE TAXES) FOR THE 2016/2017 FINANCIAL YEAR
DEPARTMENT:- SPECIAL PROGRAMMES UNIT
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Actual date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Actual date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE (1)
Older Person's Care & Suppot | 100000 | 1115044207 | 2016-07-01 | 2016-08-01 | 2016-08-30 |  | 2016-09-10 |  | 2016-09-30 |  | SPU | Advertised, closed and awarded as per Evaluation Report
District Children's Development Programmes | 100000 | 1115044230 | 2016-07-01 | 2016-08-01 | 2016-08-30 |  | 2016-09-10 |  | 2016-09-30 |  | SPU | Advertised, closed and awarded as per Evaluation Report
District Gender Programmes Coordination Care & Support | 100000 | 1115044042 | 2016-07-01 | 2016-08-01 | 2016-08-30 |  | 2016-09-10 |  | 2016-09-30 |  | SPU | Not yet advertised and TOR not yet received
District Disability Programmes | 100000 | 1115044032 | 2016-07-01 | 2016-08-01 | 2016-08-30 |  | 2016-09-10 |  | 2016-09-30 |  | SPU | Advertised, closed and awarded as per Evaluation Report
Youth Development Programmes | 500000 | 1115044113 | 2016-07-01 | 2016-08-01 | 2016-08-30 |  | 2016-09-10 |  | 2016-09-30 |  | SPU | Not yet advertised and TOR not yet received
HIV and AIDS Awareness Programmes | 50000 | 1115044003 | 2016-07-01 | 2016-08-01 | 2016-08-30 |  | 2016-09-10 |  | 2016-09-30 |  | SPU | Advertised, closed and awarded as per Evaluation Report
HIV and AIDS Coordination Care & Support Programmes | 100000 | 1115044018 | 2016-07-01 | 2016-08-01 | 2016-08-30 |  | 2016-09-10 |  | 2016-09-30 |  | SPU | Advertised, closed and awarded as per Evaluation Report
SPU Mainstreaming | 125000 | 1115044232 | 2016-07-01 | 2016-08-01 | 2016-08-30 |  | 2016-09-10 |  | 2016-09-30 |  | SPU | Not yet advertised and TOR not yet received
QUARTER TWO (2)
Older Person's Care & Suppot | 100000 | 1115044207 | 2016-10-01 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | SPU | Not yet advertised and TOR not yet received
District Children's Development Programmes | 100000 | 1115044230 | 2016-10-01 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | SPU | Advertised, closed and awarded as per Evaluation Report
District Gender Programmes Coordination Care & Support | 100000 | 1115044042 | 2016-10-01 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | SPU | Not yet advertised and TOR not yet received
District Disability Programmes | 100000 | 1115044032 | 2016-10-01 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | SPU | Not yet advertised and TOR not yet received
Youth Development Programmes | 500000 | 1115044113 | 2016-10-01 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | SPU | Advertised, closed and awarded as per Evaluation Report
HIV and AIDS Awareness Programmes | 50000 | 1115044003 | 2016-10-01 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | SPU | Advertised, closed and awarded as per Evaluation Report
HIV and AIDS Coordination Care & Support Programmes | 100000 | 1115044018 | 2016-10-01 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
SPU Mainstreaming | 125000 | 1115044232 | 2016-10-01 |  | 2016-10-25 |  | 2016-11-03 |  | 2016-11-16 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER THREE (3)
Older Person's Care & Suppot | 100000 | 1115044207 | 2017-01-06 |  | 2017-01-12 |  | 2017-02-16 |  | 2017-02-27 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
District Children's Development Programmes | 100000 | 1115044230 | 2017-01-06 |  | 2017-01-12 |  | 2017-02-16 |  | 2017-02-27 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
District Gender Programmes Coordination Care & Support | 100000 | 1115044042 | 2017-01-06 |  | 2017-01-12 |  | 2017-02-16 |  | 2017-02-27 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
District Disability Programmes | 100000 | 1115044032 | 2017-01-06 |  | 2017-01-12 |  | 2017-02-16 |  | 2017-02-27 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
Youth Development Programmes | 500000 | 1115044113 | 2017-01-06 |  | 2017-01-12 |  | 2017-02-16 |  | 2017-02-27 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
HIV and AIDS Awareness Programmes | 50000 | 1115044003 | 2017-01-06 |  | 2017-01-12 |  | 2017-02-16 |  | 2017-02-27 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
HIV and AIDS Coordination Care & Support Programmes | 100000 | 1115044018 | 2017-01-06 |  | 2017-01-12 |  | 2017-02-16 |  | 2017-02-27 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
SPU Mainstreaming | 125000 | 1115044232 | 2017-01-06 |  | 2017-01-12 |  | 2017-02-16 |  | 2017-02-27 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
Mayoral Education Intervention Programme (Community Empowerment Programme) | 250000 | 1115044312 | 2017-01-06 |  | 2017-01-12 |  | 2017-02-16 |  | 2017-02-27 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER FOUR (4)
Older Person's Care & Suppot | 100000 | 1115044207 | 2017-04-01 |  | 2017-04-12 |  | 2017-04-29 |  | 2017-05-09 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
District Children's Development Programmes | 100000 | 1115044230 | 2017-04-01 |  | 2017-04-12 |  | 2017-04-29 |  | 2017-05-09 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
District Gender Programmes Coordination Care & Support | 100000 | 1115044042 | 2017-04-01 |  | 2017-04-12 |  | 2017-04-29 |  | 2017-05-09 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
District Disability Programmes | 100000 | 1115044032 | 2017-04-01 |  | 2017-04-12 |  | 2017-04-29 |  | 2017-05-09 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
Youth Development Programmes | 500000 | 1115044113 | 2017-04-01 |  | 2017-04-12 |  | 2017-04-29 |  | 2017-05-09 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
HIV and AIDS Awareness Programmes | 50000 | 1115044003 | 2017-04-01 |  | 2017-04-12 |  | 2017-04-29 |  | 2017-05-09 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
HIV and AIDS Coordination Care & Support Programmes | 100000 | 1115044018 | 2017-04-01 |  | 2017-04-12 |  | 2017-04-29 |  | 2017-05-09 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
SPU Mainstreaming | 125000 | 1115044232 | 2017-04-01 |  | 2017-04-12 |  | 2017-04-29 |  | 2017-05-09 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
Mayoral Education Intervention Programme (Community Empowerment Programme) | 250000 | 1115044312 | 2017-01-06 |  | 2017-01-12 |  | 2017-02-16 |  | 2017-02-27 |  | SPU | Not advertised due to no Cash Flow/ cash in the Bank
Approved By:……………………………
Signature:…………………………………
Date:………………………………………

## Communications
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R30 000-R200 000 INCLUDING ALL APPLICABLE TAXES) FOR THE 2016/2017 FINANCIAL YEAR
DEPARTMENT:- COMMUNICATIONS
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Envisaged date of award | Responsible office | Status
QUARTER ONE (1)
Hiring of Equipment for Municipal events | 100000 | 111044007 | 2016-08-30 | 2016-09-05 | 2016-09-14 | 2016-09-30 | Communications Unit | Advertised, closed and awarded as per Evaluation Report
Newsletter Production | 125000 | 111044070 | 2016-08-15 | 2016-08-30 | 2016-09-10 | 2016-09-30 | Communications Unit | Advertised, closed and awarded as per Evaluation Report
Newsletters Translation | 25000 | 111044012 | 2016-08-15 | 2016-08-30 | 2016-09-10 | 2016-09-30 | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Diaries, Notepads & Calendars | 500000 | 111044013 | 2016-08-01 | 2016-08-30 | 2016-09-10 | 2016-09-30 | Communications Unit | Advertised, closed and awarded as per Evaluation Report
Branding Material, Website and Intranet | 1000000 | 111044013 | 2016-08-30 | 2016-09-05 | 2016-09-10 | 2016-09-30 | Communications Unit | Not yet advertised and TOR not yet received
Branding of Satellite Offices | 125000 | 111044092 | 2016-08-30 | 2016-09-05 | 2016-09-15 | 2016-09-30 | Communications Unit | Not yet advertised and TOR not yet received
Live Broadcast by National and Local Radios | 112500 | 111044084 | 2016-08-30 | 2016-08-30 | 2016-09-10 | 2016-09-30 | Communications Unit | Advertised, closed and awarded as per Evaluation Report
Bulk buying of space on Provincial and Local newspapers | 112500 | 111044084 | 2016-08-31 | 2016-08-31 | 2016-09-10 | 2016-09-30 | Communications Unit | Not yet advertised and TOR not yet received
Community Outreaches | 100000 | 111044021 | 2016-09-01 | 2016-09-10 | 2016-09-10 | 2016-09-30 | Communications Unit | Advertised, closed and awarded as per Evaluation Report
Heritage and Legacy Programme | 500000 | 111044092 | 2016-09-02 | 2016-09-05 | 2016-09-15 | 2016-09-30 | Communications Unit | Not yet advertised and TOR not yet received
QUARTER TWO (2)
Newsletter Production | 125000 | 111044070 | 2016-09-01 | 2016-09-25 | 2016-10-03 | 2016-10-14 | Communications Unit | Advertised, closed and awarded as per Evaluation Report
Newsletters Translation | 25000 | 111044013 | 2016-09-01 | 2016-09-25 | 2016-10-03 | 2016-10-14 | Communications Unit | Awarded as per 3 Quotes
Branding Material | 62500 | 111044084 | 2016-09-01 | 2016-09-25 | 2016-10-03 | 2016-10-14 | Communications Unit | Advertised, closed and awarded as per Evaluation Report
Branding of Satellite Offices | 125000 | 111044092 | 2016-09-01 | 2016-09-25 | 2016-10-03 | 2016-10-14 | Communications Unit | Not yet advertised and TOR not yet received
Live Broadcast by National and Local Radios | 112500 | 111044084 | 2016-09-01 | 2016-09-25 | 2016-10-03 | 2016-10-14 | Communications Unit | Advertised, closed and awarded as per Evaluation Report
Bulk buying of space on Provincial and Local newspapers | 112500 | 111044084 | 2016-09-01 | 2016-09-25 | 2016-10-03 | 2016-10-14 | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Community Outreaches | 100000 | 111044021 | 2016-09-01 | 2016-09-25 | 2016-10-03 | 2016-10-14 | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER THREE (3)
Newsletter Production | 125000 | 111044012 | 2017-01-08 | 2017-01-11 | 2017-02-18 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Newsletters Translation | 25000 | 111044070 | 2017-01-08 | 2017-01-11 | 2017-02-19 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Branding Material | 62500 | 111044092 | 2017-01-08 | 2017-01-11 | 2017-02-20 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Branding of Satellite Offices | 125000 | 111044084 | 2017-01-08 | 2017-01-11 | 2017-02-21 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Live Broadcast by National and Local Radios | 112500 | 111044013 | 2017-01-08 | 2017-01-11 | 2017-02-22 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Bulk buying of space on Provincial and Local newspapers | 112500 | 111044084 | 2017-01-08 | 2017-01-11 | 2017-02-23 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Community Outreaches | 100000 | 111044021 | 2017-01-08 | 2017-01-11 | 2017-02-24 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER FOUR (4)
Newsletter Production | 125000 | 111044070 | 2017-04-01 | 2017-04-12 | 2017-04-30 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Newsletters Translation | 25000 | 111044070 | 2017-04-01 | 2017-04-12 | 2017-04-30 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Branding Material | 62500 | 111044092 | 2017-04-01 | 2017-04-12 | 2017-04-30 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Branding of Satellite Offices | 125000 | 111044084 | 2017-04-01 | 2017-04-12 | 2017-04-30 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Live Broadcast by National and Local Radios | 112500 | 111044021 | 2017-04-01 | 2017-04-12 | 2017-04-30 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Bulk buying of space on Provincial and Local newspapers | 112500 | 111044021 | 2017-04-01 | 2017-04-12 | 2017-04-30 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Community Outreaches | 100000 | 111044061 | 2017-04-01 | 2017-04-12 | 2017-04-30 |  | Communications Unit | Not advertised due to no Cash Flow/ cash in the Bank
Approved By:………………………………………..
Signature:……………………………………………
Date:…………………………………………………….

## Internal Audit
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R30 000-R200 000 INCLUDING ALL APPLICABLE TAXES) FOR THE 2016/ 2017 FINANCIAL YEAR
DEPARTMENT:- INTERNAL AUDIT
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Actual date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Actual date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE (1)
Internal Audit
AFS & PI reviews | 200000 | 1110044121 | 2016-07-31 |  | 2016-08-02 |  | 2016-08-08 |  | 2016-08-15 |  | INTERNAL AUDIT | Advertised, closed and awarded as per Evaluation Report
Mscoa Reviews | 200000 | 1110044121 | 2016-08-15 |  | 2016-08-19 |  | 2016-08-25 |  | 2016-08-29 |  | INTERNAL AUDIT | Advertised, closed and awarded as per Evaluation Report
Quality Assurance Reviews | 200000 | 1110044121 | 2016-09-02 |  | 2016-09-09 |  | 2016-09-15 |  | 2016-09-23 |  | INTERNAL AUDIT | Advertised, closed and awarded as per Evaluation Report
QUARTER TWO (2)
Project Management Reviews | 200000 | 1110044121 | 2016-10-03 |  | 2016-10-09 |  | 2016-10-17 |  | 2016-10-23 |  | INTERNAL AUDIT | Advertised, closed and awarded as per Evaluation Report
Revise Audit Methdology | 200000 | 1110044121 | 2016-07-03 |  | 2016-07-09 |  | 2016-07-17 |  | 2016-07-23 |  | INTERNAL AUDIT | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER THREE (3)
Co-source ICT Audit | 200000 | 1110044121 | 2017-01-18 |  | 2017-01-22 |  | 2017-01-29 |  | 2017-02-05 |  | INTERNAL AUDIT | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER THREE (4)
Co-source Performance Information (Mandatory Internal Audits) | 800000 | 1110044121 | 2016-03-13 |  | 2017-03-25 |  | 2017-03-25 |  | 2016-04-07 |  | INTERNAL AUDIT | Not advertised due to no Cash Flow/ cash in the Bank
Approved By:………………………………………..
Signature:……………………………………………
Date:…………………………………………………….

## IGR
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R30 000-R200 000 INCLUDING ALL APPLICABLE TAXES) FOR THE 2016/ 2017 FINANCIAL YEAR
DEPARTMENT:- IGR
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Actual date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Actual date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE (1)
IGR & Stakeholder Programmes | 25000 | 111044206 | 2016-07-01 |  | 2016-07-14 |  | 2016-07-30 |  |  |  | IGR Office | Advertised and closed
Municipal Coorperative Agreements (MIR & Protocol) | 100000 | 111044215 | 2016-07-01 |  | 2016-07-14 |  | 2016-07-30 |  |  |  | IGR Office | Advertised, closed and awarded as per Evaluation Report
QUARTER TWO (2)
IGR & Stakeholder Programmes | 25000 | 111044206 | 2016-10-01 |  | 2016-10-14 |  | 2016-10-21 |  |  |  | IGR Office | Awarded as per 3 Quotes
Municipal Coorperative Agreements (MIR & Protocol) | 150000 | 111044215 | 2016-10-01 |  | 2016-10-14 |  | 2016-10-21 |  |  |  | IGR Office | Advertised, closed and awarded as per Evaluation Report
QUARTER THREE (3)
IGR Workshop | 200000 | 110044206 | 2017-01-06 |  | 2017-01-15 |  | 2017-02-28 |  | 2017-03-15 |  | IGR Office | Not advertised due to no Cash Flow/ cash in the Bank
IGR & Stakeholder Programmes | 25000 | 110044206 | 2017-01-06 |  | 2017-01-15 |  | 2017-02-28 |  | 2017-03-15 |  | IGR Office | Not advertised due to no Cash Flow/ cash in the Bank
Municipal Coorperative Agreements (MIR & Protocol) | 150000 | 111044215 | 2017-01-06 |  | 2017-01-15 |  | 2017-02-28 |  | 2017-03-15 |  | IGR Office | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER FOUR (4)
IGR & Stakeholder Programmes | 25000 | 110044206 | 2016-04-01 |  | 2016-04-12 |  | 2016-04-30 |  | 2016-05-09 |  | IGR Office | Not advertised due to no Cash Flow/ cash in the Bank
Municipal Coorperative Agreements (MIR & Protocol) | 100000 | 111044215 | 2016-04-01 |  | 2016-04-12 |  | 2016-04-30 |  | 2016-05-09 |  | IGR Office | Not advertised due to no Cash Flow/ cash in the Bank
Approved By:………………………………………..
Signature:……………………………………………
Date:…………………………………………………….

## Risk Management
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R30 000-R200 000 INCLUDING ALL APPLICABLE TAXES) FOR THE 2016/ 2017 FINANCIAL YEAR
DEPARTMENT:-RISK MANAGEMENT
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Actual date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Actual date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE (1)
Risk Assessment Workshop ( IT, Fraud) | 200000 | 1110044216 | 2016-07-01 | [7 empty] | Risk Management | Not advertised due to no Cash Flow/ cash in the Bank
Appointment of the Chairperson of the Risk Committee( Remunaration) | 100000 | 1110044216 | 2016-08-01 | [7 empty] | Risk Management | Advertised, closed and awarded as per Evaluation Report
Review risk management framework | 150000 | 1110044216 | 2016-08-15 | [7 empty] | Risk Management | Not yet advertised and TOR not yet received
Procurement of the risk, audit and compliance software | 400000 | 1110044216 | [8 empty] | Risk Management | Tender advertised and closed but no cash flow
QUARTER TWO (2)
Review fraud prevention plan | 150000 | 1110044216 | 2016-10-03 | [7 empty] | Risk Management | Not advertised due to no Cash Flow/ cash in the Bank
Develop the anti-corruption strategy | 150000 | 1110044216 | 2016-10-10 | [7 empty] | Risk Management | Tender advertised and closed but no cash flow
Establishment of the Ethics Hotline | 100000 | 1110044216 | 2016-10-21 | [7 empty] | Risk Management | Not advertised due to no Cash Flow/ cash in the Bank
Approved By:………………………………………..
Signature:……………………………………………
Date:…………………………………………………….
Note on B15: Sakhiwo Nelani: This item will be funded through adjustment budget

## OMM
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R30 000-R200 000 INCLUDING ALL APPLICABLE TAXES) FOR THE 2016/2017 FINANCIAL YEAR
DEPARTMENT:- OMM
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Actual date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Actual date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE
M&E Strategy | 500000 | 1110044128 | 2016-07-01 | 2016-08-01 | 2016-08-30 |  | 2016-09-10 |  | 2016-09-30 |  | OMM | No TOR have been received
QUARTER TWO (2)
QUARTER THREE (3)
M&E SDBIP Monitoring Session for Management | 250000 | 1110044128 | 2016-12-01 |  | 2016-01-15 | [5 empty] | OMM | Not advertised due to no Cash Flow/ cash in the Bank
M&E SDBIP Monitoring Session for Council | 250000 | 1110044128 | 2015-12-01 |  | 2016-01-16 | [5 empty] | OMM | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER FOUR (4)
M&E SDBIP Monitoring Session for Management | 250000 | 1110044128 | 2017-04-01 |  | 2016-04-17 | [5 empty] | OMM | Not advertised due to no Cash Flow/ cash in the Bank
M&E SDBIP Monitoring Session for Council | 250000 | 1110044128 | 2017-04-02 |  | 2016-04-17 | [5 empty] | OMM | Not advertised due to no Cash Flow/ cash in the Bank
Approved By:……………………………
Signature:…………………………………
Date:………………………………………

## CPS UNDER R200K
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R30 000-R200 000 INCLUDING ALL APPLICABLE TAXES) FOR THE 2014 / 2015 FINANCIAL YEAR
DEPARTMENT:-
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Actual date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Actual date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE (1)
Access Control | 250000 | 1 700 440 95 | 2015-08-15 |  | 20/08/2016 |  | 01/09/2016 |  | 15/09/2016 |  | HRM and Dev | Not yet advertised and TOR not yet received
Emplyment Equity Plan | 200000 | 1 700 442 83 | 2015-08-15 |  | 20/08/2016 |  | 01/09/2016 |  | 15/09/2016 |  | HRM and Dev | Advertise and closed
Policy Development and Review | 200000 | 1 700 441 84 | 2015-08-15 |  | 20/08/2016 |  | 01/09/2016 |  | 15/09/2016 |  | HRM and Dev | Advertise and closed
Payroll Employee Self Services | 80000 | NEW VOTE | 2015-08-15 |  | 20/08/2016 |  | 01/09/2016 |  | 15/09/2016 |  | HRM and Dev | Not yet advertised and TOR not yet received
QUARTER TWO (2)
Career Exhibition | 200000 | 17000 | 2015-09-01 |  | 20/09/2016 |  | 10/10/2016 |  | 31/10/2016 |  | HRM and Dev
QUARTER THREE (3)
QUARTER FOUR (4)
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R200 001 and ABOVE- INCLUDING ALL APPLICABLE TAXES) FOR 2016/17 FINANCIAL YEAR FOR THE 2014 / 2015 FINANCIAL YEAR
DEPARTMENT:-
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Actual date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Actual date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE (1)
Hardware infrastructure | 1 200 000 | 507000041 | 30/06/2016 |  | 15/07/2016 |  | 10/08/2016 |  | 15/08/2016 |  | ICT | No TOR have been received
QUARTER TWO (2)
Disaster Recovery and Business Continuity | 1 500 000 | 507000141 | 30/08/2016 |  | 30/09/2016 |  | 20/10/2016 |  | 30/10/2016 |  | ICT | No TOR have been received
Upgrade of Network Infrastructure | 1 000 000 | 507000111 | 30/08/2016 |  | 30/09/2016 |  | 20/10/2016 |  | 30/10/2016 |  | ICT | Advertise and awarded by BAC as per the BEC recommendation
Internal Audit and Risk Management solution | 25 000 | 17000 | 30/08/2016 |  | 30/09/2016 |  | 20/10/2016 |  | 30/10/2016 |  | ICT | Advertise and awarded by BAC as per the BEC recommendation
QUARTER THREE (3)
ICT Governance implementation (Phase 3) | 700 000 | 170004407 | 15/11/2016 |  | 20/11/2016 |  | 10/12/2016 |  | 15/01/2017 |  | ICT | Not advertised due to no Cash Flow/ cash in the Bank
Establishment of ICT centre and Deployment of ICT equipment on thusong Centres | 700 000 | 507000151 | 30/09/2016 |  | 05/10/2016 |  | 27/11/2016 |  | 15/01/2017 |  | ICT | Not advertised due to no Cash Flow/ cash in the Bank
Revamping of Website and Customer care System | 500 000 | 17000 38003 | 10/11/2016 |  | 15/11/2016 |  | 10/12/2016 |  | 15/01/2017 |  | ICT | Not advertised due to no Cash Flow/ cash in the Bank
SCM Solution | 25 000 | 17000 | 10/09/2016 |  | 10/11/2016 |  | 30/11/2016 |  | 10/01/2017 |  | ICT | Not advertised due to no Cash Flow/ cash in the Bank
Project Management System | 25 000 | 17000 | 10/09/2016 |  | 10/11/2016 |  | 30/11/2016 |  | 10/01/2017 |  | ICT | Not advertised due to no Cash Flow/ cash in the Bank
Asset Management System and Fleet Tracking System | 25 000 | 17000 | 10/09/2016 |  | 10/11/2016 |  | 30/11/2016 |  | 10/01/2017 |  | ICT | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER FOUR (4)
Approved By:……………………………
Signature:…………………………………
Date:………………………………………

## CPS ABOVE R200K
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R200 001 and ABOVE- INCLUDING ALL APPLICABLE TAXES) FOR THE 2014 / 2015 FINANCIAL YEAR
DEPARTMENT:-
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Actual date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Actual date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE (1)
Integrated Wellness Programme | 700000 | 1 700 440 35 | 15/09/2016 |  | 30//09/2016 |  | 15/10/2016 |  | 30/10/2016 |  | HRM AND DEV | Advertised, closed and awarded as per Evaluation Report
Coordination of 12 trainings per annum | 875000 | 170044034 | 15/09/2016 |  | 30//09/2016 |  | 15/10/2016 |  | 30/10/2016 |  | HRM AND DEV | Advertised and closed but it is 8 learners.
Individual Performance management System | 650000 | 1700044066 | 2016-08-15 |  | 2016-08-31 |  | 2016-09-15 |  | 30/09/2016 |  | HRM AND DEV | Not yet eavdertised and TOR not received
QUARTER TWO (2)
Coordination of 12 trainings per annum | 875000 | 1700044145 | 15/09/2016 |  | 30//09/2016 |  | 15/10/2016 |  | 30/10/2016 |  | HRM&DEV | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER THREE (3)
Coordination of 12 trainings per annum | 875000 | 170044 | 15/09/2016 |  | 30//09/2016 |  | 15/10/2016 |  | 30/10/2016 |  | HRM&DEV | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER FOUR (4)
Coordination of 12 trainings per annum | 2300000 | 1 700 44 | 15/09/2016 |  | 30//09/2016 |  | 15/10/2016 |  | 30/10/2016 |  | HRM&DEV | Not advertised due to no Cash Flow/ cash in the Bank
Approved By:………………………………………
Signature:………………………………………….
Date:………………………………………………….

## CDS BELOW R200k
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R30 000-R200 000 INCLUDING ALL APPLICABLE TAXES) FOR 2016/17 FINANCIAL YEAR FOR THE 2014 / 2015 FINANCIAL YEAR
DEPARTMENT:-
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Actual date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Actual date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE (1)
Procurement of educational material | 200000 | 1600-44030 | 2016-08-19 |  | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | S Mtshengu | Advertised, closed and awarded as per Evaluation Report
Capacity Building for DRM stakeholders | 200000 | 1600-44030 | 2016-08-19 |  | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | S Mtshengu | Advertised, closed and awarded as per Evaluation Report
Commemoration of Districts Traditional Leaders events | 100 000 00 | 160004402 | 2016-08-19 |  | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | M. Nxumalo | Advertised, closed and awarded as per Evaluation Report
Preparations for Saimsa games | 200 000 00 | 160004289 | 2019-08-16 |  | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | M. Nxumalo | Advertised, closed and awarded as per Evaluation Report
Burglar gaurds Nophoyi | 100000 | 5060911 | 2019-08-16 |  | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | Thusong | Advertised, closed and awarded as per Evaluation Report
Burglar gaurds Thabachicha | 80000 | 5060911 | 2019-08-16 |  | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | Thusong | Advertised, closed and awarded as per Evaluation Report
Construction of guard room | 150000 | 5060911 | 2019-08-16 |  | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | Thusong | Not yet advertised and TOR not received
Procurement of educational material for information sharing for Environmental Health Awareness | 200000 | 1600044065 | 2019-08-16 | 2016-07-20 | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | MHS | Advertised, closed and awarded as per Evaluation Report
Procument of catering for Environmental Health Awareness | 100000 | 1600044065 | 2019-08-16 | 2016-07-08 | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | MHS | Not yet advertised and TOR not received
Procurement of a Service Provider to sample air | 100000 | 1600044052 | 2019-08-16 | 2016-08-15 | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | MHS | Not yet advertised and TOR not received
Procument of customer satsfaction Survey Devices | 120000 | 1600-44270 | 2019-08-16 |  | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | N.Qasha | Advertised, closed and awarded as per Evaluation Report
Procurement of educational material | 200000 | 16000-037 | 2019-08-16 |  | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | Customer Care | Advertised, closed and awarded as per Evaluation Report
Procument of Customer Satisfaction survey devices | 100000 | 1600-44270 | 2019-08-16 |  | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | Customer Care | Advertised, closed and awarded as per Evaluation Report
Support for artists - writers and performers - Grahamstown national art festival | 4500000 | 160004402 | 2016-08-19 |  | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | M Nxumalo | Not yet advertised and TOR not received
QUARTER TWO (2)
Initiation Campaign | 650000 | 160004402 | 2016/10/03 |  | 2016-10-05 |  | 2016-10-17 |  | 2016-10-20 |  | M Nxumalo | Not yet advertised and TOR not received
Iscathamiya festival | 150000 | 160004402 | 2016-10-03 |  | 2016-10-06 |  | 2016-10-18 |  | 2016-10-21 |  | M Nxumalo | Not yet advertised and TOR not received
sport Indaba | 45000 | 160004289 | 2016-10-07 |  | 2016-10-09 |  | 2016-10-21 |  | 2016-10-24 |  | M Nxumalo | Not yet advertised and TOR not received
Conduct Nophoyi community profile | 100000 | 1600044103 | 3 October 2016 |  | 17 October 2016 |  | 1 November 2016 |  | 14 November 2016 |  | Thusong | Not yet advertised and TOR not received
Procument of catering for Environmental Health Awareness | 50000 | 1600044065 | 2016-10-31 | 2016-11-15 | 2016-11-21 |  | 2016-11-30 |  | 2016-12-07 |  | MHS | Not yet advertised and TOR not received
Procurement of a Service Provider to sample air | 50000 | 1600044052 | 2016-10-31 | 2016-11-15 | 2016-11-21 |  | 2016-11-30 |  | 2016-12-07 |  | MHS | Not yet advertised and TOR not received
Procumerent of educational material for P.I.E.R program | 100000 | 16000-44037 | 2016-10-10 |  | 2016-10-17 |  | 2016-10-25 |  | 2016-11-01 |  | Fire & Rescue Services | Advertised, closed and awarded as per Evaluation Report
Internal and external capacity building | 105000 | 16000-44037 | 2016-10-03 |  | 2016-10-10 |  | 2016-10-17 |  | 2016-10-21 |  | Fire & Rescue Services | Not yet advertised and TOR not received
Procurement of educational material | 200000 | 1600-44270 | 2016-07-06 |  | 2016-07-20 |  | 2016-08-03 |  | 2016-08-10 |  | Customer Care | Not yet advertised and TOR not received
Procument of Customer Satisfaction survey devices | 100000 | 1600-44270 | 2016-07-06 | 2016-07-08 | 2016-07-13 |  | 2016-07-20 |  | 2016-07-27 |  | Customer Care | Advertised, closed and awarded as per Evaluation Report
QUARTER THREE (3)
Choral Festival | 75000 | 160004402 | 2017-01-11 |  | 2017-01-16 |  | 2017-01-26 |  | 2017-01-30 |  | M Nxumalo | Not advertised due to no Cash Flow/ cash in the Bank
Horse rasing | 40000 | 160004289 | 2017-01-11 |  | 2017-01-13 |  | 2017-01-25 |  | 2017-01-30 |  | M Nxumalo | Not advertised due to no Cash Flow/ cash in the Bank
Training of Community based structures | 70000 | 1600044103 | 6 March 2017 |  | 20 March 2017 |  | 31 March 2017 |  | 10 April 2017 |  | Thusong | Not advertised due to no Cash Flow/ cash in the Bank
Procument of catering for Environmental Health Awareness | 50000 | 1600044065 | 2017-01-31 | 2017-02-15 | 2017-02-21 |  | 2017-02-28 |  | 2017-03-07 |  | MHS | Not advertised due to no Cash Flow/ cash in the Bank
Procurement of a Service Provider to sample air | 100000 | 1600044052 | 2017-01-31 | 2017-02-15 | 2017-02-21 |  | 2017-02-28 |  | 2017-03-07 |  | MHS | Not advertised due to no Cash Flow/ cash in the Bank
Internal and external capacity building | 105000 | 16000-44037 | 2017-01-02 |  | 2017-01-09 |  | 2017-01-17 |  | 2017-01-24 |  | Fire and Rescue Services | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER FOUR (4)
Gospel festival | 150000 | 160004402 | 2016-10-04 |  | 2016-10-07 |  | 2016-10-17 |  | 2016-10-22 |  | M Nxumalo | Not advertised due to no Cash Flow/ cash in the Bank
Initiation Campaigns | 65000 | 160004402 | 2017-04-04 |  | 2017-04-06 |  | 2017-04-18 |  | 2017-04-21 |  | M Nxumalo | Not advertised due to no Cash Flow/ cash in the Bank
Procument of catering for Environmental Health Awareness | 50000 | 1600044065 | 2017-03-03 | 2017-03-10 | 2017-03-24 |  | 2017-03-24 |  | 2017-03-31 |  | MHS | Not advertised due to no Cash Flow/ cash in the Bank
Procurement of a Service Provider to sample air | 50000 | 1600044052 | 2017-03-03 | 2017-03-10 | 2017-03-24 |  | 2017-03-24 |  | 2017-03-31 |  | MHS | Not advertised due to no Cash Flow/ cash in the Bank
Internal and external capacity building | 105000 | 16000-44037 | 2017-03-03 | 2017-03-10 | 2017-03-24 |  | 2017-03-31 |  | 2017-04-10 |  | Fire & Rescue Services | Not advertised due to no Cash Flow/ cash in the Bank
Procument of Protective clothing for customer care unit staff | 50000 | 1600-44270 | 2017-03-03 | 2017-03-10 | 2017-03-24 |  | 2017-03-31 |  | 2017-04-10 |  | Customer Care | Not advertised due to no Cash Flow/ cash in the Bank
Approved By:………………………………………..
Signature:……………………………………………
Date:…………………………………………………….

## CDS above R200k
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R200 001 and ABOVE- INCLUDING ALL APPLICABLE TAXES) FOR 2016/17 FINANCIAL YEAR FOR THE 2014 / 2015 FINANCIAL YEAR
DEPARTMENT:-
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Actual date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Actual date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE (1)
Riview of Disaster Risk Management Plans | 400000 | 16000-44030 | 2019-08-16 |  | 2026-08-16 |  | 2008-09-16 |  | 2029-09-16 |  | S Mtshengu | Not yet advertised and TOR not received
World Enviornmental Health Day & HPCSA | 500000 | 16000-44065 | 2019-08-16 |  | 2026-08-16 |  | 2008-09-16 |  | 2029-09-16 |  | MHS | Not advertised due to no Cash Flow/ cash in the Bank
Procurement of air sampling equipment | 400000 | 16000-44052 | 2019-08-16 |  | 2026-08-16 |  | 2008-09-16 |  | 2029-09-16 |  | MHS | Not advertised due to no Cash Flow/ cash in the Bank
Procurement of law enforcement documents | 250000 | 16000-037 | 2019-08-16 |  | 2026-08-16 |  | 2008-09-16 |  | 2029-09-16 |  | Fire & Rescue Services | Not advertised due to no Cash Flow/ cash in the Bank
Procument of protactive clothing and uniform | 1450000 | 16000-037 | 2019-08-16 |  | 2026-08-16 |  | 2008-09-16 |  | 2029-09-16 |  | Fire and Rescue Services | Not yet advertised and TOR received on the 03/11/2016
Facislitation of training and appointment of Law Enforcement/ Peace Officers | 225000 | 16000-037 | 2019-08-16 |  | 2026-08-16 |  | 2008-09-16 |  | 2029-09-16 |  | Fire & Rescue Services | Not advertised due to no Cash Flow/ cash in the Bank
Procurement of Fire and Rescue equipment | 500000 | 16000-037 | 2019-08-16 |  | 2026-08-16 |  | 2008-09-16 |  | 2029-09-16 |  | Fire & Rescue Services | Advertise and closed but not yedt awarded due to no cash flow
Erection and fencing of the monument at Nonqulwani Hill memorial site | 250 000 00 | 160004287 | 2019-08-16 |  | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | M. Nxumalo | Not advertised due to no Cash Flow/ cash in the Bank
Support for artists - writers and performers - Grahamstown national art festival | 4500000 | 160004402 | 2016-08-19 |  | 2026-08-16 |  | 2002-09-16 |  | 2009-09-16 |  | M Nxumalo | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER TWO (2)
Mowa memorial site hand over | 250.0000.00 | 160004287 | 2016-10-06 |  | 2016-10-12 |  | 2016-10-25 |  | 2016-10-28 |  | M Nxumalo | Not advertised due to no Cash Flow/ cash in the Bank
O. R Tambo legacy programmes | 350.000.00 | 160004287 | 2016-09-01 |  | 2016-09-14 |  | 2016-09-22 |  | 2016-09-28 |  | M Nxumalo | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER THREE (3)
Facilitate appointment of a service provider to Conduct customer satisfaction surveys | 300000 | 16000-440270 | 2017-01-10 |  | 2017-01-17 |  | 2016-03-17 |  | 2017-03-27 |  | customer care | Not advertised due to no Cash Flow/ cash in the Bank
Search funding for Alfred Nzo documentary | 300 000 00 | 160004287 | 2017-01-10 |  | 2017-01-17 |  | 2016-03-17 |  | 2017-03-27 |  | M Nxumalo | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER FOUR (4)
AlfredNzo Legacy programme | 300 000 00 | 160004287 | 2017-04-03 |  | 2017-04-06 |  | 2017-04-18 |  | 2017-04-21 |  | M Nxumalo | Not advertised due to no Cash Flow/ cash in the Bank
Salga games | 400 000 00 | 160004289 | 2017-04-03 |  | 2017-04-05 |  | 2017-04-17 |  | 2017-04-20 |  | M Nxumalo | Not advertised due to no Cash Flow/ cash in the Bank
Approved By:………………………………………
Signature:………………………………………….
Date:………………………………………………….

## LED UNDER R200K
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R30 000-R200 000 INCLUDING ALL APPLICABLE TAXES) FOR 2016/17 FINANCIAL YEAR FOR THE 2014 / 2015 FINANCIAL YEAR
DEPARTMENT:-
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Actual date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Actual date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE (1)
Procure GIS Equipment | R 150 000. 00 | 50309901 | 2016-02-08 |  | 2016-11-08 |  | 16/08/2016 |  | 2016-06-09 |  | GIS Unit | Not advertised due to no Cash Flow/ cash in the Bank
Procure GIS Awareness Material | R 200 000. 00 | 13000 44163 | 2016-02-08 |  | 2016-11-08 |  | 16/08/2016 |  | 2016-06-09 |  | GIS Unit | Advertised and closed, Awarded
Business plan development and submitted targeting ANDM old projects | R 100 000. 00 | NEW VOTE | 2016-10-08 |  | 17/08/2016 |  | 24/08/2016 |  | 31/08/2016 |  | LED Unit | ToR not received,project cancelled.
QUARTER TWO (2)
Business plan development and submitted targeting ANDM old projects | R 100 000. 00 | NEW VOTE | 14/10/2016 |  | 21/10/2016 |  | 28/10/2016 |  | 2016-07-11 |  | LED Unit | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER THREE (3)
GeoDatabase Development | R 200 000. 00 | NEW VOTE | 2017-06-01 |  | 2017-01-09 |  | 13/01/2017 |  | 20/01/2017 |  | GIS Unit | Advertised, closed and awarded as per Evaluation Report
Business plan development and submitted targeting ANDM old projects | R 100 000. 00 | NEW VOTE | 13/01/2017 |  | 20/01/2017 |  | 27/01/2017 |  | 2017-03-02 |  | LED Unit | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER FOUR (4)
Business plan development and submitted targeting ANDM old projects | R 100 000. 00 |  | 2017-03-04 |  | 2017-10-04 |  | 17/04/2017 |  | 24/04/2017 |  | LED Unit | Not advertised due to no Cash Flow/ cash in the Bank
Approved By:………………………………………..
Signature:……………………………………………
Date:…………………………………………………….

## LED ABOVE R200K
ALFRED NZO DISTRICT MUNICIPALITY PROCUREMENT PLAN
SCHEDULE OF PROCUREMENT PLAN IN RESPECT OF ADVERTISED COMPETITIVE BIDS
(GOODS, INFRASTRUCTURE PROJECTS OR SERVICES BETWEEN R200 001 and ABOVE- INCLUDING ALL APPLICABLE TAXES) FOR 2016/17 FINANCIAL YEAR FOR THE 2014 / 2015 FINANCIAL YEAR
DEPARTMENT:-
Description of goods / services / Infrastructure project | Estimated value | Vote No. | Envisaged date for submission of approved Specification / TOR by HOD to SCM | Actual date for submission of approved Specification / TOR by HOD to SCM | Envisaged date of advertisement in the website, newspapers or other media | Actual date of advertisement in the website, newspapers or other media | Envisaged closing date of bid | Actual closing date of bid | Envisaged date of award | Actual date of award | Responsible office | Status
QUARTER ONE (1)
Ntenetyana Dam Development | 500000 | 13000 50309 | 19/08/2016 |  | 28/8/2016 |  | 2016-12-09 |  | 19/09/2016 |  | LED Unit | Not yet advertised and TOR not received,No budget.
ANDM Contractor Development Programme | 1500000 | NEW VOTE | 15/08/2016 |  | 30/08/2016 |  | 2016-06-09 |  | 14/09/2016 |  | LED Unit | Not yet advertised and TOR not received,No budget.
Training and Mentorship of SMMEs and or Cooperatives in the Fashion Design Industry | R 250 000. 00 | 13000 44150 | 2016-03-08 |  | 2016-11-08 |  | 26/08/2016 |  | 2016-02-09 |  | LED Unit | Advertised, closed and awarded as per Evaluation Report
Acquire machinery for Training | R 750 000.00 | 13000 44150 | 2016-03-08 |  | 2016-11-08 |  | 26/08/2016 |  | 2016-02-09 |  | LED Unit | Advertised, closed and awarded as per Evaluation Report
Implementation of tourism Sector Plan Beach to Berg Corridor development plan | R 400 000. 00 | 13000 44158 | 2016-03-08 |  | 2016-11-08 |  | 26/08/2016 |  | 2016-02-09 |  | LED Unit | Advertised, closed and awarded as per Evaluation Report
District Agri- Parks Programme | R 250 000. 00 | NEW VOTE | 2016-03-08 |  | 2016-11-08 |  | 26/08/2016 |  | 2016-02-09 |  | LED Unit | Advertised, closed and awarded as per Evaluation Report
Collaborative Initiatives and Partnerships | R 250 000. 00 | 1300044307 | 2016-03-08 |  | 2016-11-08 |  | 26/08/2016 |  | 2016-02-09 |  | LED Unit | Pondo Festival Procurement successfully done by ANDM-LED for Ntabankulu Collerbaration.
QUARTER TWO (2)
GIS Systems Intergration | R 500 000. 00 | 13000 4418 | 2016-01-09 |  | 2016-09-08 |  | 15/09/2016 |  | 22/09/2016 |  | GIS Unit | project put on hold,ICT Implementing the project.
Rural Sanitation Data Capture | R 600 000. 00 | 13000 44260 | 2016-01-09 |  | 2016-09-08 |  | 15/09/2016 |  | 22/09/2016 |  | GIS Unit | Advertised, closed and awarded as per BAC and BEC Recommendation
Environmental Information System | R 400 000. 00 | 13000 44260 | 2016-01-09 |  | 2016-09-08 |  | 15/09/2016 |  | 22/09/2016 |  | GIS Unit | Advertised, closed and awarded as per BAC and BEC Recommendation
District Resource Mobilisation | R 500 000. 00 | NEW VOTE | 2016-01-09 |  | 2016-09-08 |  | 15/09/2016 |  | 22/09/2016 |  | LED Unit | Project put on hold
Vuka Alfred Nzo Fund | R 1 000 000. 00 | 13000 44212 | 2016-03-10 |  | 2016-07-10 |  | 24/10/2016 |  | 2016-02-11 |  | LED Unit | Not Advertised, Funds were moved during budget adjusments,Project to be advertised next financial year.
Implementation of tourism Sector Plan Beach to Berg Corridor development | R 450 000. 00 | 13000 44158 | 2016-01-09 |  | 2016-09-08 |  | 15/09/2016 |  | 22/09/2016 |  | LED Unit | Advertised, closed and awarded as per BAC and BEC Recommendation
District Agri- Parks Programme | R 250 000. 00 | NEW VOTE | 2016-01-09 |  | 2016-09-08 |  | 15/09/2016 |  | 22/09/2016 |  | LED Unit | Advertised, closed and awarded as per BAC and BEC Recommendation
Collaborative initiatives and Partnerships | R 500 000. 00 | 1300044307 | 2016-01-11 |  | 2016-09-08 |  | 15/09/2016 |  | 22/09/2016 |  | LED Unit | Funds transferred to Matatiele for Matatiele Collerboration.
QUARTER THREE (3)
Disaster Incidents Mapping | R 500 000. 00 | 1300044260 | 2016-06-01 |  | 2016-01-09 |  | 13/01/2017 |  | 20/01/2016 |  | GIS Unit | Advertised,closed, cancelled
LED Facilities Mapping | R 500 000. 00 | 1300044260 | 2016-06-01 |  | 2016-01-09 |  | 13/01/2017 |  | 20/01/2016 |  | GIS Unit | Advertise, closed, canceolled.
Ntenetyana Dam Development | R 500 000. 00 | NEW VOTE | 13/01/2016 |  | 23/01/2017 |  | 2017-07-02 |  | 15/02/2017 |  | LED Unit | Not advertised due to no Cash Flow/ cash in the Bank
Collaborative Initiatives and Partnerships | R 250 000. 00 | 1300044307 | 13/01/2016 |  | 23/01/2017 |  | 2017-07-02 |  | 15/02/2017 |  | LED Unit | Not advertised due to no Cash Flow/ cash in the Bank
QUARTER FOUR (4)
Collaborative Initiatives and Partnerships | R 250 000.00 | 1300044307 | 13/01/2017 |  | 23/01/2017 |  | 07/02/2017 |  | 15/02/2017 |  | LED Unit | Not advertised due to no Cash Flow/ cash in the Bank
District Resource Mobilisation | R 50 000.00 | NEW VOTE | 13/01/2017 |  | 23/01/2017 |  | 07/02/2017 |  | 15/02/2017 |  | LED Unit | Not advertised due to no Cash Flow/ cash in the Bank
Approved By:………………………………………
Signature:………………………………………….
Date:………………………………………………….